## ciptax
Schedule 1
Capital Improvements Program
PROJECTED MUNICIPAL PROPERTY TAX IMPACT
Capital Expenditures | [7 empty] | 2011-12 | 2012-13 | 2013-14 | 2014-15 | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
Debt service on outstanding bonds | [7 empty] | 431025 | 425405.5 | 472025.5 | 461396.75 | 449873 | 435466 | 426650 | 155525 | 154150 | 157575 | 155806 | 156681
Transfer to capital reserve funds | [7 empty] | 538960 | 937000 | 974000 | 1077000 | 1446000 | 1612000 | 1712000 | 1780000 | 1800000 | 1910000 | 1920000 | 1945000
Issuance of New Debt (see below) | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 245438 | 268751 | 426177 | 600094 | 589825 | 665062
Total property tax financing of capital expenditures | [7 empty] | 969985 | 1362405.5 | 1446025.5 | 1538396.75 | 1895873 | 2047466 | 2384088 | 2204276 | 2380327 | 2667669 | 2665631 | 2766743
CIP Major Projects Issuance of New Debt | [7 empty] | 2011-12 | 2012-13 | 2013-14 | 2014-15 | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2020-21 | 2022-23
South Fire Station (20 Yr) | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27438 | 163501 | 160751 | 158001 | 155251
Highway Garage - Replacement (20 Yr) | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 245438 | 241313 | 237188 | 233063 | 228935 | 224813
SLE Mayflower & McQuestion Rds (15 YRS) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 25488 | 206280 | 202889 | 199498
Library (30 Yr) | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85500
Total property tax financing of CIP major projects | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 245438 | 268751 | 426177 | 600094 | 589825 | 665062
Capital Reserve Funding
|  | Historical Funding of CRF | [5 empty] | 2012-13: Historic Funding; 2015-16: Historic Funding; 2020-21: Projected Funding
Capital Reserve Fund | balance 7/1/08 | 2001-02 | 2002-03 | 2003-04 | 2004-05 | 2005-06 | 2006-07 | 2008-09 | 2009-10 | 2010-11 | 2011-12 | 2012-13 | 2013-14 | 2014-15 | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23
Ambulance | 208361.69 | 35000 | 35000 | 12000 | 15000 | 60000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 12000 | 50000 | 60000 | 85000 | 115000 | 80000 | 80000 | 80000 | 80000 | 80000
Athletic Field Development | 95244.31 | 75000 | 100000 | 50000 | 100000 | 75000 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bridge Replacement * | 0 | 0 | 25000 | 57000 | 335000 | 60000 | 20000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Communications Equipment | 38984.72 | 35000 | 35000 | 25000 | 10000 | 25000 | 10000 | 35000 | 0 | 0 | 0 | 10000 | 10000 | 25000 | 146000 | 182000 | 185000 | 150000 | 70000 | 70000 | 70000 | 70000
Computer Equipment | 112127.52 | 25000 | 25000 | 15000 | 0 | 50000 | 26000 | 10000 | 10000 | 5000 | 0 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000
Drainage Improvements * | 0 | 128000 | 38000 | 53000 | 125000 | 110000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DW Highway Intersection Improvements | 780724.83 | 50000 | 50000 | 90000 | 60000 | 80000 | 115000 | 100000 | 50000 | 0 | 25000 | 25000 | 25000 | 50000 | 50000 | 50000 | 50000 | 75000 | 75000 | 75000 | 100000 | 125000
Fire Equipment | 523223.8 | 177000 | 177000 | 198000 | 200000 | 200000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 75000 | 95000 | 160000 | 192000 | 250000 | 275000 | 350000 | 350000 | 350000
Highway Equipment | 357553.18 | 160000 | 175000 | 175000 | 175000 | 225000 | 145000 | 150000 | 75000 | 168000 | 176960 | 250000 | 300000 | 300000 | 300000 | 300000 | 325000 | 350000 | 415000 | 450000 | 450000 | 450000
Land Bank | 484146.23 | 210000 | 200000 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Landfill | 0 | 1232000 | 50000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Library Construction | 0 | 600000 | 493992 | 480245 | 95044 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Library Bld Maintenance | 26169.08 | 2000 | 2000 | 2000 | 2000 | 2000 | 1000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 17000 | 10000 | 35000 | 35000 | 50000 | 45000 | 45000 | 45000 | 45000
Northwest Fire Station *** | 0 | 85000 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Playground Equipment | 58789.92 | 25000 | 35000 | 35000 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Real Estate Reappraisal | 6652.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000
Road Improvements | 782203.25 | 375000 | 215000 | 225000 | 300000 | 265000 | 190647 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Salt Shed | 15058.21 | 56000 | 56000 | 56000 | 30000 | 15000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sewer Line Extension | 915565.62 | 100000 | 100000 | 100000 | 100000 | 175000 | 115000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sidewalks and Bike Paths * | 0 | 30000 | 30000 | 30000 | 30000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Road Infrastructure CRF | 1108582.79 | [6 empty] | 150000 | 525000 | 0 | 185000 | 400000 | 400000 | 400000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000
Solid Waste Disposal | 49130.01 | 0 | 0 | 0 | 0 | 25000 | 10000 | 90000 | 75000 | 40000 | 0 | 50000 | 75000 | 75000 | 45000 | 65000 | 100000 | 125000 | 150000 | 150000 | 135000 | 135000
Fire Station | 0 | 71000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GIS |  | Historic Funding 2014-15: 10000; Historic Funding 2015-16: 65000; Historic Funding 2016-17: 65000; Projected Funding 2017-18: 20000; Projected Funding 2018-19: 20000; Projected Funding 2019-20: 20000; Projected Funding 2020-21: 20000; Projected Funding 2021-22: 20000; Projected Funding 2022-23: 20000
Traffic Signal Pre-emption System | 20048.44 | 0 | 0 | 85000 | 5000 | 12000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000 | 30000 | 20000 | 10000 | 10000 | 10000 | 10000
Wastewater Treatment Facility** | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Wastewater Treatment System** | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capital Reserve Fund Transfers | 6826515.95 | 3471000 | 1841992 | 1713245 | 1582044 | 1589000 | 857647 | 1382000 | 887000 | 365000 | 538960 | 937000 | 974000 | 1052000 | 1431000 | 1602000 | 1702000 | 1770000 | 1790000 | 1900000 | 1910000 | 1935000
Expendable Trust Funds
Milfoil | 10905 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 15000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000
Total property tax financing | [9 empty] | 365000 | 538960 | 937000 | 974000 | 1077000 | 1446000 | 1612000 | 1712000 | 1780000 | 1800000 | 1910000 | 1920000 | 1945000
Sewer Fund
Sewer Infrastructure Improvements | 955575.82 |  |  |  |  | 5650000 |  | 450000 | 500000 | 350000 | 225000 | 25000 | 25000 | 25000 | 75000 | 75000 | 300000 | 350000 | 375000 | 400000 | 375000 | 350000
Total CRF & Expandable Trust Funds | 6837420.95 | 3471000 | 1841992 | 1713245 | 1582044 | 7239000 | 867647 | 1832000 | 1387000 | 715000 | 763960 | 962000 | 999000 | 1102000 | 1521000 | 1687000 | 2012000 | 2130000 | 2175000 | 2310000 | 2295000 | 2295000
Breakdown of Funding
General Fund Expandable Trust | 10493.04 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
General Fund Capital Reserve Deposits | 6577882 | 3471000 | 1841992 | 1713245 | 1582044 | 1589000 | 857647 | 891000 | 1232000 | 1516000 | 1601000 | 1626000 | 1626000 | 1676000
Sewer Fund Capital Reserve Deposits | 667547 | 0 | 0 | 0 | 0 | 5650000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 7255922.04 | 3471000 | 1841992 | 1713245 | 1582044 | 7239000 | 867647 | 891000 | 1232000 | 1516000 | 1601000 | 1626000 | 1626000 | 1676000
Capital Reserve Spending
|  | Historical Spending of CRF | [6 empty] | Projected Spending
Capital Reserve Fund | balance 7/1/07 | 2001-02 | 2002-03 | 2003-04 | 2004-05 | 2005-06 | 2006-07 | 2007-08 | 2008-09 | 2009-10 | 2010-11 | 2011-12 | 2012-13 | 2013-14
Ambulance | 150981 | 0 | -35000 | 0 | 0 | -117701 | 0 | -135000 | 0 | 0 | -135000 | 0 | -140000 | 0
Athletic Field Development | 168435 | 0 | -9053.25 | -239194 | -27046 | 0 | 0 | -90000 | -300000 | -100000 | -350000 | -150000 | 0 | 0
Bridge Replacement | 500203 | -66673 | 0 | -36527 | -33157 | -37177 | -20429 | -385752 | -200000 | -200000 | -118333 | 0 | -20000 | -120000
Communications Equipment | 41391 | 0 | -19232 | 0 | -205319 | 0 | -6518 | -20000 | -40000 | -95000 | 0 | -25000 | 0 | 0
Computer Equipment | 115177 | 0 | 0 | -10800 | -46405.5 | -33361 | 0 | -125000 | -10000 | 0 | -10000 | 0 | -25000 | 0
Drainage Improvements | 565869 | -90613 | -16458 | 0 | 0 | 0 | 0 | 0 | -100000 | 0 | 0 | 0 | 0 | 0
DW Highway Intersection Improvements | 663324 | 0 | 0 | -22963 | -1399 | -400 | -2171 | -90000 | -79900 | -300000 | -600000 | 0 | 0 | 0
Fire Equipment | 674118 | -706763 | 0 | 0 | -384181 | 0 | 0 | 0 | -450000 | -350000 | -155000 | -450000 | -165000 | -450000
Highway Equipment | 430701 | -265524 | -77761 | -131065 | -525838 | -306141 | -112378 | -60000 | -133000 | -290000 | -270000 | -302000 | -236000 | -210000
Land Bank | 465985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Landfill | 0 | -334059.78 | -2393356.8 | -192590 | -1898614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Library Construction | 0 | 0 | -52617 | -1500 | 0 | -2900 | -2639347 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Library Roof | 24149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Northwest Fire Station | 128346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Playground Equipment | 68503 | -52732 | 0 | -56697 | 0 | 0 | 0 | 0 | -20000 | -80000 | 0 | 0 | 0 | 0
Real Estate Reappraisal | 6430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Road Improvements | 1365916 | -175000 | -44532 | -24486 | -28869 | -14084 | -22625 | -1500000 | -90000 | -700000 | 0 | 0 | -50000 | -500000
Salt Shed | 9595 | 0 | 0 | -6007.5 | -13267 | -260000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sewer Line Extension | 754641 | -206677 | -22248 | -23184 | -121709 | -298517 | 0 | 0 | -380000 | 0 | 0 | -20000 | -200000 | -250000
Sidewalks | 242167 | -270709 | 0 | -25666 | -7205 | -11001 | -18326 | -60000 | -50000 | -73440 | -494000 | -25000 | -685000 | -175000
Solid Waste Disposal | 37358 | 0 | 0 | 0 | 0 | 0 | 0 | -35000 | -30000 | -155000 | -245000 | -70000 | -70000 | 0
South Merrimack Fire Station | 145284 | 0 | -59 | -5743 | -10296 | 0 | 0 | 0 | -115000 | -30284 | 0 | 0 | 0 | 0
Traffic Signal Pre-emption System | 19309 | 0 | 0 | -85054 | 0 | 0 | 0 | -5000 | 0 | 0 | 0 | 0 | 0 | 0
WWT Facility CRF | 56173 | -176619.86 | -11107 | 2885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WWT System CRF | 611374 | -202393 | -308822 | -321512 | -335819 | -1654650 | -4311706 | -1337500 | -908600 | -800000 | -1456000 | 0 | -254000 | -1123000
Total property tax financing of capital reserve fund transfers | 7245429 | -2547763.64 | -2990246.05 | -1180103.5 | -3639124.5 | -2735932 | -7133500 | -3843252 | -2906500 | -3173724 | -3833333 | -1042000 | -1845000 | -2828000
Expendable Trust Funds
Milfoil | 10493.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total CRF & Expandable Trust Funds | 7255922.04 | -2547763.64 | -2990246.05 | -1180103.5 | -3639124.5 | -2735932 | -7133500 | -3843252 | -2906500 | -3173724 | -3833333 | -1042000 | -1845000 | -2828000
Breakdown of Funding
General Fund Expandable Trust | 10493.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
General Fund Capital Reserve Deposits | 6577882 | -2168750.78 | -2670317.05 | -861476.5 | -3303305.5 | -1081282 | -2821794 | -2505752 | -1997900 | -2373724 | -2377333 | -1042000 | -1591000 | -1705000
Sewer Fund Capital Reserve Deposits | 667547 | -379012.86 | -319929 | -318627 | -335819 | -1654650 | -4311706 | -1337500 | -908600 | -800000 | -1456000 | 0 | -254000 | -1123000
| 7255922.04 | -2547763.64 | -2990246.05 | -1180103.5 | -3639124.5 | -2735932 | -7133500 | -3843252 | -2906500 | -3173724 | -3833333 | -1042000 | -1845000 | -2828000

## Major with comments funding
Schedule 2
CAPITAL IMPROVEMENTS PROGRAM
MAJOR PROJECTS
No | Department | Project Description |  | Funding Source | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | Back-up on pg | Planning Board recommendation
1 | Fire | South Fire Station ($3,110,000) | R | Fire Station CRF (South) | 0 | 0 | 265000 | 0 | 0 | 0 | 0 | 7 | I - Urgent
|  |  |  | Bond | 0 | 0 | 2195000 | 0 | 0 | 0 | 0
|  |  |  | Private Donation | 0 | 0 | 650000 | 0 | 0 | 0 | 0
3 | Admin/Engineering | Bridge Replacement - Bedford Rd./Baboosic Brook ($4,117,440) | R | Road Infrastructure CRF | 52200 | 611309 | 0 | 0 | 0 | 0 | 0 | 8 | I - Urgent
|  |  |  | Federal Funding | 2016-17: 0; 2017-18: 800000
|  |  |  | State Funding | 208700 | 2445231 | 0 | 0 | 0 | 0 | 0
4 | Admin/Engineering | Bridge Replacement - US 3 (DW Highway)/Baboosic Brook ($3.320,400) | R | Road Infrastructure CRF | 27300 | 60000 |  | 0 | 0 | 0 | 577000 | 9 | I/II (Urgent/ Necessary)
|  |  |  | State Funding | 109100 | 240000 |  | 0 | 0 | 0 | 2307000
5 | Admin/Engineering | Stormwater Drainage Improvements | R | Road Infrastructure CRF | 100000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 10 | II - Necessary
6 | Admin/Engineering | Paving - Infrastructure Improvements ($750,000) | R | Road Improvement (Registration Fee) | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 11 | II - Necessary
|  |  |  | Budget | 625000 | 625000 | 675000 | 725000 | 775000 | 825000 | 875000
7 | Admin/Engineering | Paving - Infrastructure Improvements - Gravel Roads | R | Road Infrastructure CRF | 0 | 0 | 100000 | 100000 | 100000 | 0 | 0 | 12 | III - Desirable
8 | Admin/Engineering | Paving - DW Highway | R | DW Highway CRF | 0 | 0 | 0 | 250000 |  | 0 | 300000 | 13 | III - Desirable
9 | Admin/Engineering | Paving - Infrastructure Improvements Executive Park Drive | R | Road Infrastructure CRF | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 14 | II - Necessary
10 | Highway | Highway Garage Renovation & Replacement | R | Bond | 0 | 3300000 | 0 | 0 | 0 | 0 | 0 | 15 | I - Urgent
11 | Admin./Engineering | Wire Road Intersection Improvements | R | Road Infrastructure CRF | 0 | 0 | 100000 | 400000 | 0 | 0 | 0 | 16 | III - Desirable
12 | Admin/Engineering | Turkey Hill Road Intersection Improvements | R | Road Infrastructure CRF | 2019-20: 200000 | 17 | III - Desirable
13 | Admin/Engineering | Merrimack River Boat Ramp Access Improvement (Formally Griffen St) | R | Road Infrastructure CRF | 0 | 67000 | 0 | 0 | 0 | 0 | 0 | 18 | IV - Deferrable
14 | Admin/Engineering | Seaverns Bridge Canoe Launch Ramp Access Improvement | R | Road Infrastructure CRF | 0 | 0 | 50000 |  | 0 | 0 | 0 | 19 | III - Desirable
15 | Admin/Engineering | Souhegan River Trail | R | Road Infrastructure CRF | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | N/A
|  |  |  | Federal Funding | 436000 | 0 | 0 | 0 | 0 | 0 | 0
16 | Admin/Engineering | Daniel Webster & Woodbury Sidewalks (place holder) * ($105,000) | R | Road Infrastructure CRF |  | 21000 | 0 | 109000 | 0 | 0 | 0 | 21 | II - Necessary
|  |  |  | Federal Funding |  | 84000 | 0 | 436000 | 0 | 0 | 0
17 | Admin/Engineering | Daniel Webster & Baboosic Lake Sidewalks (place holder) * ($152,000) | R | Road Infrastructure CRF |  |  | 0 | 30400 | 0 | 152000 | 0 | 22 | III - Desirable
|  |  |  | Federal Funding |  |  | 0 | 121600 | 0 | 608000 | 0
18 | Admin/Engineering | Baboosic Lake Road Sidewalk (Joppa Road to Madeline Bennett) (place holder) * | R | Road Infrastructure CRF | 2018-19: 0; 2020-21: 0; 2021-22: 42000; 2022-23: 210000 | 23 | III - Desirable
|  |  |  | Federal Funding | 2018-19: 0; 2020-21: 0; 2021-22: 168000; 2022-23: 840000
19 | Admin/Engineering | Sewer Line Extensions (Mayflower and McQuestion Sewer Basins) | R | Bond | 0 | 0 | 0 | 2360000 | 0 | 0 | 0 | 24 | II - Necessary
20 | Library | Parking Lot Repaving/Walkway | R | Library Maintenance CRF | 2016-17: 45000; 2017-18: 0; 2018-19: 0; 2019-20: 0 | 25 | N/A
21 | Library | HVAC | R | Library Maintenance CRF | 2021-22: 0; 2022-23: 100000 | 26
22 | Library | Sprinkler System | R | Library Maintenance CRF | 2021-22: 0; 2022-23: 100000 | 27 | III - Desirable
23 | Library | New Library (place holder) | R | Bond | 0 | 0 | 0 | 0 | 0 | 0 | 6000000 |  | IV - Deferrable
24 | Parks & Recreation | New Athletic Fields (place holder) | A | Bond | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 |  | IV - Deferrable
| TOTAL GENERAL FUND |  |  |  | 1878300 | 8728540 | 4360000 | 5057000 | 1200000 | 2120000 | 13634000
1 | Wastewater | Executive Park Drive Pump Station | N | User Fees State Loan SRF | 0 | 0 | 0 | 0 |  | 1040000 | 0 | 28 | III - Desirable
2 | Wastewater | Wastewater Treatment Plant Phase III and Pump Station Upgrades | R | User Fees State Loan SRF | 0 | 350000 | 0 | 12600000 | 0 | 0 | 0 | 29 | II - Necessary
3 | Wastewater | 4 Year Sanitary Sewer System Evaluation Program` | N | User Fees State Loan SRF | 0 | 150000 | 140000 | 140000 | 145000 | 0 | 0 | 30 | II - Necessary
| TOTAL SEWER FUND |  |  |  | 0 | 500000 | 140000 | 12740000 | 145000 | 1040000 | 0
|  |  |  | CRF | 374500 | 1109309 | 715000 | 1289400 | 300000 | 394000 | 1487000
|  |  |  | Funded through Budget | 625000 | 625000 | 675000 | 725000 | 775000 | 825000 | 875000
|  |  |  | Bonds | 0 | 3300000 | 2195000 | 2360000 | 0 | 0 | 8000000
|  |  |  | Road Improvement (RSA261:153) | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000
|  |  |  | Private Donation | 0 | 0 | 650000 | 0 | 0 | 0 | 0
|  |  |  | State Aid | 317800 | 2685231 | 0 | 0 | 0 | 0 | 2307000
|  |  |  | Federal Aid | 436000 | 884000 | 0 | 557600 | 0 | 776000 | 840000
|  |  |  | User Fees/Bonds | 0 | 500000 | 140000 | 12740000 | 145000 | 1040000 | 0
[5 empty] | 1878300 | 9228540 | 4500000 | 17797000 | 1345000 | 3160000 | 13634000
* Included in CIP just in case we are a recipient of TAP Grant
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
MES -
CRF - $250,000
Taxes - $35,000
Total - $285,000
RFS -
CRF - $50,000 Taxes - $90,000 Total - $140,000
Moved
Moved
MES -
CRF - $250,000
Taxes - $35,000
Total - $285,000
MES -
CRF - $250,000
Taxes - $35,000
Total - $285,000
MES -
CRF - $250,000
Taxes - $35,000
Total - $285,000

## cipminor
Schedule 3
Capital Improvements Program
MINOR PROJECTS
No | Department | Year | Replace SCH | Model |  | Funding Source | Vehicle Replacement Year | Replacement Cost |  | Current Year | YR 1 | YR 2 | YR 3 | YR 4 | YR 5 | YR 6 | YR 7 | YR 8 | YR 9 | YR 10
[10 empty] | 2016/17 | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26 | 2026/27
1 | Assessing |  |  | Revaluation | R | Revaluation CRF | every 5 yrs | 75000 |  | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0
2 | Bld & Grounds | 2004 | 15-20 yrs | 450 4x4 | R | Budget | 2014/15 | 40000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0
2 | Bld & Grounds |  | 15-20 yrs | Small pickup | N | Budget |  |  |  | 0 | 13000 | 0 | 0 | 0 | 0 | 0
3 | Communications |  |  | Communications Recorder | R | Communication CRF |  | 25000 |  | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000
4 | Communications |  |  | Radio Base Stations | R | Communication CRF |  | 120000 |  | 0 | 516000 | 0 | 0 | 0 |  | 120000 | 0 | 0 | 0 | 0
5 | Communications |  |  | Fire Dispatch, Station 1, Radio Base Stations | R | Communication CRF | 2016/17 | 43000 |  | 0 | 43000 | 0 | 0 | 0 | 0 | 0
6 | Communications |  |  | Access Control / Facility Monitoring | R | Communication CRF |  | 30000 |  | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 30000
7 | Communications |  |  | CAD/RMS Server replacement/Dispatch upgrade | R | Communication CRF |  | 25000 |  | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 25000 | 0
8 | Community Development |  |  | GIS Update & Maintenance Program | R | GIS CRF |  |  |  | 135000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
9 | Fire | 2010 | 100k (miles) | F450 Ambulance A1226 (PD CSI) | R | Ambulance CRF ($235,000) | 2017 | 220000 |  | 0 | 235000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 250000
10 | Fire | 2005 | 100k (miles) | F450 Ambulance A220 | R | Ambulance CRF ($235,000) | 2015 | 225000 |  | 0 | 0 | 0 | 0 | 0 | 0 | . | 0 | 235000 | 0 | 0
10 | Fire | 2014 | 100k (miles) | F350 Ambulance A3231 | R | Ambulance CRF | 2020 | 230000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 230000 | 0 | 0 | 0 | 0
11 | Fire | 2008 | 20 yrs | Pumper Engine Sutphen E1 (First Due Dist 1) | R | Fire Equip CRF ($578,000) | 2018 | 578000 |  | 0 | 0 | 0 | 0 | 578000 | 0 | 0 | 0 | 0 | 598000 | 0
12 | Fire | 2013 | 20 yrs | Pumper Engine KME E2 | R | Fire Equip CRF | 2023 | 575000 |  | 2016/17: 0; YR 1 2017/18: 0; YR 2 2018/19: 0; YR 3 2019/20: 0; YR 6 2022/23: 575000
13 | Fire | 1996 | 20 yrs | Pumper Engine International E3 | R | Fire Equip CRF | 2nd Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Fire | 2005 | 20 yrs | Pumper Engine ALF E4 | R | Fire Equip CRF | 2nd Due | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Fire | 2013 | 20 yrs | Pumper Engine KME E2 (First Due Dist 2) | R | Fire Equip CRF ($578,000) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Fire | 2002 | 25 yrs | ALF Ladder Truck | R | Fire Equip CRF ($967,500) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Fire | 2000 | 25 yrs | KME Rescue | R | Fire Equip CRF ($653,500) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Fire | 1988 | 15 yrs | Pickup (1 ton) Forestry Truck F1 | R | Fire Equip CRF ($85,000) | 2017 | 85000 |  | 85000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Fire | 1968 | EOL | Pickup (1 ton) Forestry Truck F2 | R | Fire Equip CRF ($85,500) | 2021 | 85000 |  | 0 | 0 | 0 | 0 | 0 | 85500 | 0 | 0 | 0 | 0 | 0
15 | Fire | 1989 | EOL | Forestry Tanker Truck F3 (5 ton) | R | Fire Equip CRF | 0 | 175000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Fire | 1994 | EOL | Boat Rigid Hull Inflatable B1 | R | Fire Equip CRF ($49.000) | 2020 | 48000 |  | 0 | 0 | 49000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Fire | 1994 | EOL | Boat Inflatable B2 | R | Fire Equip CRF ($15,000) | 2017 | 35000 |  | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Fire | 2002 | 25 yr | Aerial Fire Truck L1 | R | Fire Equip CRF | 2026 | 890000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 890000
19 | Fire | 2003 | EOL | Heavy Rescue Vehicle R1 | R | Fire Equip CRF | 2024 | 595000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 595000 | 0 | 0
20 | Fire | 2001 | EOL | Gator Rescue / Forestry Vehicle |  | Fire Equip CRF | 2025 | 25460 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 25460
21 | Fire | 2014 | 15-20 yrs | Fire Command Vehicle C1 | R | Fire Equip CRF | 2030/31 | 38000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Fire | 2010 | 15 yrs | Fire Command Vehicle | R | Fire Equip CRF ($38,000) | 2026/27 | 38000 |  | 0 | 0 | 0 | 0 | 38000 | 0 | 0 | 0 | 0 | 0 | 35000
19 | Fire | 2002 | 15 yrs | Fire Command Vehicle | R | Fire Equip CRF ($38,000) | 2014/15 | 38000 |  | 2016/17: 0; YR 1 2017/18: 0; YR 2 2018/19: 38000; YR 3 2019/20: 0
20 | Fire | 2015 | 15 yrs | Fire Command Vehicle | R | Fire Equip CRF ($38,000) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Fire | 1998 | 15 yrs | Prevention/Inspection/Education Vehicle | R | Fire Equip CRF ($42,000) | 2019/20 | 42000 |  | 0 | 0 | 42000 | 0 | 0 |  |  |  | 0 | 0 | 0
21 | Fire | 2006 | 15 yrs | 162 SD SC Chassi U1 (1 ton) (6 wheel) | R | Fire Equip CRF ($56,000) | 2025/26 | 56400 |  | 0 | 0 | 0 | 56000 | 0 | 0 | 0 | 0 | 0 | 53000 | 0
22 | Fire | 2000 | EOL | Building Official Vehicle (166) (Used) | R | Budget | 2018/19 | 25000 |  | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Fire | 2000 | EOL | Building Inspector Vehicle (184) (Used) | R | Budget | 2017/18 | 25000 |  | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Fire | 2000 | EOL | Fire Inspector Vehicle (111) (Used) | R | Budget | 2016/17 | 25000 |  | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Fire | 2000 | EOL | Health Officer Vehicle (Used) (182) | R | Budget | 2020/21 | 25000 |  | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0
26 | Fire | 2014 | EOL | Cardiac Defibrillator/Monitor/Transmitter | R | Ambulance CRF | 2022 | 180000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 0 | 0 | 0 | 0
27 | Fire | 2014 | EOL | Automatic Rescue CPR Devices | R | Ambulance CRF | 2022 | 90000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 90000
28 | Fire | 1995 | EOL | Thermal Imaging Rescue Cameras | R | Fire CRF ($120,000) | 2018 | 120000 |  | 40000 | 40000 | 40000 | 0 | 0 | 0 | 0
29 | Fire | NFPA | EOL | Emergency Breathing Air (SCBA) Replacements | R | Fire Equip CRF | 2016 to 2018 | 347000 |  | 28872 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | Fire | 2002 | EOL | Toxic Gas Monitoring Equipment | R | Fire Equip CRF ($24,000) | 2018/21 | 24000 |  | 0 | 0 | 0 | 0 | 24000 | 0 | 0
31 | Fire | 1980 | EOL | Large Diameter Supply Hose | R | Fire Equip CRF ($39,000) | 2019/21 | 39000 |  | 0 | 13000 | 13000 | 13000 | 0 | 0 | 0
32 | Fire | 1980 | EOL | Fire Suppression Hose | R | Fire Equip CRF ($34,000) | 2018/21 | 34000 |  | 0 | 0 | 0 | 34000 | 0 | 0 | 0
33 | Fire |  | EOL | Portable Radios | R | Fire Equip CRF ($298,000) | 2016 to 2018 | 245000 |  | 0 | 0 | 298000 | 0 | 0 | 0 | 0
34 | Fire |  | EOL | Access Control / Facility Monitoring | A | Budget | 2016/17 | 42000 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0
35 | Fire |  | EOL | Hydraulic Rescue Tools (Jaws of Life) | R | Fire Equip CRF | 2025 | 235000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 235000
35 | Fire |  | EOL | Opticom Repair / Replace | R | Traffic Pre-emption CRF | 2017 | 50000 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | Fire |  | EOL | Equipment Trailer | A | Fire Equip CRF | 2016 | 15000 |  | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0
37 | Fire | 2004 | EOL | Special Operation Trailer | R | Fire Equip CRF | 2025 | 25000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0
37 | Fire | 2012 | EOL | Gator Trailer | R | Budget | 2022 | 15000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2022 | 0 | 0 | 0 | 0
38 | Fire | 2011 | EOL | Hazardous Materials Trailer | R | Fire Equip CRF | 2025 | 25000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0
39 | Fire |  |  | Electronic Reader Board | N | Budget |  |  |  | 2016/17: 0; YR 1 2017/18: 0; YR 4 2020/21: 35000
40 | Highway | 1992 | 20 yr | Hotbox, Asphalt | R | Highway Equip CRF | 2023/24 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0
40 | Highway | 2005 | 10 yr | 6 Wheel Dump H-22 | R | Highway Equip CRF | 2016/17 | 150000 | 0 | 0 | 170000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175000
41 | Highway | 2005 | 10 yr | 6 Wheel Dump H-27 | R | Highway Equip CRF | 2016/17 | 150000 | 0 | 0 | 170000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175000
42 | Highway | 1990 | 25 yr | Trailer, Paint | R | Highway Equip CRF | 2017/18 | 15000 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | Highway | 2007 | 10 yr | Mower, Exmark | R | Budget | 2017/18 | 12000 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | Highway | 2002 | 15 yr | Cement Mixer | R | Budget | 2017/18 | 4000 | 0 | 0 |  | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | Highway | 2005 | 10 yr | 6 Wheel Dump H-28 | R | Highway Equip CRF | 2017/18 | 150000 | 0 | 0 | 0 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | Highway | 2005 | 10 yr | 6 Wheel Dump H-34 | R | Highway Equip CRF | 2017/18 | 150000 | 0 | 0 | 0 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | Highway | 2000 | 15 yr | SUV H-1 | R | Highway Equip CRF | 2018/19 | 35000 | 0 | 0 | 35000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | Highway | 2008 | 10 yr | 3/4 T Pickup H-6 | R | Highway Equip CRF | 2018/19 | 35000 | 0 | 0 | 0 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | Highway | 2002 | 10 yr | 6 Wheel Dump H-24 | R | Highway Equip CRF | 2014/15 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170000 | 0 | 0
50 | Highway | 2002 | 10 yr | 6 Wheel Dump H-25 | R | Highway Equip CRF | 2014/15 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170000 | 0 | 0
51 | Highway | 2002 | 10 yr | Tractor H-41 | R | Highway Equip CRF | 2014/15 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95000 | 0 | 0
52 | Highway | 2003 | 10 yr | Mower, Exmark | R | Budget | 2014/15 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0
53 | Highway | 1988 | 25 yr | Trailer | R | Highway Equip CRF | 2015/16 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | Highway | 2001 | 10 yr | 6 Wheel Dump H-31 | R | Highway Equip CRF | 2015/16 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175000 | 0
55 | Highway | 2003 | 10 yr | Loader H-16 | R | Highway Equip CRF | 2015/16 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175000 | 0
49 | Highway | 2002 | 10 yr | 6 Wheel Dump H-21 | R | Highway Equip CRF | 2015/16 | 150000 | 0 | 170000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 0
50 | Highway | 2004 | 10 yr | Mower, Exmark | R | Budget | 2016/17 | 12000 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000
51 | Highway | 2005 | 10 yr | Utility Vehicle H-43 | R | Highway Equip CRF | 2016/17 | 125000 | 0 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000
52 | Highway | 2006 | 10 yr | 3/4 T Pickup H-2 | R | Highway Equip CRF | 2016/17 | 35000 | 0 | 0 | 0 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
53 | Highway | 2006 | 10 yr | 6 Wheel Dump H-20 | R | Highway Equip CRF | 2018/19 | 150000 | 0 | 0 | 0 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | Highway | 2006 | 10 yr | 6 Wheel Dump H-30 | R | Highway Equip CRF | 2018/19 | 150000 | 0 | 0 | 0 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | Highway | 2008 | 10 yr | 1 Ton Dump H-10 | R | Highway Equip CRF | 2018/19 | 60000 | 0 | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0
56 | Highway | 2004 | 15 yr | Tree chipper | R | Highway Equip CRF | 2019/20 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0
57 | Highway | 2006 | 12 yr | Bucket Truck H-18 | R | Highway Equip CRF | 2019/20 | 100000 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0
58 | Highway | 2009 | 10 yr | 6 Wheel Dump H-35 | R | Highway Equip CRF | 2019/20 | 150000 | 0 | 0 | 0 | 0 | 0 | 185000 | 0 | 0 | 0 | 0 | 0 | 0
59 | Highway | 1981 | 25 yr | Trailer, Roller | R | Highway Equip CRF | 2020/21 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0
60 | Highway | 2008 | 12 yr | 3/4 T Pickup H-4 | R | Highway Equip CRF | 2020/21 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0
61 | Highway | 2009 | 10 yr | 6 Wheel Truck H-29 | R | Highway Equip CRF | 2020/21 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 190000 | 0 | 0 | 0 | 0 | 0
62 | Highway | 1996 | 25 yr | Trailer | R | Highway Equip CRF | 2021/22 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0
63 | Highway | 2011 | 10 yr | 1 Ton Dump H-7 | R | Highway Equip CRF | 2021/22 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0
64 | Highway | 2007 | 15 yr | Backhoe/loader H-13 | R | Highway Equip CRF | 2022/23 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 140000 | 0 | 0 | 0 | 0 | 0
65 | Highway | 2010 | 12 yr | 10 Wheel Dump H-33 | R | Highway Equip CRF | 2022/23 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195000 | 0 | 0 | 0 | 0
66 | Highway | 1997 | 25 yr | Grader H-12 | R | Highway Equip CRF | 2023/24 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0
67 | Highway | 1998 | 25 yr | Trailer, wash | R | Highway Equip CRF | 2023/24 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0
68 | Highway | 2008 | 15 yr | Message Board | R | Highway Equip CRF | 2023/24 | 65000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000 | 0 | 0 | 0
69 | Highway | 2008 | 15 yr | Catch Basin Cleaner H-19 | R | Highway Equip CRF | 2023/24 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170000 | 0 | 0 | 0
70 | Highway | 2013 | 10 yr | Mower, Exmark | R | Budget | 2023/24 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0
71 | Highway | 2013 | 10 yr | 1 Ton Dump H-9 | R | Highway Equip CRF | 2023/24 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 0
72 | Highway | 2013 | 10 yr | 1 Ton Dump H-11 | R | Highway Equip CRF | 2023/24 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 0
73 | Highway | 2013 | 10 yr | 1 Ton Dump H-8 | R | Highway Equip CRF | 2023/24 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 0
74 | Highway | 2013 | 10 yr | 6 Wheel Dump H-26 | R | Highway Equip CRF | 2023/24 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170000 | 0 | 0 | 0
75 | Highway | 2012 | 12 yr | 3/4 T Pickup H-5 | R | Highway Equip CRF | 2024/25 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 0 | 0
76 | Highway | 2002 | 25 yr | Trailer | R | Highway Equip CRF | 2027/28 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
77 | Highway | 2012 | 15 yr | Utility Vehicle H-44 | R | Highway Equip CRF | 2027/28 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 | Highway | 2003 | 25 yr | Trailer | R | Highway Equip CRF | 2028/29 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | Highway | 2013 | 15 yr | Hydraulic Power Unit | R | Budget | 2028/29 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | Highway | 2013 | 15 yr | Backhoe/Loader H-17 | R | Highway Equip CRF | 2028/29 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | Highway | 2013 | 15 yr | 6 Wheel Dump H-23 | R | Highway Equip CRF | 2028/29 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
82 | Highway | 2013 | 15 yr | 1 Ton Utility Truck, M-1 | R | Highway Equip CRF | 2028/29 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Highway | 2005 | 25 yr | Trailer | R | Highway Equip CRF | 2030/31 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | Highway | 2011 | 25 yr | Roller, Steel Drum | R | Highway Equip CRF | 2035/36 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | Highway | 2013 | 12 yr | 3/4 T Pickup H-3 | R | Highway Equip CRF | 2025/26 | 35000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 0
67 | Highway |  |  | H-29 Plow and spreader fit up |  | Highway Equip CRF |  |  |  | 0 | 0 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | Highway |  |  | Trailer for Hot Box |  | Budget |  |  |  | 0 | 0 | 14000 | 0 | 0 | 0 | 0
69 | Library |  |  | Book Mobile | A | Budget |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 150000
70 | Library |  |  | Elevator | R | Library Maintenance CRF |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 75000
71 | Library |  |  | Sheetrock repair | R | Library Maintenance CRF |  |  |  | 0 | 0 | 75000 | 0 | 0 | 0 | 0
72 | Parks and Recreation | 2013 |  | F-150 | R | Budget | 2015/16 | 30000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | Parks and Recreation |  |  | Pond Dredging | A | Budget |  |  |  | 0 | 0 | 63791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 | Parks and Recreation |  |  | Netting Twardosky Field | A | Athelitic Field CRF |  |  |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74 | Parks and Recreation |  |  | Dock Replacement | R | Budget |  |  |  | 0 | 0 | 14242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
75 | Police | Var |  | Patrol Vehicles | R | Budget | Yearly | 30000 |  | 111000 | 90000 | 123600 | 127308 | 131127.24 | 135061.0572 | 139112.8889 | 143286.2756 | 147584.8639 | 152012.4098 | 156572.7821
76 | Police | Var |  | Detective Vehicles | R | Budget | every 5 yrs | 25000 |  | 0 | 30000 | 0 | 0 | 0 | 0 | 27000 | 0 | 0 | 0 | 0
77 | Police |  |  | Crime Scene vehicle replacement | R | Budget | every 10 yrs | 100000 |  | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 | Police | 2003 |  | Animal Control Vehicle | R | Budget | 2008/09 | 25000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 | Solid Waste Disposal | 2005 | 10 yr | 100 CY Trailers (4) | R | Solid Waste CRF | Various | 350000 |  | 0 | 70000 | 70000 | 0 | 70000 | 70000 | 0 | 0 | 0 | 0 | 0
79 | Solid Waste Disposal |  | 20 yr | Landfill Slope Mower | N | Solid Waste CRF | 2022/23 | 45000 |  | 0 | 0 | 0 | 45000 | 0 | 0 | 0 | 0 |  |  | 0
80 | Solid Waste Disposal | 1999 | 12yr | Truck Cab & Chassis - Peterbilt Tractor | R | Solid Waste CRF | 2008/9 | 120000 |  | 0 | 0 | 120000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
81 | Solid Waste Disposal | 2005 | 12yr | Truck Cab & Chassis - International Tractor | R | Solid Waste CRF |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 120000
82 | Solid Waste Disposal | 2003 | 15yr | Fork Lift | R | Solid Waste CRF | 2018/20 | 25000 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0
83 | Solid Waste Disposal | 2005 | 12yr | Transfer Station Loader | R | Solid Waste CRF | 2010/11 | 250000 |  | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | Solid Waste Disposal | 2013 | 12yr | Transfer Station Loader | R | Solid Waste CRF |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 300000
84 | Solid Waste Disposal | 2005 | 15yr | Skid Steer Loader | R | Solid Waste CRF | 2011/12 | 32000 |  | 0 | 0 | 0 | 0 | 35000 | 0 | 0 | 0 | 0 | 0
85 | Solid Waste Disposal | 2012 | 15yr | Skid Steer Loader | R | Solid Waste CRF |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 40000
85 | Solid Waste Disposal | 2010 | 10yr | Pickup Trucks w/ Plow | R | Solid Waste CRF |  |  |  | 2016/17: 0; YR 1 2017/18: 0; YR 2 2018/19: 0; YR 3 2019/20: 0; YR 4 2020/21: 35000; YR 5 2021/22: 0
86 | Solid Waste Disposal | 2016 | 10yr | Pickup Trucks w/ Plow | R | Solid Waste CRF | 2020/21 | 35000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
86 | Technology |  |  | Licenses | R | Computer CRF |  |  |  | 30000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | Technology |  |  | Campus WIFI | R | Computer CRF |  |  |  | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0
88 | Town Clerk/Tax Collector |  |  | Computer Equipment | R | Computer CRF |  | 10000 |  | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL GENERAL FUND | [9 empty] | 751872 | 1585000 | 1494633 | 1124308 | 1486127.24 | 795561.0572 | 2153134.8889 | 875286.2756 | 1485044.8639 | 1928012.4098 | 2193572.7821
1 | Wastewater Treatment | 2017 |  | Manhole/Sewer Rehabilitation | R | User Fees |  | 25000 |  | 25000 | 25000 | 82000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000
2 | Wastewater Treatment | 2017 | 10 | CCTV Camera Equipment for Sewer System | R | User Fees |  |  |  | YR 1 2017/18: 98000
3 | Wastewater Treatment | 2017 | 5 | 5 year Sewer System Evaluation Program | N | User Fees
4 | Wastewater Treatment | 2012 | 5 | Bobcat Skid Steer Loaders | R | User Fees | 2017/18 | 40000 |  | YR 1 2017/18: 40000
5 | Wastewater Treatment | 2016 | 20 | Bobcat Toolcat, trailer and accessories-X Country Sewer Maintenance | A | User Fees | 2015/16 | 75000
6 | Wastewater Treatment | 2013 | 25 | Penn Valley pumps | A | User Fees | 2013/14 | 55000
7 | Wastewater Treatment | 2014 | 25 | Thorntons Ferry Pump Station grinder | R | User Fees | 2014/15 | 50000
8 | Wastewater Treatment | 2002 | 15 | Camera/Sewer Maintenance E-350 Cut Away truck 16' box | R | User Fees | 2016/17 | 32000 |  | 2016/17: 32000
9 | Wastewater Treatment | 2005 | 15 | Explorer | R | User Fees | 2020/21 | 32000 |  | 0 | 0 | 0 | 0 |  | 32000 | 0 | 0 | 0 | 0 | 0
10 | Wastewater Treatment | 2007 | 15 | Explorer | R | User Fees | 2021/22 | 30000 |  | YR 3 2019/20: 30000
11 | Wastewater Treatment | 2005 | 15 | Sewer Vacuum Truck | R | User Fees | 2020/21 | 300000 |  | YR 3 2019/20: 300000
12 | Wastewater Treatment | 2021 | 20 | Compost screener | R | User Fees |  |  |  | YR 2 2018/19: 200000
13 | Wastewater Treatment | 2006 | 15 | 3- Cat938 loaders | R | User Fees | 2018/19 | 600000 |  | YR 4 2020/21: 200000; YR 5 2021/22: 200000; YR 6 2022/23: 200000
14 | Wastewater Treatment |  | 3 | 3- tires for 938 front end loaders | R | User Fees | 2016/17 | 36000 |  | 2016/17: 12000; YR 1 2017/18: 12500; YR 2 2018/19: 13000; YR 4 2020/21: 13000; YR 5 2021/22: 13500; YR 6 2022/23: 14000
15 | Wastewater Treatment |  | 10 | 3-Hypochlorite pumps | R | User Fees | 2016/17 | 12000 |  | 2016/17: 13500
16 | Wastewater Treatment |  | 10 | 2- MAU for Compost bld. heating | R | User Fees | 2016/17 | 90000 |  | 2016/17: 90000
17 | Wastewater Treatment |  | 15 | Emergency generator for P. Square PS | R | User Fees | 2016/17 | 50000 |  | 2016/17: 50000
18 | Wastewater Treatment |  | 10 | Overhead Door adjustment and opener | R | User Fees | 2016/17 | 10000 |  | 2016/17: 10000
19 | Wastewater Treatment |  | 10 | 8-Overhead Door Opener Replacements | R | User Fees | 2016/17 | 28000 |  | 2016/17: 28000
20 | Wastewater Treatment |  | 20 | Overhead Door and opener | R | User Fees | 2016/17 | 12000 |  | 2016/17: 12000
21 | Wastewater Treatment |  | 15 | Replacement centrifugal drain pump | R | User Fees | 2016/17 | 5500 |  | 2016/17: 5500
22 | Wastewater Treatment |  | 10 | Replacement instrumentation controllers and probes | R | User Fees | 2016/17 | 10000 |  | 0 | 37000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL SEWER FUND | [9 empty] | 278000 | 212500 | 295000 | 355000 | 238000 | 270500 | 239000 | 25000 | 25000 | 25000 | 25000
1 | Cable Television |  |  | Other CATV Equipment | R | Franchise Fees |  |  |  | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 0 | 0 | 0 | 0
2 | Cable Television |  |  | Software and Licenses | R | Franchise Fees |  | 10000 |  | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Cable Television |  |  | Matthew Thornton room equipment Upgrades | A | Franchise Fees |  |  |  | YR 2 2018/19: 20000; YR 3 2019/20: 10000
4 | Cable Television |  |  | Town Hall Memorial Conference Room Equipment | R | Franchise Fees |  | 10000 |  | 0 | 0 | 10000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0
5 | Cable Television |  |  | Media Staff Hardware | R | Franchise Fees |  | 10000 |  | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0
6 | Cable Television |  |  | Public Access Cameras and Audio Equipment | R | Franchise Fees |  | 10000 |  | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0
7 | Cable Television |  |  | Replace Cablecast / WebCast Devices | R | Franchise Fees |  | 30000 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Cable Television |  |  | Remote Equipment | R | Franchise Fees |  | 30000 |  | 0 | 0 | 0 | 20000 | 0 |  | 0 | 0 | 0 | 0 | 0
9 | Cable Television |  |  | Public Access Studio Lighting | R | Franchise Fees |  | 25000 |  | 2016/17: 10000; YR 1 2017/18: 0; YR 2 2018/19: 0; YR 3 2019/20: 0; YR 4 2020/21: 0
10 | Cable Television |  |  | Public Access Cameras and Video Switcher | R | Franchise Fees |  | 10000 |  | 2016/17: 20000; YR 1 2017/18: 0; YR 2 2018/19: 0; YR 3 2019/20: 0; YR 4 2020/21: 0; YR 5 2021/22: 0
11 | Cable Television |  |  | Public Access File Storage (Server) | R | Franchise Fees |  | 10000 |  | 2016/17: 0; YR 1 2017/18: 0; YR 2 2018/19: 0; YR 3 2019/20: 0; YR 4 2020/21: 0
12 | Cable Television |  |  | Public Access Editing Systems | R | Franchise Fees |  | 25000 |  | 2016/17: 10000; YR 1 2017/18: 0; YR 2 2018/19: 0; YR 3 2019/20: 0; YR 4 2020/21: 0
13 | Cable Television |  |  | Lower Power FM Equipment | R | Franchise Fees |  | 20000 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total CATV FUND | [8 empty] | 50000 | 50000 | 50000 | 50000 | 50000 | 10000 | 10000 | 0 | 0 | 0 | 0
[10 empty] | 1079872 | 1847500 | 1839633 | 1529308 | 1774127.24 | 1076061.0572 | 2402134.8889 | 900286.2756 | 1510044.8639 | 1953012.4098 | 2218572.7821 | 0 | 0
[6 empty] | CRF | Cap Reserve |  |  | 628872 | 1452000 | 1095000 | 978000 | 1305000 | 660500 | 1837022 | 680000 | 1325460 | 1776000 | 2025000 | 0 | 0
[6 empty] | Funded through Budget | Funded through Budget |  |  | 123000 | 133000 | 399633 | 146308 | 181127.24 | 135061.0572 | 316112.8889 | 195286.2756 | 159584.8639 | 152012.4098 | 168572.7821 | 0 | 0
[6 empty] | User Fees/Bonds | User Fees WWTF |  |  | 278000 | 212500 | 295000 | 355000 | 238000 | 270500 | 239000 | 25000 | 25000 | 25000 | 25000 | 0 | 0
[6 empty] | Cable Franchise Fees | Franchise Fees |  |  | 50000 | 50000 | 50000 | 50000 | 50000 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 1079872 | 1847500 | 1839633 | 1529308 | 1774127.24 | 1076061.0572 | 2402134.8889 | 900286.2756 | 1510044.8639 | 1953012.4098 | 2218572.7821 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## South Fire (2)
Capital Improvements Program
PROJECT REQUEST FORM
1. Description of Project: SOUTH FIRE STATION PROJECT
Replace the South Merrimack, District Fire Station
2a. Was this same project reflected in the prior CIP? Yes
2b. If 2a = yes, indicate areas of significant changes reflected in this Project Request Form
and briefly explain why the changes have been made: cost X ; year X ; scope __; none __
(check all that apply)
Explanation:
The replacement of this station is urgent, the fire department will be looking to have an outside firm complete a department study to include a review of all current fire stations, response capabilities and assess the departments operational abilities for current and projected community growth. From this study we are looking for recommendations to meet the needs of the community to include station locations and staffing for future planning. In order to ensure that the monies for a fire station are expended to their utmost benefit to the community this study by an outside organization is imparative and would be benificial to the community.
3. Expected Useful Life: 50+ years with proper maintenance and care
4. Explanation of Need:
The South Fire Station originally constructed in 1973 as a two bay garage to house only fire apparatus. With the need for increased emergency protection within the South section of the community, the addition of low cost living areas were added to the station in 1987, which would allow permanent emergency personnel to occupy the structure meeting the emergent needs of a growing community with industrial/commercial growth continuing in the community, with the Merrimack Premium Outlet Mall increased residential single family homes now with the ability of adding ADUs that can be used as rental income, Nanocomp, Laidlaw Freight, and future build out in the North end of the community this need is growing each day.
The process of upgrading or replacing the South Fire Station has been in the works for the last 16 plus years. During this time and budget restraints have limited the spending of monies to upgrade the structure in anticipation of the construction of a new building. The building is currently in need of major repair from deterioration due to its age, code compliance, insufficient space for emergency training, administrative activities, proper storage of apparatus and equipment to name a few. The facility currently does not meet the need of ADA, or an equal opportunity employer, (as it has no accommodations for female employees) and a very limited fire protection system. We currently have on staff female fulltime employee that at this point is not able to rotate through Station 2 as her other male counterparts due to accommodations. This will be an issue in the very near future due to discrimination.
The construction of a new station project is currently not projecting additional fire personnel, although the projected growth of the community commercial/industrial and the completion of the airport access road will increase the need for additional emergency services throughout the town.
5. Estimated Cost:
Design | 65000
Engineering | 85000
Construction | 2310000
Equipment | 650000
Bond issue costs | 0
Temporary housing | 0
Total | 3110000
6. Financing:
Federal/State Grant | 0
Private Grant | 650000
User Fees (Sewer/Water) | 0
Sale of Replaced Asset | 0
Capital Reserve Fund | 265000
Bond Proceeds | 2195000
Property Tax | 0
Total | 3110000
7. Impact on Operating Budget:
Personnel | 37000
Maintenance | 3000
Insurance | 2500
Utilities | 6500
Total | 49000
8. Project Period:
0
0
0
2017-18 | 0
2018-19 | 3110000
2019-20 | 0
2020-21 | 0
Total | 3110000

## Bridge-Bedford Rd.
Capital Improvements Program
PROJECT REQUEST FORM
Project: Bridge Replacement - Bedford Road @ Baboosic Brook
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
Explanation and Need: See attached information sheet.
Estimated Cost:
Design
Engineering - including wetlands mitigation, ROW acquisitions, permits | 381136
Construction | 3866539
Equipment
Trade-In Allowance
Total | 4247675
Financing:
Federal/State Grant (80% State Bridge Aid) FED - $800,000 | 3398140
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund (20%) (Infrastructure CRF) | 849535
Bond Proceeds
Property Tax
Total | 4247675
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2016-17 | 260900
2017-18 | 3856539
2018-19
2019-20
2020-21
2021-22
2022-23
Total | 4117439

## Bridge-US 3
Capital Improvements Program
PROJECT REQUEST FORM
Project: Bridge Replacement - US 3 (DW Highway) @ Baboosic Brook
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
NEW PROJECT
Explanation and Need: See attached information sheet.
Estimated Cost:
Design
Engineering - including wetlands mitigation, ROW acquisitions, permits | 436400
Construction | 2884000
Equipment
Trade-In Allowance
Total | 3320400
Financing:
Federal/State Grant (80% State Bridge Aid) | 2656320
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund (20%) (Infrastructure CRF) | 664080
Bond Proceeds
Property Tax
Total | 3320400
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2016-17 | 136400
2017-18 | 300000
2018-19
2019-20
2020-21
2021-22
2022-23 | 2884000
Total | 436400

## StormwaterDrainage
Capital Improvements Program
PROJECT REQUEST FORM
Project: Stormwater Drainage Improvements
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
Explanation and Need: See attached information sheet.
Estimated Cost:
Design | 30000
Engineering - including wetlands mitigation, ROW acquisitions, permits
Construction | 170000
Equipment
Trade-In Allowance
Total | 200000
Financing: (ANNUAL)
Federal/State Grant
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund (Infrastructure CRF) | 200000
Bond Proceeds
Property Tax
Total | 200000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2016-17 | 100000
2017-18 | 200000
2018-19 | 200000
2019-20 | 200000
2020-21 | 200000
2021-22 | 200000
2022-23 | 200000
Total | 1300000

## Paving
Capital Improvements Program
PROJECT REQUEST FORM
Paving - Infrastructure Improvements
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
Explanation and Need: See attached information sheet. See Sunset Shores Project
Estimated Cost:
Design
Engineering - including wetlands mitigation, ROW acquisitions, permits
Construction | 750000
Equipment
Trade-In Allowance
Total
Financing: (ANNUAL)
Federal/State Grant
Private Grant
User Fees (Road Improvement Registration Fee) | 125000
Sale of Replaced Asset
Capital Reserve Fund
Bond Proceeds
Property Tax | 625000
Total | 750000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2016-17 | 750000
2017-18 | 750000
2018-19 | 800000
2019-20 | 850000
2020-21 | 900000
2021-22 | 950000
2022-23 | 1000000
Total | 6000000

## Paving Gravel Roads
Capital Improvements Program
PROJECT REQUEST FORM
Project: Paving - Gravel Roads
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: X Year: Scope: None: (Check all that apply).
Explanation and Need: See attached information sheet.
Estimated Cost:
Design
Engineering - including wetlands mitigation, ROW acquisitions, permits
Construction | 300000
Equipment
Trade-In Allowance
Total | 300000
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund (Infrastructure CRF) | 300000
Bond Proceeds
Property Tax
Total | 300000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2016-17
2017-18
2018-19 | 100000
2019-20 | 100000
2020-21 | 100000
2021-22
2022-23
Total | 300000

## Paving DW Highway
Capital Improvements Program
PROJECT REQUEST FORM
Project: Paving - Daniel Webster Highway
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: X Year: Scope: None: (Check all that apply).
Explanation and Need: See attached information sheet.
Estimated Cost:
Design
Engineering - including wetlands mitigation, ROW acquisitions, permits
Construction | 550000
Equipment
Trade-In Allowance
Total | 550000
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund (DW Highway Infrastructure Account) | 550000
Bond Proceeds
Property Tax
Total | 550000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2016-17
2017-18
2018-19
2019-20 | 250000
2020-21
2021-22
2022-23 | 300000
Total | 550000

## Paving - Executive Park Dr.
Capital Improvements Program
PROJECT REQUEST FORM
Project: Paving - Executive Park Drive
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
Explanation and Need: See attached information sheet.
Estimated Cost:
Design
Engineering - including wetlands mitigation, ROW acquisitions, permits
Construction | 150000
Equipment
Trade-In Allowance
Total | 150000
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund (Infrastructure CRF) | 150000
Bond Proceeds
Property Tax
Total | 150000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2016-17
2017-18 | 150000
2018-19
2019-20
2020-21
2021-22
2022-23
Total | 150000

## Highway Garage
Capital Improvements Program
PROJECT REQUEST FORM
Project: Highway Garage Renovations/Replacement
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: X Year: X Scope: None: (Check all that apply).
Explanation and Need: See attached information sheet.
Estimated Cost:
Design
Engineering - including wetlands mitigation, ROW acquisitions, permits (10%) | 330000
Construction | 2970000
Equipment
Trade-In Allowance
Total | 3300000
Financing:
Federal/State Grant
Private Grant
User Fees (Unearned Impact Fees)
Sale of Replaced Asset
Capital Reserve Fund
Bond Proceeds | 3300000
Property Tax
Total | 3300000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities | 5000
Total | 5000
Project Period:
2016-17
2017-18 | 3300000
2018-19
2019-20
2020-21
2021-22
2022-23
Total | 3300000

## Wire@DWIntersection
Capital Improvements Program
PROJECT REQUEST FORM
Project: Wire Road Intersection Improvements
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: X Year: Scope: None: (Check all that apply).
Explanation and Need: See attached information sheet.
Estimated Cost:
Design
Engineering - including wetlands mitigation, ROW acquisitions, permits | 100000
Construction | 400000
Equipment
Trade-In Allowance
Total | 500000
Financing:
Federal/State Grant
Private Grant
User Fees (Unearned Impact Fees) (Reeds Ferry Crossing) | 0
Sale of Replaced Asset
Capital Reserve Fund (Infrastructure CRF) | 500000
Bond Proceeds
Property Tax
Total | 500000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2016-17
2017-18
2018-19 | 100000
2019-20 | 400000
2020-21
2021-22
2022-23
Total | 500000

## Turkey Hill Intersection
Capital Improvements Program
PROJECT REQUEST FORM
Project: Turkey Hill Road Intersection Improvements
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: X Year: Scope: None: (Check all that apply).
Explanation and Need: See attached information sheet.
Estimated Cost:
Design
Engineering - including wetlands mitigation, ROW acquisitions, permits
Construction | 200000
Equipment
Trade-In Allowance
Total | 200000
Financing:
Federal/State Grant
Private Grant
User Fees (Unearned Impact Fees) (Reeds Ferry Crossing) | 0
Sale of Replaced Asset
Capital Reserve Fund (Infrastructure CRF) | 200000
Bond Proceeds
Property Tax
Total | 200000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2016-17
2017-18
2018-19
2019-20 | 200000
2020-21
2021-22
2022-23
Total | 200000

## Merrimack River Boat ramp
Capital Improvements Program
PROJECT REQUEST FORM
Project: Merrimack River Boat Ramp Access Improvement
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
New Project.
Explanation and Need: See attached information sheet.
Estimated Cost:
Design | 0
Engineering - including wetlands mitigation, ROW acquisitions, permits | 2000
Construction | 65000
Equipment
Trade-In Allowance
Total | 67000
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund (Infrastructure CRF) | 67000
Bond Proceeds
Property Tax
Total | 67000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2016-17
2017-18 | 67000
2018-19
2019-20
2020-21
2021-22
2022-23
Total | 67000

## Seaverns Bridge Canoe Launch
Capital Improvements Program
PROJECT REQUEST FORM
Project: Seaverns Bridge Canoe Launch Ramp and Access Improvement
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
New Project.
Explanation and Need: See attached information sheet.
Estimated Cost:
Design
Engineering - including wetlands mitigation, ROW acquisitions, permits | 2000
Construction | 48000
Equipment
Trade-In Allowance
Total | 50000
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund | 50000
Bond Proceeds
Property Tax
Total
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2016-17
2017-18 | 0
2018-19 | 50000
2019-20
2020-21
2021-22
2022-23
Total | 50000

## Souhegan River Trail
Capital Improvements Program
PROJECT REQUEST FORM
Project:Souhegan River Trail
Project same as reflected in prior CIP? Yes: No: X
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: X Year: Scope: None: (Check all that apply).
New Project.
Explanation and Need: See attached information sheet.
Estimated Cost:
Design (Complete)
Engineering - including wetlands mitigation, ROW acquisitions, permits
Construction | 586000
Equipment
Trade-In Allowance
Total | 586000
Financing:
Federal/State Grant | 436000
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund (Infrastructure CRF) | 150000
Bond Proceeds
Property Tax
Total | 586000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2016-17 | 586000
2017-18
2018-19
2019-20
2020-21
2021-22
2022-23
Total | 586000

## DW & Woodbury Sidewalks
Capital Improvements Program
PROJECT REQUEST FORM
Project: Sidewalk Construction: DW Highway & Woodbury Street
Project same as reflected in prior CIP? Yes: No: X
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
Explanation and Need: See Attached Information Sheet
Estimated Cost:
Design
Engineering - including wetlands mitigation, ROW acquisitions, permits | 105000
Construction | 545000
Equipment
Trade-In Allowance
Total | 650000
Financing:
Federal/State Grant | 520000
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund | 130000
Bond Proceeds
Property Tax
Total | 650000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2016-17
2017-18 | 105000
2018-19
2019-20 | 545000
2020-21
2021-22
2022-23
Total | 650000

## DW & Baboosic Sidewalks
Capital Improvements Program
PROJECT REQUEST FORM
Project: Sidewalk Construction: DW Highway & Baboosic Lake Road
Project same as reflected in prior CIP? Yes: No: X
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
Explanation and Need: See Attached Information Sheet
Estimated Cost:
Design
Engineering - including wetlands mitigation, ROW acquisitions, permits | 152000
Construction | 760000
Equipment
Trade-In Allowance
Total | 912000
Financing:
Federal/State Grant | 729600
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund
Bond Proceeds
Property Tax | 182400
Total | 912000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2016-17
2017-18
2018-19
2019-20 | 152000
2020-21
2021-22 | 760000
2022-23
Total | 912000

## SIDEWALK BABOOSIC LAKE RD
Capital Improvements Program
PROJECT REQUEST FORM
Project: Sidewalk Construction: Baboosic Lake Road to Middle School
Project same as reflected in prior CIP? Yes: No: X
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
Explanation and Need: See Attached Information Sheet
Estimated Cost:
Design
Engineering - including wetlands mitigation, ROW acquisitions, permits | 210000
Construction | 1050000
Equipment
Trade-In Allowance
Total | 1260000
Financing:
Federal/State Grant | 1008000
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund | 252000
Bond Proceeds
Property Tax
Total | 1260000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2016-17
2017-18
2018-19
2019-20
2020-21
2021-22 | 210000
2022-23 | 1050000
Total | 1260000

## Sewer Line Ext.
Capital Improvements Program
PROJECT REQUEST FORM
Project: Sewer Line Ext.
Project same as reflected in prior CIP? Yes: No: X
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: X Year: Scope: None: (Check all that apply).
New Project.
Explanation and Need: See attached information sheet.
Estimated Cost:
Design (Complete)
Engineering - including wetlands mitigation, ROW acquisitions, permits
Construction
Equipment
Trade-In Allowance
Total | 2360000
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund
Bond Proceeds | 2360000
Property Tax
Total | 2360000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2016-17
2017-18
2018-19
2019-20 | 2360000
2020-21
2021-22
2022-23
Total | 2360000

## parking Lot Paving
Capital Improvements Program
PROJECT REQUEST FORM
1. Description of Project: Repaving of Library Parking Lot
2a. Was this same project reflected in the prior CIP? No
2b. If 2a = yes, indicate areas of significant changes reflected in this Project Request Form
and briefly explain why the changes have been made: cost ; year ; scope __; none __
(check all that apply)
Explanation: Library lot has many potholes and major cracks that can no longer simply be sealed, according to the vendors we
spoke with when calling to schedule a sealing.
3. Expected Useful Life:
4. Explanation of Need: The Library lot has many potholes and major cracks that can no longer simply be sealed. We are
thankful for the help that the DPW has provided to do minor repairs so far, but realize that this is a temporary solution until the lot can be
properly repaved.
5. Estimated Cost: | 45000
Design | 0
Engineering | 0
Construction | 0
Equipment | 0
Bond issue costs | 0
Temporary housing | 0
Total | 0
6. Financing:
Federal/State Grant | 0
Private Grant | 0
User Fees (Sewer/Water) | 0
Sale of Replaced Asset | 0
Capital Reserve Fund | 45000
Bond Proceeds | 0
Property Tax | 0
Total | 45000
7. Impact on Operating Budget:
Personnel | 0
Maintenance | 0
Insurance | 0
Utilities | 0
Total | 0
8. Project Period:
2016-17 | 45000
2017-18 | 0
2018-19
2019-20
2020-21 | 0
2021-22 | 0
2022-23 | 0
Total | 45000

## HVAC Library
Capital Improvements Program
PROJECT REQUEST FORM
1. Description of Project: HVAC Upgrade
2a. Was this same project reflected in the prior CIP? No
2b. If 2a = yes, indicate areas of significant changes reflected in this Project Request Form
and briefly explain why the changes have been made: cost ; year ; scope __; none __
(check all that apply)
Explanation: HVAC system upgrade to accommodate changing technology in that system
3. Expected Useful Life:
4. Explanation of Need: HVAC system runs on older and outdated technology; spot repairs are expensive as current fixtures
are not fitted with the HVAC technology that exists in that field.
5. Estimated Cost: | 100000
Design | 0
Engineering | 0
Construction | 0
Equipment | 0
Bond issue costs | 0
Temporary housing | 0
Total | 0
6. Financing:
Federal/State Grant | 0
Private Grant | 0
User Fees (Sewer/Water) | 0
Sale of Replaced Asset | 0
Capital Reserve Fund | 100000
Bond Proceeds | 0
Property Tax | 0
Total | 100000
7. Impact on Operating Budget:
Personnel | 0
Maintenance | 0
Insurance | 0
Utilities | 0
Total | 0
8. Project Period:
2016-17
2017-18 | 0
2018-19 | 0
2019-20 | 0
2020-21
2021-22
2022-23 | 100000
Total | 100000

## Sprinkler Library
Capital Improvements Program
PROJECT REQUEST FORM
1. Description of Project: Dry Fire Sprinkler System Upgrade
2a. Was this same project reflected in the prior CIP? No
2b. If 2a = yes, indicate areas of significant changes reflected in this Project Request Form
and briefly explain why the changes have been made: cost ; year ; scope __; none __
(check all that apply)
Explanation: Dry Fire Sprinkler system is older technology and leaks.
3. Expected Useful Life:
4. Explanation of Need: Dry Fire Sprinkler system runs on older and outdated technology; spot repairs are expensive as leaks
are common and unpredictable.
5. Estimated Cost: | 100000
Design | 0
Engineering | 0
Construction | 0
Equipment | 0
Bond issue costs | 0
Temporary housing | 0
Total | 0
6. Financing:
Federal/State Grant | 0
Private Grant | 0
User Fees (Sewer/Water) | 0
Sale of Replaced Asset | 0
Capital Reserve Fund | 100000
Bond Proceeds | 0
Property Tax | 0
Total | 100000
7. Impact on Operating Budget:
Personnel | 0
Maintenance | 0
Insurance | 0
Utilities | 0
Total | 0
8. Project Period:
2016-17
2017-18 | 0
2018-19 | 0
2019-20
2020-21
2021-22 | 0
2022-23 | 100000
Total | 100000

## Executive Park Dr. PS
Capital Improvements Program
PROJECT REQUEST FORM
Project: Executive Park Dr. pump station
Project same as reflected in prior CIP? Yes:X No:
If No, indicate area of significant change reflected and briefly explain why the
changes have been made: Cost: Year: FY Scope:
Explanation and Need: See attached information sheet
Estimated Cost:
Design | 156000
Engineering - | 156000
Construction | 624000
Contingency | 104000
Trade-In Allowance
Total | 1040000
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water) State Revolving Loan Fund or Bond | 1040000
Sale of Replaced Asset
Capital Reserve Fund
Bond Proceeds
Property Tax
Total | 1040000
Impact on Operating Budget:
Personnel | 0
Maintenance | 2500
Insurance | 500
Utilities | 4000
Total | 7000
Project Period:
2016-17
2017-18
2018-19
2019-20
2020-21
2021-22 | 1040000
2022-23
Total | 1040000

## Phase III & PS
Capital Improvements Program
PROJECT REQUEST FORM
Project: Phase III plant and TF and Souhgan pump station improvements
Project same as reflected in prior CIP? Yes: No: X
If No, indicate area of significant change reflected and briefly explain why the
changes have been made: Cost: X Year: FY 19/20 Scope: Added TF and
Souhegan pump station projects and adjusted costs for project.
Explanation and Need: See attached information sheet
Estimated Cost:
Design Final | 500000
Engineering - | 975000
Construction | 10500000
Contingency | 625000
Trade-In Allowance
Total | 12600000
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water) State Revolving Loan Fund or Bond | 12600000
Sale of Replaced Asset
Capital Reserve Fund
Bond Proceeds
Property Tax
Total | 12600000
Impact on Operating Budget:
Personnel | 0
Maintenance | -10000
Insurance | 0
Utilities | -50000
Total | -60000
Project Period:
2016-17
2017-18 CRF | 200000
2018-19 CRF | 200000
2019-20 Loan | 12600000
2020-21
2021-22
2022-23
Total | 13000000

## SSSE
Capital Improvements Program
PROJECT REQUEST FORM
Project: Sanitary Sewer System Evaluation
Project same as reflected in prior CIP? Yes: No: X
If No, indicate area of significant change reflected and briefly explain why the
changes have been made: Cost: Year: Scope:
Explanation and Need: A four year evaluation program to determine the
condition of the sewer lines and manholes. There is approximately 90
miles of pipe and 1,500 manhole structures.
Estimated Cost:
Design
Engineering - | 175000
Construction | 400000
Contingency
Trade-In Allowance
Total | 575000
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water) State Revolving Loan Fund or Bond | 575000
Sale of Replaced Asset
Capital Reserve Fund
Bond Proceeds
Property Tax
Total | 575000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2016-17
2017-18 | 150000
2018-19 | 140000
2019-20 | 140000
2020-21 | 145000
2021-22
2022-23
Total | 575000