## ciptax
Schedule 1
Capital Improvements Program
PROJECTED MUNICIPAL PROPERTY TAX IMPACT
Capital Expenditures | [7 empty] | 2011-12 | 2012-13 | 2013-14 | 2014-15 | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | 2023-24
Debt service on outstanding bonds | [7 empty] | 431025 | 425405.5 | 472025.5 | 461396.75 | 449873 | 435466 | 406500 | 155525 | 421038 | 419100 | 411969 | 407481 | 245438
Transfer to capital reserve funds | [7 empty] | 538960 | 937000 | 974000 | 1077000 | 1446000 | 1612000 | 1697000 | 1765000 | 1840000 | 1920000 | 2000000 | 2085000 | 2170000
Issuance of New Debt (see below) | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275825 | 562360 | 550994 | 539628 | 528262 | 923396
Total property tax financing of capital expenditures | [7 empty] | 969985 | 1362405.5 | 1446025.5 | 1538396.75 | 1895873 | 2047466 | 2103500 | 2196350 | 2823398 | 2890094 | 2951597 | 3020743 | 3338834
CIP Major Projects Issuance of New Debt | [7 empty] | 2011-12 | 2012-13 | 2013-14 | 2014-15 | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2020-21 | 2022-23 | 2023-24
Public Safety Complex(20 Yr) | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 334560 | 327904 | 321248 | 314592 | 307936
Highway Garage - Replacement (20 Yr) | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275825 | 0 | 0 | 0 | 0 | 0
SLE Mayflower & McQuestion Rds (15 YRS) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 227800 | 223090 | 218380 | 213670 | 208960
Library (30 Yr) | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 406500
Total property tax financing of CIP major projects | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275825 | 562360 | 550994 | 539628 | 528262 | 923396
Capital Reserve Funding
|  | Historical Funding of CRF | [5 empty] | 2012-13: Historic Funding; 2016-17: Historic Funding; 2020-21: Projected Funding
Capital Reserve Fund | balance 7/1/08 | 2001-02 | 2002-03 | 2003-04 | 2004-05 | 2005-06 | 2006-07 | 2008-09 | 2009-10 | 2010-11 | 2011-12 | 2012-13 | 2013-14 | 2014-15 | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | 2023-24
Ambulance | 208361.69 | 35000 | 35000 | 12000 | 15000 | 60000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 12000 | 50000 | 60000 | 85000 | 115000 | 80000 | 80000 | 80000 | 80000 | 90000 | 90000
Athletic Field Development | 95244.31 | 75000 | 100000 | 50000 | 100000 | 75000 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 25000 | 25000 | 25000
Bridge Replacement * | 0 | 0 | 25000 | 57000 | 335000 | 60000 | 20000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Communications Equipment | 38984.72 | 35000 | 35000 | 25000 | 10000 | 25000 | 10000 | 35000 | 0 | 0 | 0 | 10000 | 10000 | 25000 | 146000 | 182000 | 185000 | 125000 | 125000 | 125000 | 100000 | 100000 | 100000
Computer Equipment | 112127.52 | 25000 | 25000 | 15000 | 0 | 50000 | 26000 | 10000 | 10000 | 5000 | 0 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 45000 | 45000 | 45000
Drainage Improvements * | 0 | 128000 | 38000 | 53000 | 125000 | 110000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DW Highway Intersection Improvements | 780724.83 | 50000 | 50000 | 90000 | 60000 | 80000 | 115000 | 100000 | 50000 | 0 | 25000 | 25000 | 25000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 75000 | 100000 | 100000 | 150000
Fire Equipment | 523223.8 | 177000 | 177000 | 198000 | 200000 | 200000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 75000 | 95000 | 160000 | 192000 | 250000 | 275000 | 275000 | 350000 | 450000 | 450000
Highway Equipment | 357553.18 | 160000 | 175000 | 175000 | 175000 | 225000 | 145000 | 150000 | 75000 | 168000 | 176960 | 250000 | 300000 | 300000 | 300000 | 300000 | 325000 | 400000 | 425000 | 425000 | 450000 | 500000 | 500000
Land Bank | 484146.23 | 210000 | 200000 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Landfill | 0 | 1232000 | 50000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Library Construction | 0 | 600000 | 493992 | 480245 | 95044 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Library Bld Maintenance | 26169.08 | 2000 | 2000 | 2000 | 2000 | 2000 | 1000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 17000 | 10000 | 35000 | 35000 | 75000 | 100000 | 150000 | 150000 | 150000 | 175000
Northwest Fire Station *** | 0 | 85000 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Playground Equipment | 58789.92 | 25000 | 35000 | 35000 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Real Estate Reappraisal | 6652.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 20000 | 20000 | 20000
Road Improvements | 782203.25 | 375000 | 215000 | 225000 | 300000 | 265000 | 190647 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Salt Shed | 15058.21 | 56000 | 56000 | 56000 | 30000 | 15000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sewer Line Extension | 915565.62 | 100000 | 100000 | 100000 | 100000 | 175000 | 115000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sidewalks and Bike Paths * | 0 | 30000 | 30000 | 30000 | 30000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Road Infrastructure CRF | 1108582.79 | [6 empty] | 150000 | 525000 | 0 | 185000 | 400000 | 400000 | 400000 | 600000 | 600000 | 600000 | 550000 | 525000 | 525000 | 490000 | 440000 | 440000
Solid Waste Disposal | 49130.01 | 0 | 0 | 0 | 0 | 25000 | 10000 | 90000 | 75000 | 40000 | 0 | 50000 | 75000 | 75000 | 45000 | 65000 | 100000 | 125000 | 135000 | 150000 | 150000 | 125000 | 135000
Fire Station | 0 | 71000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GIS |  | Historic Funding 2014-15: 10000; Historic Funding 2015-16: 65000; Historic Funding 2016-17: 65000; Historic Funding 2017-18: 20000; Projected Funding 2018-19: 30000; Projected Funding 2019-20: 20000; Projected Funding 2020-21: 10000; Projected Funding 2021-22: 10000; Projected Funding 2022-23: 10000; Projected Funding 2023-24: 10000
Traffic Signal Pre-emption System | 20048.44 | 0 | 0 | 85000 | 5000 | 12000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000 | 15000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000
Wastewater Treatment Facility** | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Wastewater Treatment System** | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capital Reserve Fund Transfers | 6826515.95 | 3471000 | 1841992 | 1713245 | 1582044 | 1589000 | 857647 | 1382000 | 887000 | 365000 | 538960 | 937000 | 974000 | 1052000 | 1431000 | 1602000 | 1687000 | 1755000 | 1830000 | 1910000 | 1990000 | 2075000 | 2160000
Expendable Trust Funds
Milfoil | 10905 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 15000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000
Total property tax financing | [6 empty] | 867647 |  |  | 365000 | 538960 | 937000 | 974000 | 1077000 | 1446000 | 1612000 | 1697000 | 1765000 | 1840000 | 1920000 | 2000000 | 2085000 | 2170000
Sewer Fund
Sewer Infrastructure Improvements | 955575.82 |  |  |  |  | 5650000 |  | 450000 | 500000 | 350000 | 225000 | 25000 | 25000 | 25000 | 75000 | 75000 | 300000 | 300000 | 350000 | 350000 | 350000 | 350000 | 350000
Total CRF & Expandable Trust Funds | 6837420.95 | 3471000 | 1841992 | 1713245 | 1582044 | 7239000 | 867647 | 1832000 | 1387000 | 715000 | 763960 | 962000 | 999000 | 1102000 | 1521000 | 1687000 | 1997000 | 2065000 | 2190000 | 2270000 | 2350000 | 2435000 | 2520000
Breakdown of Funding
General Fund Expandable Trust | 10493.04 | Historical Funding of CRF 2001-02: 0; Historical Funding of CRF 2002-03: 0; Historical Funding of CRF 2003-04: 0; Historical Funding of CRF 2004-05: 0; Historical Funding of CRF 2005-06: 0; Historical Funding of CRF 2006-07: 10000; Historical Funding of CRF 2008-09: 0; Historic Funding 2009-10: 0; Historic Funding 2010-11: 0; Historic Funding 2011-12: 0; Historic Funding 2012-13: 0; Historic Funding 2013-14: 0; Historic Funding 2014-15: 0
General Fund Capital Reserve Deposits | 6577882 | Historical Funding of CRF 2001-02: 3471000; Historical Funding of CRF 2002-03: 1841992; Historical Funding of CRF 2003-04: 1713245; Historical Funding of CRF 2004-05: 1582044; Historical Funding of CRF 2005-06: 1589000; Historical Funding of CRF 2006-07: 857647; Historical Funding of CRF 2008-09: 891000; Historic Funding 2009-10: 1232000; Historic Funding 2010-11: 1516000; Historic Funding 2011-12: 1601000; Historic Funding 2012-13: 1626000; Historic Funding 2013-14: 1626000; Historic Funding 2014-15: 1676000
Sewer Fund Capital Reserve Deposits | 667547 | Historical Funding of CRF 2001-02: 0; Historical Funding of CRF 2002-03: 0; Historical Funding of CRF 2003-04: 0; Historical Funding of CRF 2004-05: 0; Historical Funding of CRF 2005-06: 5650000; Historical Funding of CRF 2006-07: 0; Historical Funding of CRF 2008-09: 0; Historic Funding 2009-10: 0; Historic Funding 2010-11: 0; Historic Funding 2011-12: 0; Historic Funding 2012-13: 0; Historic Funding 2013-14: 0; Historic Funding 2014-15: 0
| 7255922.04 | Historical Funding of CRF 2001-02: 3471000; Historical Funding of CRF 2002-03: 1841992; Historical Funding of CRF 2003-04: 1713245; Historical Funding of CRF 2004-05: 1582044; Historical Funding of CRF 2005-06: 7239000; Historical Funding of CRF 2006-07: 867647; Historical Funding of CRF 2008-09: 891000; Historic Funding 2009-10: 1232000; Historic Funding 2010-11: 1516000; Historic Funding 2011-12: 1601000; Historic Funding 2012-13: 1626000; Historic Funding 2013-14: 1626000; Historic Funding 2014-15: 1676000
Capital Reserve Spending
|  | Historical Spending of CRF | [6 empty] | Projected Spending
Capital Reserve Fund | balance 7/1/07 | 2001-02 | 2002-03 | 2003-04 | 2004-05 | 2005-06 | 2006-07 | 2007-08 | 2008-09 | 2009-10 | 2010-11 | 2011-12 | 2012-13 | 2013-14
Ambulance | 150981 | 0 | -35000 | 0 | 0 | -117701 | 0 | -135000 | 0 | 0 | -135000 | 0 | -140000 | 0
Athletic Field Development | 168435 | 0 | -9053.25 | -239194 | -27046 | 0 | 0 | -90000 | -300000 | -100000 | -350000 | -150000 | 0 | 0
Bridge Replacement | 500203 | -66673 | 0 | -36527 | -33157 | -37177 | -20429 | -385752 | -200000 | -200000 | -118333 | 0 | -20000 | -120000
Communications Equipment | 41391 | 0 | -19232 | 0 | -205319 | 0 | -6518 | -20000 | -40000 | -95000 | 0 | -25000 | 0 | 0
Computer Equipment | 115177 | 0 | 0 | -10800 | -46405.5 | -33361 | 0 | -125000 | -10000 | 0 | -10000 | 0 | -25000 | 0
Drainage Improvements | 565869 | -90613 | -16458 | 0 | 0 | 0 | 0 | 0 | -100000 | 0 | 0 | 0 | 0 | 0
DW Highway Intersection Improvements | 663324 | 0 | 0 | -22963 | -1399 | -400 | -2171 | -90000 | -79900 | -300000 | -600000 | 0 | 0 | 0
Fire Equipment | 674118 | -706763 | 0 | 0 | -384181 | 0 | 0 | 0 | -450000 | -350000 | -155000 | -450000 | -165000 | -450000
Highway Equipment | 430701 | -265524 | -77761 | -131065 | -525838 | -306141 | -112378 | -60000 | -133000 | -290000 | -270000 | -302000 | -236000 | -210000
Land Bank | 465985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Landfill | 0 | -334059.78 | -2393356.8 | -192590 | -1898614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Library Construction | 0 | 0 | -52617 | -1500 | 0 | -2900 | -2639347 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Library Roof | 24149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Northwest Fire Station | 128346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Playground Equipment | 68503 | -52732 | 0 | -56697 | 0 | 0 | 0 | 0 | -20000 | -80000 | 0 | 0 | 0 | 0
Real Estate Reappraisal | 6430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Road Improvements | 1365916 | -175000 | -44532 | -24486 | -28869 | -14084 | -22625 | -1500000 | -90000 | -700000 | 0 | 0 | -50000 | -500000
Salt Shed | 9595 | 0 | 0 | -6007.5 | -13267 | -260000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sewer Line Extension | 754641 | -206677 | -22248 | -23184 | -121709 | -298517 | 0 | 0 | -380000 | 0 | 0 | -20000 | -200000 | -250000
Sidewalks | 242167 | -270709 | 0 | -25666 | -7205 | -11001 | -18326 | -60000 | -50000 | -73440 | -494000 | -25000 | -685000 | -175000
Solid Waste Disposal | 37358 | 0 | 0 | 0 | 0 | 0 | 0 | -35000 | -30000 | -155000 | -245000 | -70000 | -70000 | 0
South Merrimack Fire Station | 145284 | 0 | -59 | -5743 | -10296 | 0 | 0 | 0 | -115000 | -30284 | 0 | 0 | 0 | 0
Traffic Signal Pre-emption System | 19309 | 0 | 0 | -85054 | 0 | 0 | 0 | -5000 | 0 | 0 | 0 | 0 | 0 | 0
WWT Facility CRF | 56173 | -176619.86 | -11107 | 2885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WWT System CRF | 611374 | -202393 | -308822 | -321512 | -335819 | -1654650 | -4311706 | -1337500 | -908600 | -800000 | -1456000 | 0 | -254000 | -1123000
Total property tax financing of capital reserve fund transfers | 7245429 | -2547763.64 | -2990246.05 | -1180103.5 | -3639124.5 | -2735932 | -7133500 | -3843252 | -2906500 | -3173724 | -3833333 | -1042000 | -1845000 | -2828000
Expendable Trust Funds
Milfoil | 10493.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total CRF & Expandable Trust Funds | 7255922.04 | -2547763.64 | -2990246.05 | -1180103.5 | -3639124.5 | -2735932 | -7133500 | -3843252 | -2906500 | -3173724 | -3833333 | -1042000 | -1845000 | -2828000
Breakdown of Funding
General Fund Expandable Trust | 10493.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
General Fund Capital Reserve Deposits | 6577882 | -2168750.78 | -2670317.05 | -861476.5 | -3303305.5 | -1081282 | -2821794 | -2505752 | -1997900 | -2373724 | -2377333 | -1042000 | -1591000 | -1705000
Sewer Fund Capital Reserve Deposits | 667547 | -379012.86 | -319929 | -318627 | -335819 | -1654650 | -4311706 | -1337500 | -908600 | -800000 | -1456000 | 0 | -254000 | -1123000
| 7255922.04 | -2547763.64 | -2990246.05 | -1180103.5 | -3639124.5 | -2735932 | -7133500 | -3843252 | -2906500 | -3173724 | -3833333 | -1042000 | -1845000 | -2828000

## Major with comments funding
Schedule 2
CAPITAL IMPROVEMENTS PROGRAM
MAJOR PROJECTS
No | Department | Project Description |  | Funding Source | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | 2023-24 | Back-up on pg | Planning Board recommendation
1 | Fire | Public Safety Complex | R | Fire Station CRF (South) | 0 | 25000 | 240000 | 0 | 0 | 0 | 0 | 8 | II - Necessary
|  |  |  | Budget |  | 25000 | 0 | 0 | 0 | 0 | 0
|  |  |  | Bond | 0 |  | 4095000 | 0 | 0 | 0 | 0
|  |  |  | Private Donation | 0 |  | 650000 | 0 | 0 | 0 | 0
2 | Admin/Engineering | Bridge Replacement - US 3 (DW Highway)/Baboosic Brook ($3.320,000) | R | Road Infrastructure CRF | 60000 | 0 | 0 | 0 | 0 | 604200 | 0 | 9 | I - Urgent
|  |  |  | State Funding | 240000 | 0 | 0 | 0 | 0 | 2415800 | 0
3 | Admin/Engineering | Stormwater Drainage Improvements | R | Road Infrastructure CRF | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 11 | II - Necessary
4 | Admin/Engineering | Paving - Infrastructure Improvements ($750,000) | R | Road Improvement (Registration Fee) | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 13 | II - Necessary
|  |  |  | Budget | 625000 | 675000 | 725000 | 775000 | 825000 | 875000 | 925000
5 | Admin/Engineering | Paving - Infrastructure Improvements - Gravel Roads | R | Road Infrastructure CRF | 0 | 100000 | 100000 | 100000 | 0 | 0 | 0 | 15 | II - Necessary
6 | Admin/Engineering | Paving - DW Highway | R | DW Highway CRF | 2018-19: 50000; 2021-22: 0; 2022-23: 50000; 2023-24: 300000 | 17 | III - Desirable III - Desirable
7 | Admin./Engineering | Wire Road Intersection Improvements (TYP, FY2027) | R | Road Infrastructure CRF | 0 | 0 | 0 | 0 | 0 | 0 | 230425 | 19 | III - Desirable
|  |  |  | Federal Funding | 0 | 0 | 0 | 0 | 0 | 0 | 921700
8 | Admin/Engineering | Turkey Hill Road Intersection Improvements | R | Road Infrastructure CRF | 2019-20: 300000 | 21 | III - Desirable
9 | Admin/Engineering | Merrimack River Boat Ramp Access Improvement (Formally Griffin St) | R | Road Infrastructure CRF | 67000 | 0 | 200000 | 0 | 0 | 0 | 0 | 23 | IV - Deferrable
|  |  |  | Federal Funding | 0 | 0 | 200000 | 0 | 0 | 0 | 0
11 | Admin/Engineering | Seaverns Bridge Canoe Launch Ramp Access Improvement | R | Road Infrastructure CRF | 0 | 50000 |  | 0 | 0 | 0 | 0 | 25 | II - Necessary
12 | Admin/Engineering | Daniel Webster & Woodbury Sidewalks | R | Road Infrastructure CRF | 21000 | 0 | 109000 | 0 | 0 | 0 | 0 | 27 | II - Necessary
|  |  |  | Federal Funding | 84000 | 0 | 436000 | 0 | 0 | 0 | 0
13 | Admin/Engineering | Daniel Webster & Baboosic Lake Sidewalks (place holder) * | R | Road Infrastructure CRF | 0 | 0 | 30400 | 0 | 152000 | 0 | 0 | 29 | III - Desirable
|  |  |  | Federal Funding | 0 | 0 | 121600 | 0 | 608000 | 0 | 0
14 | Admin/Engineering | Baboosic Lake Road Sidewalk (Joppa Road to Madeline Bennett) (place holder) * | R | Road Infrastructure CRF | 0 | 0 | 0 | 0 | 42000 |  | 210000 | 31 | III - Desirable
|  |  |  | Federal Funding | 0 | 0 | 0 | 0 | 168000 | 0 | 840000
15 | Admin/Engineering | Sewer Line Extensions (Mayflower and McQuestion Sewer Basins) | R | Bond | 0 | 0 | 2360000 | 0 | 0 | 0 | 0 | 33 | II - Necessary
17 | Library | Sidewalk | R | Library Maintenance CRF | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 35 | IV - Deferrable
18 | Library | Slate roof | R | Library Maintenance CRF | 0 | 0 | 0 | 0 | 0 | 200000 |  | 36 | IV - Deferrable
19 | Library | Drainage Trench by Children's windows | R | Library Maintenance CRF | 0 | 0 | 0 | 0 | 100000 | 0 |  | 37 | II - Necessary
20 | Library | Elevator | R | Library Maintenance CRF | 2021-22: 0; 2022-23: 0; 2023-24: 100000 | 38 | IV - Deferrable
21 | Library | New Library (place holder) |  | Budget | 2019-20: 100000 | 39 | III - Desirable
|  |  | R | Bond | 0 | 0 | 0 | 0 | 0 | 0 | 6000000
22 | Parks & Recreation | New Athletic Fields (place holder) | A | Athelic Field CRF | 2023-24: 250000 |  | V - Premature
|  |  |  | Bond | 0 | 0 | 0 | 0 | 0 | 0 | 1750000
| TOTAL GENERAL FUND |  |  |  | 1422000 | 1250000 | 9992000 | 1200000 | 2220000 | 4470000 | 11952125
1 | Wastewater | Relocate sewer connector under Everett Turnpike (FKA Exec. Pk. Pump Station) | R | Wastewater CRF | 0 |  |  | 0 | 1300000 | 0 | 0 | 41 | II - Necessary
2 | Wastewater | Wastewater Treatment Plant Phase III and Pump Station Upgrades | R | User Fees State Loan SRF | 350000 | 0 | 12600000 | 0 | 0 | 0 | 0 | 43 | II - Necessary
0
| TOTAL SEWER FUND |  |  |  | 350000 | 0 | 12600000 | 0 | 1300000 | 0 | 0
|  |  |  | CRF | 348000 | 425000 | 1179400 | 300000 | 494000 | 1054200 | 1390425
|  |  |  | Funded through Budget | 625000 | 700000 | 825000 | 775000 | 825000 | 875000 | 925000
|  |  |  | Bonds | 0 | 0 | 6455000 | 0 | 0 | 0 | 7750000
|  |  |  | Road Improvement (RSA261:153) | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000
|  |  |  | Private Donation | 0 | 0 | 650000 | 0 | 0 | 0 | 0
|  |  |  | State Aid | 240000 | 0 | 0 | 0 | 0 | 2415800 | 0
|  |  |  | Federal Aid | 84000 | 0 | 757600 | 0 | 776000 | 0 | 1761700
|  |  |  | User Fees/Bonds | 350000 | 0 | 12600000 | 0 | 1300000 | 0 | 0
[5 empty] | 1772000 | 1250000 | 22592000 | 1200000 | 3520000 | 4470000 | 11952125
* Included in CIP just in case we are a recipient of TAP Grant
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
MES -
CRF - $250,000
Taxes - $35,000
Total - $285,000
RFS -
CRF - $50,000 Taxes - $90,000 Total - $140,000
Moved
Moved
MES -
CRF - $250,000
Taxes - $35,000
Total - $285,000
MES -
CRF - $250,000
Taxes - $35,000
Total - $285,000
MES -
CRF - $250,000
Taxes - $35,000
Total - $285,000
MES -
CRF - $250,000
Taxes - $35,000
Total - $285,000
RFS -
CRF - $50,000 Taxes - $90,000 Total - $140,000
Moved
Moved
MES -
CRF - $250,000
Taxes - $35,000
Total - $285,000
MES -
CRF - $250,000
Taxes - $35,000
Total - $285,000
MES -
CRF - $250,000
Taxes - $35,000
Total - $285,000

## cipminor
Schedule 3
Capital Improvements Program
MINOR PROJECTS
No | Department | Year | Replace SCH | Model |  | Funding Source | Vehicle Replacement Year | Replacement Cost |  | Current Year | YR 1 | YR 2 | YR 3 | YR 4 | YR 5 | YR 6 | YR 7 | YR 8 | YR 9 | YR 10
[10 empty] | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28
1 | Assessing |  |  | Revaluation | R | Revaluation CRF | every 5 yrs | 75000 |  | 0 | 0 | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0
2 | Bld & Grounds | 2004 | 15-20 yrs | 450 4x4 | R | Budget | 2014/15 | 40000 |  | 0 | 0 | 0 | 0 | 0 | 40000 |  | 0 | 0 | 0 | 0
3 | Bld & Grounds |  | 15-20 yrs | Small pickup | N | Budget |  |  |  | 2017/18: 0; YR 1 2018/19: 0; YR 2 2019/20: 0; YR 3 2020/21: 25000; YR 4 2021/22: 0; YR 5 2022/23: 0
4 | Bld & Grounds |  |  | HVAC (Town Hall & PD) | R | Budget |  |  |  | YR 1 2018/19: 225000
5 | Bld & Grounds |  |  | Reconstruct Parking Lots (Fire station) | R | Budget |  |  |  | YR 4 2021/22: 90000
6 | Bld & Grounds |  |  | Replace brick veneer siding | R | Budget | 0 | 0 |  |  |  |  | 75000 | 0 | 0 | 40000 | 0 | 0 | 0 | 0
7 | Bld & Grounds |  |  | Reconstruct Parking Lots (Lower PD and Adult Community Center) | R | Budget | 0 |  |  | YR 2 2019/20: 45000; YR 4 2021/22: 0; YR 5 2022/23: 0
8 | Communications |  |  | Communications Recorder | R | Communication CRF |  | 20000 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000 | 0
9 | Communications |  |  | Radio Base Stations | R | Communication CRF |  | 95000 |  | 516000 | 0 | 0 | 0 |  | 120000 | 0 | 0 | 0 | 0 | 120000
10 | Communications |  |  | Fire Dispatch, Station 1, Radio Base Stations | R | Communication CRF | 2016/17 | 43000 |  | 2017/18: 43000; YR 1 2018/19: 0; YR 2 2019/20: 0
11 | Communications |  |  | Access Control / Facility Monitoring | R | Communication CRF |  | 30000 |  | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 30000 | 0
12 | Communications |  |  | Backup console fire/police | R | Communication CRF |  | 150000 |  | 0 | 50000 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 |  | 0
13 | Communications |  |  | CAD/RMS Server replacement/Dispatch upgrade | R | Communication CRF |  | 25000 |  | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 25000 | 0 | 0
14 | Community Development |  |  | GIS Update & Maintenance Program | R | GIS CRF |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000
15 | Community Development |  |  | Pool Car | R | Budget |  |  |  | YR 1 2018/19: 20000
16 | Fire |  |  | HVAC (Central Station) |  | Budget |  |  |  | YR 6 2023/24: 25000
17 | Fire | 2017 | 100k (miles) | Ambulance 226 | R | Ambulance CRF | 2025 | 235000 |  | 235000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 250000
18 | Fire | 2016 | 100k (miles) | Ambulance 233 | R | Ambulance CRF | 2024 | 250000 |  | 0 | 0 | 0 | 0 | 0 | . | 0 | 235000 | 0 | 0 | 0
19 | Fire | 2014 | 100k (miles) | Ambulance 231 | R | Ambulance CRF | 2022 | 235000 |  | 0 | 0 | 0 | 0 | 0 | 235000 | 0 | 0 | 0 | 0 | 0
20 | Fire | 2014 | EOL | Cardiac Defibrillator/Monitor/Transmitter | R | Ambulance CRF | 2022 | 180000 |  | 0 | 0 | 0 | 0 | 0 | 180000 | 0 | 0 | 0 | 0 | 0
21 | Fire | 2014 | EOL | Automatic Rescue CPR Devices | R | Ambulance CRF | 2022 | 90000 |  | 2017/18: 0; YR 1 2018/19: 0; YR 2 2019/20: 0; YR 3 2020/21: 0; YR 4 2021/22: 0; YR 5 2022/23: 90000
22 | Fire | 2008 | 10 yrs First Due | Pumper Engine E1 | R | Fire Equip CRF | 2019 | 578000 |  | 0 | 0 | 578000 | 0 | 0 | 0 | 0 | 0 | 598000 | 0 | 0
23 | Fire | 2013 | 10 yrs First Due | Pumper Engine E2 | R | Fire Equip CRF | 2022 | 575000 |  | 2017/18: 0; YR 1 2018/19: 0; YR 2 2019/20: 0; YR 5 2022/23: 578500
24 | Fire | 1996 | 20 yr EOL Review | Pumper Engine E3 | R | Pass Down from 10 yrsFirst Due | N/A | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Fire | 2005 | 20 yr EOL Review | Pumper Engine E4 | R | Pass Down from 10 yrsFirst Due | N/A | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | Fire | 2003 | EOL | Rescue 1 Breathing Air Cascade Replacement | R | Fire Equip CRF | EOL | 25000 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | Fire | 2000 | EOL | Fire Apparatus Computer Replacemnt | R | Fire Equip CRF | EOL | 15000 |  | YR 1 2018/19: 15000; YR 2 2019/20: 15000; YR 3 2020/21: 15000
28 | Fire |  | 20 yr EOL Review | Pumper Engine 5 Reserve | R | Pass Down from 10 yrsFirst Due | EOL | 0
29 | Fire | 2017 | EOL | Pickup (1 ton) Forestry Truck F1 | R | Fire Equip CRF | 2027 | 85000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | Fire | 1968 | EOL | Pickup (1 ton) Forestry Truck F2 | R | Fire Equip CRF | 2021 | 98000 |  | 0 | 0 | 0 | 0 | 98500 | 0 | 0 | 0 | 0 | 0 | 0
31 | Fire | 1989 | EOL | Forestry Tanker Truck F3 | R | Fire Equip CRF | N/A | 175000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | Fire | 1994 | EOL | Boat Rigid Hull Inflatable | R | Fire Equip CRF | 2018 | 49000 |  | 0 | 0 | 0 | 49000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | Fire | 1994 | EOL | Boat Inflatables | R | Fire Equip CRF | 2027 | 35000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | Fire | 2002 | 25 yr | Tower/Ladder Quint | R | Fire Equip CRF | 2026 | 950000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950000 | 0
35 | Fire | 2003 | EOL | Heavy Rescue Vehicle R1 | R | Fire Equip CRF | 2024 | 653500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 653500 | 0 | 0 | 0
36 | Fire | 2001 | EOL | Rescue / Forestry UTV | R | Fire Equip CRF | 2024 | 25460 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 25460
37 | Fire | 2014 | EOL | Fire Command Vehicle | R | Fire Equip CRF | 2027 | 40000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
38 | Fire | 2010 | EOL | Fire Command Vehicle | R | Fire Equip CRF | 2021 | 40000 |  | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 35000 | 0
39 | Fire | 2002 | EOL | Fire Command Vehicle | R | Fire Equip CRF | 2018 | 39000 |  | 2017/18: 0; YR 1 2018/19: 39000; YR 2 2019/20: 0
40 | Fire | 2015 | EOL | Fire Command Vehicle | R | Fire Equip CRF | 2023 | 40000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 40000
41 | Fire | 1998 | EOL | Prevention/Inspection/Education/Utility Vehicle | R | Fire Equip CRF | 2018 | 42000 |  | 0 | 0 | 0 | 0 | 42000 |  |  | 0 | 0 | 0 | 0
42 | Fire | 2006 | EOL | 162 SD SC Chassi Utility 1 (1 ton) (6 wheel) | R | Fire Equip CRF | 2019 | 57000 |  | 0 | 0 | 0 | 57000 | 0 | 0 | 0 | 0 | 53000 | 0 | 0
43 | Fire | 2000 | EOL | Equipment Trailer | A | Fire Equip CRF | 2020 | 15000 |  | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | Fire | 2004 | EOL | Special Operation Trailer EMS / Incident Command | R | Fire Equip CRF | 2023 | 25000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0
45 | Fire | 2012 | EOL | Gator Rescue / Forestry Vehicle Trailer | R | Fire Equip CRF | 2022 | 15000 |  | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0
46 | Fire | 2011 | EOL | Hazardous Materials Trailer | R | Fire Equip CRF | 2023 | 25000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0
47 | Fire | 1995 | EOL | Thermal Imaging / Night Vision Rescue Cameras | R | Fire Equip CRF | 2018 | 80000 |  | 2017/18: 40000; YR 1 2018/19: 40000; YR 2 2019/20: 0; YR 3 2020/21: 0; YR 4 2021/22: 0; YR 5 2022/23: 0
48 | Fire | 1990 | EOL | Emergency Breathing Air (SCBA) Cascade System Replacement Replacements | R | Fire Equip CRF | 2019 | 56000 |  |  | 0 | 0 | 56000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | Fire | 2000 | EOL | Toxic Gas Monitoring Equipment | R | Fire Equip CRF | 2020 | 24000 |  | 2017/18: 0; YR 1 2018/19: 0; YR 2 2019/20: 0; YR 3 2020/21: 24000; YR 4 2021/22: 0; YR 5 2022/23: 0
50 | Fire | 1980 | EOL | Large Diameter Supply Hose | R | Fire Equip CRF | 2017 to 2019 | 43000 |  | 2017/18: 13000; YR 1 2018/19: 15000; YR 2 2019/20: 15000; YR 3 2020/21: 0; YR 4 2021/22: 0; YR 5 2022/23: 0
51 | Fire | 1980 | EOL | Fire Suppression Hose | R | Fire Equip CRF | 2018 to 2019 | 34000 |  | 2017/18: 0; YR 1 2018/19: 17000; YR 2 2019/20: 17000; YR 3 2020/21: 0; YR 4 2021/22: 0; YR 5 2022/23: 0
52 | Fire | 2000 | EOL | Portable Radios | R | Fire Equip CRF | 2018 | 245000 |  | 2017/18: 0; YR 1 2018/19: 298000; YR 2 2019/20: 0; YR 3 2020/21: 0; YR 4 2021/22: 0; YR 5 2022/23: 0
53 | Fire | 2003 | EOL | Hydraulic Rescue Tools (Jaws of Life) | R | Fire Equip CRF | 2025 | 235000 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 235000
54 | Fire | 2000 | EOL | Fire House Software Upgrades | R | Computer CRF | 2020/21 | 25000 |  | 0 |  |  | 52000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | Fire | N/A | EOL | Opticom Repair / Replace | R | Traffic Pre-emption CRF | 2017 | 25000 |  | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | Fire | N/A | EOL | Access Control / Facility Monitoring | A | Budget | 2018 | 20000 |  | 2017/18: 0; YR 1 2018/19: 20000; YR 2 2019/20: 0; YR 3 2020/21: 0; YR 4 2021/22: 0; YR 5 2022/23: 0
57 | Fire | 2000 | EOL | Building Official Vehicle (166) (Used) | R | Budget | 2018/19 | 25000 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | Fire | 2000 | EOL | Building Inspector Vehicle (184) (Used) | R | Budget | 2017/18 | 25000 |  | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | Fire | 2000 | EOL | Fire Inspector Vehicle (111) (Used) | R | Budget | 2016/17 | 25000 |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | Fire |  | EOL | Message Board | N | Budget | 2019 | 35000 |  | YR 1 2018/19: 35000; YR 3 2020/21: 0
61 | Highway | 1992 | 20 yr | Hotbox, Asphalt | R | Highway Equip CRF | 2023/24 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0
62 | Highway | 2005 | 10 yr | 6 Wheel Dump H-22 | R | Highway Equip CRF | 2016/17 | 150000 | 0 | 170000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 175000
63 | Highway | 2005 | 10 yr | 6 Wheel Dump H-34 | R | Highway Equip CRF | 2016/17 | 150000 | 0 | 170000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 175000
64 | Highway | 1990 | 25 yr | Trailer, Paint | R | Highway Equip CRF | 2017/18 | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 | Highway | 2005 | 10 yr | 6 Wheel Dump H-28 | R | Highway Equip CRF | 2017/18 | 150000 | 0 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 | Highway | 2005 | 10 yr | 6 Wheel Dump H-27 | R | Highway Equip CRF | 2017/18 | 150000 | 0 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | Highway | 2000 | 15 yr | SUV H-1 | R | Highway Equip CRF | 2018/19 | 35000 | 0 | 28000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | Highway | 2008 | 10 yr | 3/4 T Pickup H-6 | R | Highway Equip CRF | 2018/19 | 35000 | 0 | 0 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69 | Highway | 2002 | 10 yr | 6 Wheel Dump H-24 | R | Highway Equip CRF | 2014/15 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170000 | 0 | 0 | 0
70 | Highway | 2002 | 10 yr | 6 Wheel Dump H-25 | R | Highway Equip CRF | 2014/15 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170000 | 0 | 0 | 0
71 | Highway | 2002 | 10 yr | Tractor H-41 | R | Highway Equip CRF | 2014/15 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95000 | 0 | 0 | 0
72 | Highway | 1988 | 25 yr | Trailer | R | Highway Equip CRF | 2015/16 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 | Highway | 2001 | 10 yr | 6 Wheel Dump H-31 | R | Highway Equip CRF | 2015/16 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175000 | 0 | 0
74 | Highway | 2003 | 10 yr | Loader H-16 | R | Highway Equip CRF | 2015/16 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175000 | 0 | 0
75 | Highway | 2002 | 10 yr | 6 Wheel Dump H-21 | R | Highway Equip CRF | 2015/16 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 0 | 0
76 | Highway | 2017 | 10 yr | Utility Vehicle H-43 | R | Highway Equip CRF | 2016/17 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145000 | 125000
77 | Highway | 2006 | 10 yr | 3/4 T Pickup H-2 | R | Highway Equip CRF | 2016/17 | 35000 | 0 | 0 | 35000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000
78 | Highway | 2006 | 10 yr | 6 Wheel Dump H-20 | R | Highway Equip CRF | 2018/19 | 150000 | 0 | 0 | 0 | 185000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | Highway | 2006 | 10 yr | 6 Wheel Dump H-30 | R | Highway Equip CRF | 2018/19 | 150000 | 0 | 0 | 0 | 185000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | Highway | 2008 | 10 yr | 1 Ton Dump H-10 | R | Highway Equip CRF | 2018/19 | 60000 | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | Highway | 2004 | 15 yr | Tree chipper | R | Highway Equip CRF | 2019/20 | 50000 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
82 | Highway | 2006 | 12 yr | Bucket Truck H-18 | R | Highway Equip CRF | 2019/20 | 100000 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Highway | 2009 | 10 yr | 6 Wheel Dump H-35 | R | Highway Equip CRF | 2019/20 | 150000 | 0 | 0 | 0 | 0 | 185000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | Highway | 1981 | 25 yr | Trailer, Roller | R | Highway Equip CRF | 2020/21 | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | Highway | 2008 | 12 yr | 3/4 T Pickup H-4 | R | Highway Equip CRF | 2020/21 | 40000 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | Highway | 2009 | 10 yr | 6 Wheel Truck H-29 | R | Highway Equip CRF | 2020/21 | 150000 | 0 | 0 | 0 | 0 | 0 | 190000 | 0 | 0 | 0 | 0 | 0 | 0
87 | Highway | 1996 | 25 yr | Trailer | R | Highway Equip CRF | 2021/22 | 15000 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0
88 | Highway | 2011 | 10 yr | 1 Ton Dump H-7 | R | Highway Equip CRF | 2021/22 | 60000 | 0 | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0
89 | Highway | 2007 | 15 yr | Backhoe/loader H-13 | R | Highway Equip CRF | 2022/23 | 140000 | 0 | 0 | 0 | 0 | 0 | 140000 | 0 | 0 | 0 | 0 | 0 | 0
90 | Highway | 2010 | 12 yr | 10 Wheel Dump H-33 | R | Highway Equip CRF | 2022/23 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 195000 | 0 | 0 | 0 | 0 | 0
91 | Highway | 1997 | 25 yr | Grader H-12 | R | Highway Equip CRF | 2023/24 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0
92 | Highway | 1998 | 25 yr | Trailer, wash | R | Highway Equip CRF | 2023/24 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0
93 | Highway | 2008 | 15 yr | Message Board | R | Highway Equip CRF | 2023/24 | 65000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000 | 0 | 0 | 0 | 0
94 | Highway | 2008 | 15 yr | Catch Basin Cleaner H-19 | R | Highway Equip CRF | 2023/24 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170000 | 0 | 0 | 0 | 0
95 | Highway | 2013 | 10 yr | 1 Ton Dump H-9 | R | Highway Equip CRF | 2023/24 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 0
96 | Highway | 2013 | 10 yr | 1 Ton Dump H-11 | R | Highway Equip CRF | 2023/24 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 0
97 | Highway | 2013 | 10 yr | 1 Ton Dump H-8 | R | Highway Equip CRF | 2023/24 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 0
98 | Highway | 2013 | 10 yr | 6 Wheel Dump H-26 | R | Highway Equip CRF | 2023/24 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170000 | 0 | 0 | 0 | 0
99 | Highway | 2012 | 12 yr | 3/4 T Pickup H-5 | R | Highway Equip CRF | 2024/25 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 0 | 0 | 0
100 | Highway | 2002 | 25 yr | Trailer | R | Highway Equip CRF | 2027/28 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101 | Highway | 2012 | 15 yr | Utility Vehicle H-44 | R | Highway Equip CRF | 2027/28 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | Highway | 2003 | 25 yr | Trailer | R | Highway Equip CRF | 2028/29 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 | Highway | 2013 | 15 yr | Backhoe/Loader H-17 | R | Highway Equip CRF | 2028/29 | 140000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104 | Highway | 2013 | 15 yr | 6 Wheel Dump H-23 | R | Highway Equip CRF | 2028/29 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
105 | Highway | 2013 | 15 yr | 1 Ton Utility Truck, M-1 | R | Highway Equip CRF | 2028/29 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
106 | Highway | 2005 | 25 yr | Trailer | R | Highway Equip CRF | 2030/31 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
107 | Highway | 2011 | 25 yr | Roller, Steel Drum | R | Highway Equip CRF | 2035/36 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
108 | Highway | 2013 | 12 yr | 3/4 T Pickup H-3 | R | Highway Equip CRF | 2025/26 | 35000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 0 | 0
109 | Highway |  |  | H-29 Plow and spreader fit up | R | Highway Equip CRF |  |  |  | 0 | 29000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
110 | Highway |  |  | Athletic Field Groomer | R | Highway Equip CRF |  |  |  | YR 1 2018/19: 35000
111 | Highway | 2013 | 10 yr | Mower, Exmark | R | Budget | 2023/24 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0
112 | Highway | 2013 | 15 yr | Hydraulic Power Unit | R | Budget | 2028/29 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
113 | Highway | 2004 | 10 yr | Mower, Exmark | R | Budget | 2016/17 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 12000
114 | Highway | 2003 | 10 yr | Mower, Exmark | R | Budget | 2014/15 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0
115 | Highway | 2007 | 10 yr | Mower, Exmark | R | Budget | 2017/18 | 12000 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
116 | Highway | 2002 | 15 yr | Cement Mixer | R | Budget | 2017/18 | 4000 | 0 |  | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
117 | Highway |  |  | Trailer for Hot Box | R | Budget |  |  |  | 2017/18: 0; YR 1 2018/19: 16000; YR 2 2019/20: 0; YR 3 2020/21: 0; YR 4 2021/22: 0; YR 5 2022/23: 0
118 | Highway |  |  | Asphalt Milling attachment for H-43 | R | Budget |  |  |  | YR 1 2018/19: 25000
119 | Library |  |  | Book Mobile | A | Budget |  |  |  | 2017/18: 0; YR 1 2018/19: 0; YR 2 2019/20: 0; YR 3 2020/21: 0; YR 4 2021/22: 100000; YR 5 2022/23: 0
120 | Library |  |  | Granite Steps | R | Library Maintenance CRF |  |  |  | 2017/18: 0; YR 1 2018/19: 0; YR 2 2019/20: 0; YR 3 2020/21: 0; YR 4 2021/22: 0; YR 5 2022/23: 75000
121 | Library |  |  | Children Room Windows | R | Library Maintenance CRF |  |  |  | YR 2 2019/20: 75000
122 | Library |  |  | Sign | R | Library Maintenance CRF |  |  |  | YR 2 2019/20: 0; YR 3 2020/21: 75000
123 | Library |  |  | Reader Boards | R | Library Maintenance CRF |  |  |  | 2017/18: 0; YR 1 2018/19: 0; YR 2 2019/20: 0; YR 3 2020/21: 75000; YR 4 2021/22: 0; YR 5 2022/23: 0
124 | Parks and Recreation | 2013 |  | F-150 | R | Budget | 2015/16 | 30000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
125 | Parks and Recreation |  |  | Pond Dredging | A | Budget |  |  |  | 0 | 49549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
126 | Parks and Recreation |  |  | Netting Twardosky Field | A | Athelitic Field CRF |  |  |  | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
127 | Parks and Recreation |  |  | Dock Replacement | R | Budget |  |  |  | 2017/18: 0; YR 1 2018/19: 42326
128 | Parks and Recreation |  |  | O'Gara Drive renovations | R | Budget/warrant article? |  |  |  | YR 1 2018/19: 150000
129 | Parks and Recreation |  |  | Reconstruct Parking Lot (MYA) | R | Budget |  |  |  | YR 4 2021/22: 0; YR 5 2022/23: 45000
130 | Parks and Recreation |  |  | Function Hall Flooring | R | Budget |  |  |  | YR 1 2018/19: 0; YR 2 2019/20: 75000
131 | Parks and Recreation |  |  | Tennis Court resurfacing - Wasserman | R | Budget |  |  |  | 0 | 0 | 0 | 37000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
132 | Parks and Recreation |  |  | Function Hall basement Retro fit | R | Budget | Yearly | 30000 |  | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0
133 | Police | Var |  | Patrol Vehicles | R | Budget | Yearly | 30000 |  | 90000 | 90000 | 92700 | 95481 | 98345.43 | 101295.7929 | 104334.6667 | 107464.7067 | 110688.6479 | 114009.3073 | 117429.5865
134 | Police |  |  | Motorcyle | R | Budget |  |  |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0
135 | Police | Var |  | Detective Vehicles | R | Budget | every 5 yrs | 25000 |  | 0 | 0 | 0 | 30000 | 0 | 27000 | 0 | 0 | 0 | 0 | 0
136 | Police |  |  | Crime Scene vehicle replacement | R | Budget | every 10 yrs | 100000 |  | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
137 | Police | 2003 |  | Animal Control Vehicle | R | Budget | 2008/09 | 25000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
138 | Solid Waste Disposal | 2005 | 10 yr | 100 CY Trailers (4) | R | Solid Waste CRF | Various | 350000 |  | 70000 | 70000 | 0 | 70000 | 70000 | 0 | 0 | 0 | 0 | 0 | 0
139 | Solid Waste Disposal |  | 20 yr | Landfill Slope Mower | N | Solid Waste CRF | 2022/23 | 45000 |  | 0 | 0 | 45000 | 0 | 0 | 0 | 0 |  |  | 0 | 0
140 | Solid Waste Disposal | 1999 | 15 yr | Truck Cab & Chassis - Peterbilt Tractor | R | Solid Waste CRF | 2008/9 | 120000 |  | 0 | 120000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
141 | Solid Waste Disposal | 2005 | 15 yr | Truck Cab & Chassis - International Tractor | R | Solid Waste CRF |  |  |  | 2017/18: 0; YR 1 2018/19: 0; YR 2 2019/20: 0; YR 3 2020/21: 0; YR 4 2021/22: 0; YR 5 2022/23: 120000
142 | Solid Waste Disposal | 2003 | 15 yr | Fork Lift | R | Solid Waste CRF | 2018/20 | 25000 |  | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
143 | Solid Waste Disposal | 2005 | 12 yr | Transfer Station Loader | R | Solid Waste CRF | 2010/11 | 250000 |  | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
144 | Solid Waste Disposal | 2013 | 12 yr | Transfer Station Loader | R | Solid Waste CRF |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 300000
145 | Solid Waste Disposal | 2005 | 15 yr | Skid Steer Loader | R | Solid Waste CRF | 2011/12 | 32000 |  | 0 | 0 | 0 | 35000 | 0 | 0 | 0 | 0 | 0
146 | Solid Waste Disposal | 2012 | 15 yr | Skid Steer Loader | R | Solid Waste CRF |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 40000
147 | Solid Waste Disposal | 2010 | 10 yr | Pickup Trucks w/ Plow | R | Solid Waste CRF |  |  |  | 2017/18: 0; YR 1 2018/19: 0; YR 2 2019/20: 0; YR 3 2020/21: 35000; YR 4 2021/22: 0
148 | Solid Waste Disposal | 2016 | 10 yr | Pickup Trucks w/ Plow | R | Solid Waste CRF | 2020/21 | 35000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
149 | Solid Waste Disposal |  | 10 yr | Mower, Exmark | N | Budget | 2020/21 | 35000 |  | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
150 | Technology |  |  | Licenses | R | Computer CRF |  |  |  | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
151 | Technology |  |  | Campus WIFI | R | Computer CRF |  |  |  | 10000 | 0 | 0 | 0 | 0 | 0 | 0
152 | Technology |  |  | Telephone Upgrade | R | Computer CRF |  |  |  | 0 | 71310.89 | 0 | 0 | 0 | 0 | 0
153 | Town Clerk/Tax Collector |  |  | Voting Booths | R | Budget | every 10 yrs | 100000 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0
154 | Town Clerk/Tax Collector |  |  | Computer Equipment | R | Computer CRF |  | 10000 |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL GENERAL FUND | [9 empty] | 1510000 | 2056185.89 | 1636700 | 1370481 | 1313845.43 | 2121795.7929 | 901334.6667 | 1503424.7067 | 2136688.6479 | 1671009.3073 | 1254429.5865
1 | Wastewater Treatment | 2017 | ongoing | Manhole/Sewer Rehabilitation | R | User Fees |  | 25000 |  | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000
2 | Wastewater Treatment
3 | Wastewater Treatment | 1996 | 10 | CCTV Camera Equipment for Sewer System | R | User Fees |  |  |  | 2017/18: 98000
4 | Wastewater Treatment
5 | Wastewater Treatment | 2012 | 5 | 2-Bobcat Skid Steer Loaders-compost facility | R | User Fees | 2017/18 | 40000 |  | 2017/18: 40000; YR 5 2022/23: 45000; YR 10 2027/28: 50000
6 | Wastewater Treatment | 2016 | 20 | Bobcat Toolcat, trailer and accessories-X Country Sewer Maintenance | A | User Fees | 2015/16 | 75000
7 | Wastewater Treatment | 2001 | 20 | Compost Screener | R | User Fees |  |  |  | YR 4 2021/22: 200000
8 | Wastewater Treatment | 2005 | 15 | Sewer Vacuum Truck | R | User Fees | 2020/21 | 300000 |  | YR 3 2020/21: 300000
9 | Wastewater Treatment | 2005 | 15 | Ford Explorer -Sewer Inspector | R | User Fees | 2020/21 | 32000 |  | 0 | 0 | 0 | 32000 |  |  |  | 0 | 0 | 0 | 0
10 | Wastewater Treatment | 2007 | 15 | Ford Explorer -Pretreatment Manager | R | User Fees | 2021/22 | 30000 |  | YR 5 2022/23: 35000
11 | Wastewater Treatment | 2006 | 10 | Cat 938 loader C-1-compost facility | R | User Fees |  |  |  | YR 1 2018/19: 200000
12 | Wastewater Treatment | 2006 | 10 | Cat 938 loader C-2-compost facility | R | User Fees |  |  |  | YR 2 2019/20: 200000
13 | Wastewater Treatment | 2006 | 10 | Cat 938 loader C-3-compost facility | R | User Fees | 2018/19 | 600000
14 | Wastewater Treatment | 2009 | 15 | Ford Focus Assistant DPW | R | User Fees |  |  |  | YR 6 2023/24: 25000
15 | Wastewater Treatment | 2012 | 15 | Ford F-150 4X4- Maintenance | R | User Fees |  |  |  | YR 10 2027/28: 27000
16 | Wastewater Treatment | 2012 | 20 | Kenworth T-800 Roll Off truck-sludge hauling | R | User Fees
17 | Wastewater Treatment | 2014 | 10 | Ford F-250 4X4 Maintenance/plow vehicle | R | User Fees
18 | Wastewater Treatment | 2016 | 10 | Ford F-250 4X4 Maintenance/plow vehicle | R | User Fees |  |  |  | YR 8 2025/26: 36000
19 | Wastewater Treatment | 2017 | 15 | Chevrolet 350 Cut Away (Camera) Van-Sewer System CCTV & Maintenance | R | User Fees
20 | Wastewater Treatment | 2013 | 10 | Husquvarna Zero Turn riding mower | R | User Fees |  |  |  | YR 7 2024/25: 10000
21 | Wastewater Treatment | 2015 | 10 | Exmark walk behind mower | R | User Fees |  |  |  | YR 9 2026/27: 12000
22 | Wastewater Treatment | 2009 | 10 | Update Sewer Rate Study | R | User Fees |  |  |  | YR 2 2019/20: 20000
23 | Wastewater Treatment | 1970 | 20 | Replace OEM lights with new LED lights in all plant buildings | R | User Fees |  |  |  | YR 1 2018/19: 48000
24 | Wastewater Treatment | 1996 | 20 | Emergency generator- Pearson Rd pump station | R | User Fees |  |  |  | YR 4 2021/22: 20000
25 | Wastewater Treatment | 1970 | 20 | Replace two sludge pumps | R | User Fees |  |  |  | YR 1 2018/19: 25000; YR 2 2019/20: 25000
26 | Wastewater Treatment | 2007 | 10 | Replacement instrumentation controllers and probes | R | User Fees | 2016/17 | 10000 |  | 37000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
27 | Wastewater Treatment |  |  | Sewer System Assesment Program | N | User Fees |  | 33464 |  | 0 | 25315 | 14564 | 13920 | 13020 | 12500 | 0
TOTAL SEWER FUND | [9 empty] | 200000 | 323315 | 284564 | 370920 | 258020 | 117500 | 50000 | 35000 | 61000 | 77000 | 102000
1 | Cable Television |  |  | Replace Cablecast / WebCast Devices | R | Franchise Fees |  |  |  | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Cable Television |  |  | Town Hall Matthew Thornton Room Equipment | R | Franchise Fees |  |  |  |  | 40000 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0
3 | Cable Television |  |  | Town Hall Memorial Conference Room Equipment | A | Franchise Fees |  |  |  | YR 1 2018/19: 0; YR 2 2019/20: 0; YR 3 2020/21: 20000; YR 4 2021/22: 0; YR 5 2022/23: 0; YR 6 2023/24: 0
4 | Cable Television |  |  | Software | A | Franchise Fees |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Cable Television |  |  | Remote Equipment | A | Franchise Fees |  |  |  |  | 10000 | 0 | 0 | 20000 | 0 | 10000 | 0 | 0 | 0 | 0
6 | Cable Television |  |  | Public Access Studio Lighting | A | Franchise Fees |  |  |  |  | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Cable Television |  |  | Public Access Studio Equipment | A | Franchise Fees |  |  |  |  | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Cable Television |  |  | Public Access Studio Cameras and Video Switcher | R | Franchise Fees |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Cable Television |  |  | Cable Company HD Tier Upgrade | R | Franchise Fees |  |  |  | YR 1 2018/19: 0; YR 2 2019/20: 50000; YR 3 2020/21: 0; YR 4 2021/22: 0; YR 5 2022/23: 0; YR 6 2023/24: 0
10 | Cable Television |  |  | Public Access Editing Systems | R | Franchise Fees |  |  |  | YR 1 2018/19: 0; YR 2 2019/20: 0; YR 3 2020/21: 0; YR 4 2021/22: 0; YR 5 2022/23: 10000; YR 6 2023/24: 0
11 | Cable Television |  |  | Media Staff Hardware | R | Franchise Fees |  |  |  | YR 1 2018/19: 0; YR 2 2019/20: 0; YR 3 2020/21: 0; YR 4 2021/22: 0; YR 5 2022/23: 10000; YR 6 2023/24: 0
12 | Cable Television |  |  | Public Access Cameras and Audio Equipment | A | Franchise Fees |  |  |  | YR 1 2018/19: 0; YR 2 2019/20: 0; YR 3 2020/21: 0; YR 4 2021/22: 10000; YR 5 2022/23: 0; YR 6 2023/24: 0
13 | Cable Television |  |  | Lower Power FM Equipment | R | Franchise Fees |  |  |  | 20000 | 0 | 0 | 0 | 0 | 20000 | 0
14 | Cable Television |  |  | Other CATV Equipment | R | Franchise Fees |  |  |  | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000
| Total CATV FUND | [8 empty] | 50000 | 60000 | 60000 | 50000 | 40000 | 50000 | 60000 | 0 | 0 | 0 | 0
[10 empty] | 1760000 | 2439500.89 | 1981264 | 1791401 | 1611865.43 | 2289295.7929 | 1011334.6667 | 1538424.7067 | 2197688.6479 | 1748009.3073 | 1356429.5865 | 0 | 0
[6 empty] | CRF | Cap Reserve |  |  | 1420000 | 1219310.89 | 1400000 | 1108000 | 965500 | 1908500 | 720000 | 1383960 | 2026000 | 1505000 | 1125000 | 0 | 0
[6 empty] | Funded through Budget | Funded through Budget |  |  | 90000 | 836875 | 236700 | 262481 | 348345.43 | 213295.7929 | 181334.6667 | 119464.7067 | 110688.6479 | 166009.3073 | 129429.5865 | 0 | 0
[6 empty] | User Fees/Bonds | User Fees WWTF |  |  | 200000 | 323315 | 284564 | 370920 | 258020 | 117500 | 50000 | 35000 | 61000 | 77000 | 102000 | 0 | 0
[6 empty] | Cable Franchise Fees | Franchise Fees |  |  | 50000 | 60000 | 60000 | 50000 | 40000 | 50000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 1760000 | 2439500.89 | 1981264 | 1791401 | 1611865.43 | 2289295.7929 | 1011334.6667 | 1538424.7067 | 2197688.6479 | 1748009.3073 | 1356429.5865 | 0 | 0
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Public Safety Building
Capital Improvements Program
PROJECT REQUEST FORM
1. Description of Project: Public Safety Complex
Replace the South Merrimack, District Fire Station and Police Station
2a. Was this same project reflected in the prior CIP? Yes
2b. If 2a = yes, indicate areas of significant changes reflected in this Project Request Form
and briefly explain why the changes have been made: cost X ; year X ; scope __; none __
(check all that apply)
Explanation:
The replacement of the South Fire Station is urgent. The Police department is outgrowing the current station. The two departments are looking to have a space needs study completed in the upcoming fiscal year. So that a Public Safety Complex could be accurately sized.
3. Expected Useful Life: 50+ years with proper maintenance and care
4. Explanation of Need:
The South Fire Station originally constructed in 1973 as a two bay garage to house only fire apparatus. This station was expanded in the 1987 to included living quarters for 3 Fire personal. The Police Station is made up of two indivdual builds that have a common entry way built when the police department was relocated there in the 1994. The first was constructed in 1960 and the second was built in 1975.
Merrimack has had steady growth since these facilities were first open. Some of the latest growth includes: The Merrimack Premium Outlet Mall, Nanocomp, Laidlaw Freight, and future build out in the North end of the community. In addition with the age of these facilities it is hard to expand to due the fact that both of these locations are in Residentail areas and there is no availabel land surronding these facilities.
The construction of a new Public Safety Complex would allow the town's first responders to be colocated in an area of town where access to the major roads is easily available.
5. Estimated Cost:
Design | 90000
Engineering | 85000
Construction | 4210000
Equipment | 650000
Bond issue costs | 0
Temporary housing | 0
Total | 5035000
6. Financing:
Federal/State Grant | 0
Private Grant | 650000
User Fees (Sewer/Water) | 0
Sale of Replaced Asset | 0
Capital Reserve Fund | 265000
Bond Proceeds | 4095000
Property Tax | 25000
Total | 5035000
7. Impact on Operating Budget:
Personnel | 0
Maintenance | 3000
Insurance | 2500
Utilities | 6500
Total | 12000
8. Project Period:
0
Project Period:
2017-18
2018-19 | 50000
2019-20 | 4985000
2020-21
2021-22
2022-23
2023-24
Total | 5035000

## Bridge-US 3 (2)
Capital Improvements Program
PROJECT REQUEST FORM
Project: Bridge Replacement - US 3 (DW Highway) @ Baboosic Brook
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
NEW PROJECT
Explanation and Need: See attached information sheet.
Estimated Cost:
Design
Engineering - including wetlands mitigation, ROW acquisitions, permits | 436000
Construction | 2884000
Equipment
Trade-In Allowance
Total | 3320000
Financing:
State Grant (80% State Bridge Aid) | 2655800
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund (20%) (Infrastructure CRF) | 664200
Bond Proceeds
Property Tax
Total | 3320000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2017-18 | 436000
2018-19
2019-20
2020-21
2021-22
2022-23
2023-24 | 2884000
Total | 3320000

## StormwaterDrainage (2)
Capital Improvements Program
PROJECT REQUEST FORM
Project: Stormwater Drainage Improvements
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
Explanation and Need: See attached information sheet.
Estimated Cost:
Design | 30000
Engineering - including wetlands mitigation, ROW acquisitions, permits
Construction | 170000
Equipment
Trade-In Allowance
Total | 200000
Financing: (ANNUAL)
Federal/State Grant
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund (Infrastructure CRF) | 200000
Bond Proceeds
Property Tax
Total | 200000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2017-18 | 200000
2018-19 | 200000
2019-20 | 200000
2020-21 | 200000
2021-22 | 200000
2022-23 | 200000
2023-24 | 200000
Total | 1400000

## Paving (2)
Capital Improvements Program
PROJECT REQUEST FORM
Paving - Infrastructure Improvements
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
Explanation and Need: See attached information sheet. See Sunset Shores Project
Estimated Cost:
Design
Engineering - including wetlands mitigation, ROW acquisitions, permits
Construction | 750000
Equipment
Trade-In Allowance
Total
Financing: (ANNUAL)
Federal/State Grant
Private Grant
User Fees (Road Improvement Registration Fee) | 125000
Sale of Replaced Asset
Capital Reserve Fund
Bond Proceeds
Property Tax | 675000
Total | 800000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2017-18 | 750000
2018-19 | 800000
2019-20 | 850000
2020-21 | 900000
2021-22 | 950000
2022-23 | 1000000
2023-24 | 1050000
Total | 6300000

## Paving Gravel Roads (2)
Capital Improvements Program
PROJECT REQUEST FORM
Project: Paving - Gravel Roads
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: X Year: Scope: None: (Check all that apply).
Explanation and Need: See attached information sheet.
Estimated Cost:
Design
Engineering - including wetlands mitigation, ROW acquisitions, permits
Construction | 300000
Equipment
Trade-In Allowance
Total | 300000
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund (Infrastructure CRF) | 300000
Bond Proceeds
Property Tax
Total | 300000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2017-18
2018-19 | 100000
2019-20 | 100000
2020-21 | 100000
2021-22
2022-23
2023-24
Total | 300000

## Paving DW Highway (2)
Capital Improvements Program
PROJECT REQUEST FORM
Project: Paving - Daniel Webster Highway
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: X Year: Scope: None: (Check all that apply).
Explanation and Need: See attached information sheet.
Estimated Cost:
Design
Engineering - including wetlands mitigation, ROW acquisitions, permits
Construction | 400000
Equipment
Trade-In Allowance
Total | 400000
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund (DW Highway Infrastructure Account) | 400000
Bond Proceeds
Property Tax
Total | 400000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2017-18
2018-19 | 50000
2019-20
2020-21
2021-22
2022-23 | 50000
2023-24 | 300000
Total | 400000

## Wire@DWIntersection (2)
Capital Improvements Program
PROJECT REQUEST FORM
Project: Wire Road Intersection Improvements
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: X Year: Scope: None: (Check all that apply).
Explanation and Need: See attached information sheet.
Estimated Cost:
Design
Engineering - including wetlands mitigation, ROW acquisitions, permits | 230425
Construction | 921700
Equipment
Trade-In Allowance
Total | 1152125
Financing:
Federal/State Grant | 921700
Private Grant
User Fees (Unearned Impact Fees) (Reeds Ferry Crossing)
Sale of Replaced Asset
Capital Reserve Fund (Infrastructure CRF) | 230425
Bond Proceeds
Property Tax
Total | 1152125
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2017-18
2018-19
2019-20
2020-21
2021-22
2022-23
2023-24 (Scheduled for Federal FY2027) | 1152125
Total | 0

## Turkey Hill Intersection (2)
Capital Improvements Program
PROJECT REQUEST FORM
Project: Turkey Hill Road Intersection Improvements
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: X Year: Scope: None: (Check all that apply).
Explanation and Need: See attached information sheet.
Estimated Cost:
Design
Engineering - including wetlands mitigation, ROW acquisitions, permits
Construction | 300000
Equipment
Trade-In Allowance
Total | 300000
Financing:
Federal/State Grant
Private Grant
User Fees (Unearned Impact Fees) (Reeds Ferry Crossing)
Sale of Replaced Asset
Capital Reserve Fund (Infrastructure CRF) | 300000
Bond Proceeds
Property Tax
Total | 300000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2017-18
2018-19
2019-20 | 300000
2020-21
2021-22
2022-23
2023-24
Total | 300000

## Merrimack River Boat ramp (2)
Capital Improvements Program
PROJECT REQUEST FORM
Project: Merrimack River Boat Ramp Access Improvement
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
New Project.
Explanation and Need: See attached information sheet.
Estimated Cost:
Design | 0
Engineering - including wetlands mitigation, ROW acquisitions, permits | 80000
Construction | 320000
Equipment
Trade-In Allowance
Total | 400000
Financing:
Federal/State Grant | 200000
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund (Infrastructure CRF) | 200000
Bond Proceeds
Property Tax
Total | 400000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2017-18
2018-19
2019-20 | 400000
2020-21
2021-22
2022-23
2023-24
Total | 400000

## Seaverns Bridge Canoe Launc (2
Capital Improvements Program
PROJECT REQUEST FORM
Project: Seaverns Bridge Canoe Launch Ramp and Access Improvement
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
New Project.
Explanation and Need: See attached information sheet.
Estimated Cost:
Design
Engineering - including wetlands mitigation, ROW acquisitions, permits | 5000
Construction | 45000
Equipment
Trade-In Allowance
Total | 50000
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund | 50000
Bond Proceeds
Property Tax
Total
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2017-18
2018-19 | 50000
2019-20
2020-21
2021-22
2022-23
2023-24
Total | 50000

## DW & Woodbury Sidewalks (2)
Capital Improvements Program
PROJECT REQUEST FORM
Project: Sidewalk Construction: DW Highway & Woodbury Street
Project same as reflected in prior CIP? Yes: No: X
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
Explanation and Need: See Attached Information Sheet
Estimated Cost:
Design
Engineering - including wetlands mitigation, ROW acquisitions, permits | 105000
Construction | 545000
Equipment
Trade-In Allowance
Total | 650000
Financing:
Federal/State Grant | 520000
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund | 130000
Bond Proceeds
Property Tax
Total | 650000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2017-18 | 105000
2018-19
2019-20 | 545000
2020-21
2021-22
2022-23
2023-24
Total | 650000

## DW & Baboosic Sidewalks (2)
Capital Improvements Program
PROJECT REQUEST FORM
Project: Sidewalk Construction: DW Highway & Baboosic Lake Road
Project same as reflected in prior CIP? Yes: No: X
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
Explanation and Need: See Attached Information Sheet
Estimated Cost:
Design
Engineering - including wetlands mitigation, ROW acquisitions, permits | 152000
Construction | 760000
Equipment
Trade-In Allowance
Total | 912000
Financing:
Federal/State Grant | 729600
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund
Bond Proceeds
Property Tax | 182400
Total | 912000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2017-18
2018-19
2019-20 | 152000
2020-21
2021-22 | 760000
2022-23
2023-24
Total | 912000

## SIDEWALK BABOOSIC LAKE RD (2)
Capital Improvements Program
PROJECT REQUEST FORM
Project: Sidewalk Construction: Baboosic Lake Road to Middle School
Project same as reflected in prior CIP? Yes: No: X
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
Explanation and Need: See Attached Information Sheet
Estimated Cost:
Design
Engineering - including wetlands mitigation, ROW acquisitions, permits | 210000
Construction | 1050000
Equipment
Trade-In Allowance
Total | 1260000
Financing:
Federal/State Grant | 1008000
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund | 252000
Bond Proceeds
Property Tax
Total | 1260000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2017-18
2018-19
2019-20
2020-21
2021-22 | 210000
2022-23
2023-24 | 1050000
Total | 1260000

## Sewer Line Ext. (2)
Capital Improvements Program
PROJECT REQUEST FORM
Project: Sewer Line Ext.
Project same as reflected in prior CIP? Yes: No: X
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: X Year: Scope: None: (Check all that apply).
New Project.
Explanation and Need: See attached information sheet.
Estimated Cost:
Design (Complete)
Engineering - including wetlands mitigation, ROW acquisitions, permits
Construction
Equipment
Trade-In Allowance
Total | 2360000
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund
Bond Proceeds | 2360000
Property Tax
Total | 2360000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2017-18
2018-19
2019-20 | 2360000
2020-21
2021-22
2022-23
2023-24
Total | 2360000

## Library Sidewalk
Capital Improvements Program
PROJECT REQUEST FORM
Project: Library Sidewalk Replacement
Project same as reflected in prior CIP? Yes: No: X
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
Explanation and Need: replacement of all library sidewalks: along parking lot side of building;
Baboosic side and corner; DW side of building
May coincide with future renovation proejcts
Estimated Cost:
Design
Construction
Equipment
Trade-In Allowance
Total | 0
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund
Bond Proceeds
Property Tax
Total | 0
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2016-17
2017-18
2018-19
2019-20
2020-21
2021-22
2022-23 | 100000
Total | 0

## Library Slate Roof
Capital Improvements Program
PROJECT REQUEST FORM
Project: Library Slate Roof
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
Explanation and Need: Slate Roof needs to be repaired or replaced because of
leaks and ice dams.
Estimated Cost:
Design
Construction
Equipment
Trade-In Allowance
Total | 0
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund | 200000
Bond Proceeds
Property Tax
Total | 200000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2016-17
2017-18
2018-19
2019-20
2020-21
2021-22
2022-23 | 200000
Total | 200000

## Library DW Trench Drain
Capital Improvements Program
PROJECT REQUEST FORM
Project: Library DW Trench Drain Evaluation/Repair
Project same as reflected in prior CIP? Yes: No: X
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
Explanation and Need: With flooding 2 consecutive years 2016 & 2017 during heavy
summer rains, the drain in the trench should be evaluated to determine a better
configuration to prevent additional future flooding of the Children's Room
Coordinate with Town's proposed Stormwater Drain evaluation project?
Estimated Cost:
Design
Construction
Equipment
Trade-In Allowance
Total | 0
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund | 100000
Bond Proceeds
Property Tax
Total | 100000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2016-17
2017-18
2018-19
2019-20
2020-21 | 100000
2021-22
2022-23 | 0
Total | 100000

## Library Elevator
Capital Improvements Program
PROJECT REQUEST FORM
Project: Library Elevator
Project same as reflected in prior CIP? Yes: No: X
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
Explanation and Need: replacement of elevator
May coincide with future renovation projects.
Estimated Cost:
Design
Construction
Equipment
Trade-In Allowance
Total | 0
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund | 100000
Bond Proceeds
Property Tax
Total | 100000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2016-17
2017-18
2018-19
2019-20
2020-21 | 100000
2021-22
2022-23 | 0
Total | 100000

## Library Evaluation
Capital Improvements Program
PROJECT REQUEST FORM
Project: Library Evaluation
Project same as reflected in prior CIP? Yes: No: X
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
Explanation and Need: Merrimack has outgrown the 1979 library addition. The staff and
Trustees will look to hire an outside firm to evaluate the space needs that may include a
renovation, addition or new building construction. This evaluation will include consideration of
staffing levels needed for service goals that will benefit our community.
Estimated Cost:
Design
Construction
Equipment
Trade-In Allowance
Total | 0
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund | 100000
Bond Proceeds
Property Tax
Total | 100000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2016-17
2017-18
2018-19
2019-20 | 100000
2020-21
2021-22
2022-23
Total | 100000

## New Library
Capital Improvements Program
PROJECT REQUEST FORM
Project: New Library
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
Explanation and Need: Merrimack has outgrown the 1979 library addition.
Placeholder for new construction dependent on updated evaluation - see CIP for Library
Evaluation.
Estimated Cost:
Design
Construction
Equipment
Trade-In Allowance
Total | 0
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund
Bond Proceeds | 6000000
Property Tax
Total | 6000000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2016-17
2017-18
2018-19
2019-20
2020-21
2021-22
2022-23 | 6000000
Total | 6000000

## Executive Park Dr. PS (2)
Capital Improvements Program
PROJECT REQUEST FORM
Project: Executive Park Dr. pump station
Project same as reflected in prior CIP? Yes: No: X
If No, indicate area of significant change reflected and briefly explain why the
changes have been made: Cost: Year: FY Scope:
Explanation and Need: See attached information sheet
Estimated Cost:
Design
Engineering - | 260000
Construction | 1040000
Contingency
Trade-In Allowance
Total | 1300000
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water) State Revolving Loan Fund or Bond
Sale of Replaced Asset
Capital Reserve Fund | 1300000
Bond Proceeds
Property Tax
Total | 1300000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2017-18
2018-19
2019-20
2020-21
2021-22 | 1300000
2022-23
2023-24
Total | 1300000

## Phase III & PS (2)
Capital Improvements Program
PROJECT REQUEST FORM
Project: Phase III plant and TF and Souhgan pump station improvements
Project same as reflected in prior CIP? Yes: No: X
If No, indicate area of significant change reflected and briefly explain why the
changes have been made: Cost: X Year: FY 19/20 Scope: Added TF and
Souhegan pump station projects and adjusted costs for project.
Explanation and Need: See attached information sheet
Estimated Cost:
Design Final | 500000
Engineering - | 975000
Construction | 10500000
Contingency | 625000
Trade-In Allowance
Total | 12600000
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water) State Revolving Loan Fund or Bond | 12600000
Sale of Replaced Asset
Capital Reserve Fund
Bond Proceeds
Property Tax
Total | 12600000
Impact on Operating Budget:
Personnel | 0
Maintenance | -10000
Insurance | 0
Utilities | -50000
Total | -60000
Project Period:
2017-18
2018-19
2019-20 | 12600000
2020-21
2021-22
2022-23
2023-24
Total | 12600000

## master
Capital Improvements Program
PROJECT REQUEST FORM
Project:
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
Explanation and Need:
Estimated Cost:
Design
Construction
Equipment
Trade-In Allowance
Total | 0
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund
Bond Proceeds
Property Tax
Total | 0
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2016-17
2017-18
2018-19
2019-20
2020-21
2021-22
2020-22
Total | 0

## PD Siding
Capital Improvements Program
PROJECT REQUEST FORM
Project: Police Station Siding
Project same as reflected in prior CIP? Yes: No: X
If No, indicate area of significant change reflected and briefly explain why the
changes have been made: Cost: Year: FY Scope:
Explanation and Need: The brick veneer is falling off of the police station
Estimated Cost:
Design
Engineering -
Construction | 75000
Contingency
Trade-In Allowance
Total | 75000
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water) State Revolving Loan Fund or Bond
Sale of Replaced Asset
Capital Reserve Fund
Bond Proceeds
Property Tax | 75000
Total | 75000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2017-18
2018-19
2019-20
2020-21 | 75000
2021-22
2022-23
2023-24
Total | 75000

## PD_ACC Parking Lot
Capital Improvements Program
PROJECT REQUEST FORM
Project: Reconstruc Parking lot at PD and Adult Comm. Center
Project same as reflected in prior CIP? Yes: No: X
If No, indicate area of significant change reflected and briefly explain why the
changes have been made: Cost: Year: FY Scope:
Explanation and Need: The PD Rear lot and ACC lots are failing and need to be reconstructed
Estimated Cost:
Design
Engineering -
Construction | 45000
Contingency
Trade-In Allowance
Total | 45000
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water) State Revolving Loan Fund or Bond
Sale of Replaced Asset
Capital Reserve Fund
Bond Proceeds
Property Tax | 45000
Total | 45000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2017-18
2018-19
2019-20 | 45000
2020-21
2021-22
2022-23
2023-24
Total | 45000

## Library CR Windows
Capital Improvements Program
PROJECT REQUEST FORM
Project: Children's Room Window Replacement and Reconfiguration
Project same as reflected in prior CIP? Yes: No: X
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
Explanation and Need: The Children's Room windows have flooded during heavy rains two
years in a row. These windows are below street level and border a trench with a drain.
When the drain clogs or is slow to empty, the water in the trench rises and spills into the room.
We propose hiring a contractor to build up the bottom wall and design and install new, smaller
windows that are higher than the flood line.
Estimated Cost:
Design
Construction
Equipment
Trade-In Allowance
Total | 0
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund
Bond Proceeds
Property Tax
Total | 0
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2016-17
2017-18
2018-19
2019-20 | 75000
2020-21
2021-22
2022-23
Total | 75000

## Library Granite Steps
Capital Improvements Program
PROJECT REQUEST FORM
Project: Library DW Steps Replacement/Repair
Project same as reflected in prior CIP? Yes: No: X
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
Explanation and Need: Library granite steps at DW entrance are uneven;
with steps that were installed later; Iron railing is loose.
Estimated Cost:
Design
Construction
Equipment
Trade-In Allowance
Total | 0
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund
Bond Proceeds
Property Tax
Total | 0
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2016-17
2017-18
2018-19
2019-20 | 75000
2020-21
2021-22 | 75000
2022-23
Total | 75000

## Library Bookmobile
Capital Improvements Program
PROJECT REQUEST FORM
Project: Library Bookmobile
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
Explanation and Need: The Library staff and Trustees recognize the need to provide
outreach services to residents who are home bound or are otherwise not able to come to
the building. We can evaluate the possibility of using a professional vehicle to deliver materials
or to provide off site library services.
Estimated Cost:
Design
Construction
Equipment
Trade-In Allowance
Total | 0
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund
Bond Proceeds
Property Tax
Total | 0
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2016-17
2017-18
2018-19
2019-20
2020-21
2021-22
2022-23 | 100000
Total | 0

## Library Readerboard
Capital Improvements Program
PROJECT REQUEST FORM
Project: Replace Readerboard Sign at Northside
Project same as reflected in prior CIP? Yes: No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
Explanation and Need: Replacement of outdated and cumbersome Readerboard sign with
digital sign.
Estimated Cost:
Design
Construction
Equipment
Trade-In Allowance
Total | 0
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund
Bond Proceeds
Property Tax
Total | 0
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2016-17
2017-18
2018-19
2019-20
2020-21 | 75000
2021-22
2022-23
Total | 75000

## Library Baboosic Sign
Capital Improvements Program
PROJECT REQUEST FORM
Project: Library Baboosic Sign
Project same as reflected in prior CIP? Yes: No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
Explanation and Need: Residents report they don't know what the library building is.
Installation of small digital sign with "Library" at the Baboosic corner would clearly identify
the building.
Estimated Cost:
Design
Construction
Equipment
Trade-In Allowance
Total | 0
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund
Bond Proceeds
Property Tax
Total | 0
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2016-17
2017-18
2018-19
2019-20
2020-21 | 75000
2021-22
2022-23
Total | 75000

## Sewer System Evaluation
Capital Improvements Program
PROJECT REQUEST FORM
Project:
Project same as reflected in prior CIP? Yes: No:X
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: X Year: Scope: None: (Check all that apply).
Explanation and Need: Engineering level assistance to assist staff in developing a
comprehensive condition assesment of the sewer system with the goal of
planning future rehabilitation and upgrade projects utilizing Town generated videos
and rating criteria based on industry standards and incorporating into VUEWorks
asset management software. Estimated project costs will be developed from this information
starting with the most critical needs.
Estimated Cost:
Design | 112783
Construction
Equipment
Trade-In Allowance
Total | 112783
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water) | 112783
Sale of Replaced Asset
Capital Reserve Fund
Bond Proceeds
Property Tax
Total | 112783
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2017-18
2018-19 | 33464
2019-20 | 25315
2020-21 | 14564
2021-22 | 13920
2022-23 | 13020
2023-24 | 12500
Total | 112783