## ciptax
Schedule 1
Capital Improvements Program
PROJECTED MUNICIPAL PROPERTY TAX IMPACT
Capital Expenditures | [7 empty] | 2011-12 | 2012-13 | 2013-14 | 2014-15 | 2015-16 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | 2023-24 | 2024-25
Debt service on outstanding bonds | [7 empty] | 431025 | 425405.5 | 472025.5 | 461396.75 | 449873 | 406500 | 155525 | 429915 | 425435 | 415761 | 410731 | 245438 | 236240
Transfer to capital reserve funds | [7 empty] | 538960 | 937000 | 1077000 | 1446000 | 1612000 | 1697000 | 1640000 | 1665000 | 1825000 | 2005000 | 2115000 | 2200000 | 2285000
Issuance of New Debt (see below) | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 288101 | 0 | 0 | 334160 | 553672 | 542437 | 1096806
Total property tax financing of capital expenditures | [7 empty] | 969985 | 1362405.5 | 1549025.5 | 1907396.75 | 2061873 | 2103500 | 2083626 | 2094915 | 2250435 | 2754921 | 3079403 | 2987875 | 3618046
CIP Major Projects Issuance of New Debt | [7 empty] | 2011-12 | 2012-13 | 2013-14 | 2014-15 | 2015-16 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | 2023-24 | 2024-25
Public Safety Complex(20 Yr) | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 334160 | 327524 | 320889 | 314254
Highway Garage - Replacement (20 Yr) | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 288101 | 0 | 0 | 0 | 0 | 0 | 0
SLE Mayflower & McQuestion Rds (15 YRS) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226148 | 221548 | 216948
Atheletic Field (10YR) | [7 empty] | 2024-25: 220000
Library (30 Yr) | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345604
Total property tax financing of CIP major projects | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 288101 | 0 | 0 | 334160 | 553672 | 542437 | 1096806
Capital Reserve Funding
|  | Historical Funding of CRF | [5 empty] | 2012-13: Historic Funding; 2017-18: Historic Funding; 2022-23: Projected Funding
Capital Reserve Fund | balance 7/1/08 | 2001-02 | 2002-03 | 2003-04 | 2004-05 | 2005-06 | 2006-07 | 2008-09 | 2009-10 | 2010-11 | 2011-12 | 2012-13 | 2014-15 | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | 2023-24 | 2024-25
Ambulance | 208361.69 | 35000 | 35000 | 12000 | 15000 | 60000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 60000 | 85000 | 115000 | 80000 | 80000 | 80000 | 80000 | 80000 | 90000 | 90000
Athletic Field Development | 95244.31 | 75000 | 100000 | 50000 | 100000 | 75000 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 25000 | 25000 | 25000
Bridge Replacement * | 0 | 0 | 25000 | 57000 | 335000 | 60000 | 20000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Communications Equipment | 38984.72 | 35000 | 35000 | 25000 | 10000 | 25000 | 10000 | 35000 | 0 | 0 | 0 | 10000 | 25000 | 146000 | 182000 | 185000 | 125000 | 125000 | 125000 | 125000 | 100000 | 100000 | 100000
Computer Equipment | 112127.52 | 25000 | 25000 | 15000 | 0 | 50000 | 26000 | 10000 | 10000 | 5000 | 0 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 45000 | 45000 | 50000 | 50000 | 50000
Drainage Improvements * | 0 | 128000 | 38000 | 53000 | 125000 | 110000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DW Highway Intersection Improvements | 780724.83 | 50000 | 50000 | 90000 | 60000 | 80000 | 115000 | 100000 | 50000 | 0 | 25000 | 25000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 75000 | 100000 | 100000 | 150000
Fire Equipment | 523223.8 | 177000 | 177000 | 198000 | 200000 | 200000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 75000 | 95000 | 160000 | 192000 | 250000 | 250000 | 350000 | 450000 | 550000 | 650000 | 650000
Highway Equipment | 357553.18 | 160000 | 175000 | 175000 | 175000 | 225000 | 145000 | 150000 | 75000 | 168000 | 176960 | 250000 | 300000 | 300000 | 300000 | 325000 | 400000 | 400000 | 425000 | 435000 | 465000 | 500000 | 500000
Land Bank | 484146.23 | 210000 | 200000 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Landfill | 0 | 1232000 | 50000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Library Construction | 0 | 600000 | 493992 | 480245 | 95044 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Library Bld Maintenance | 26169.08 | 2000 | 2000 | 2000 | 2000 | 2000 | 1000 | 2000 | 2000 | 2000 | 2000 | 2000 | 17000 | 10000 | 35000 | 35000 | 75000 | 75000 | 100000 | 150000 | 150000 | 150000 | 175000
Northwest Fire Station *** | 0 | 85000 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Playground Equipment | 58789.92 | 25000 | 35000 | 35000 | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Real Estate Reappraisal | 6652.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 20000 | 20000 | 20000
Road Improvements | 782203.25 | 375000 | 215000 | 225000 | 300000 | 265000 | 190647 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Salt Shed | 15058.21 | 56000 | 56000 | 56000 | 30000 | 15000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sewer Line Extension | 915565.62 | 100000 | 100000 | 100000 | 100000 | 175000 | 115000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sidewalks and Bike Paths * | 0 | 30000 | 30000 | 30000 | 30000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Road Infrastructure CRF | 1108582.79 | [6 empty] | 150000 | 525000 | 0 | 185000 | 400000 | 400000 | 600000 | 600000 | 600000 | 450000 | 450000 | 425000 | 415000 | 385000 | 350000 | 350000
Solid Waste Disposal | 49130.01 | 0 | 0 | 0 | 0 | 25000 | 10000 | 90000 | 75000 | 40000 | 0 | 50000 | 75000 | 45000 | 65000 | 100000 | 125000 | 125000 | 135000 | 150000 | 150000 | 125000 | 135000
Fire Station | 0 | 71000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GIS |  | Historic Funding 2014-15: 10000; Historic Funding 2015-16: 65000; Historic Funding 2016-17: 65000; Historic Funding 2017-18: 20000; Historic Funding 2018-19: 20000; Projected Funding 2019-20: 20000; Projected Funding 2020-21: 20000; Projected Funding 2021-22: 20000; Projected Funding 2022-23: 20000; Projected Funding 2023-24: 20000; Projected Funding 2024-25: 20000
Traffic Signal Pre-emption System | 20048.44 | 0 | 0 | 85000 | 5000 | 12000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000 | 15000 | 5000 | 30000 | 20000 | 10000 | 10000 | 10000 | 10000
Wastewater Treatment Facility** | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Wastewater Treatment System** | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capital Reserve Fund Transfers | 6826515.95 | 3471000 | 1841992 | 1713245 | 1582044 | 1589000 | 857647 | 1382000 | 887000 | 365000 | 538960 | 937000 | 1052000 | 1431000 | 1602000 | 1687000 | 1630000 | 1655000 | 1815000 | 1995000 | 2105000 | 2190000 | 2275000
Expendable Trust Funds
Milfoil | 10905 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 25000 | 15000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000
Total property tax financing | [6 empty] | 867647 |  |  | 365000 | 538960 | 937000 | 1077000 | 1446000 | 1612000 | 1697000 | 1640000 | 1665000 | 1825000 | 2005000 | 2115000 | 2200000 | 2285000
Sewer Fund
Sewer Infrastructure Improvements | 955575.82 |  |  |  |  | 5650000 |  | 450000 | 500000 | 350000 | 225000 | 25000 | 25000 | 75000 | 75000 | 300000 | 300000 | 350000 | 450000 | 550000 | 500000 | 450000 | 400000
Total CRF & Expandable Trust Funds | 6837420.95 | 3471000 | 1841992 | 1713245 | 1582044 | 7239000 | 867647 | 1832000 | 1387000 | 715000 | 763960 | 962000 | 1102000 | 1521000 | 1687000 | 1997000 | 1940000 | 2015000 | 2275000 | 2555000 | 2615000 | 2650000 | 2685000
Breakdown of Funding
General Fund Expandable Trust | 10493.04 | Historical Funding of CRF 2001-02: 0; Historical Funding of CRF 2002-03: 0; Historical Funding of CRF 2003-04: 0; Historical Funding of CRF 2004-05: 0; Historical Funding of CRF 2005-06: 0; Historical Funding of CRF 2006-07: 10000; Historical Funding of CRF 2008-09: 0; Historic Funding 2009-10: 0; Historic Funding 2010-11: 0; Historic Funding 2011-12: 0; Historic Funding 2012-13: 0; Historic Funding 2014-15: 0; Historic Funding 2015-16: 0
General Fund Capital Reserve Deposits | 6577882 | Historical Funding of CRF 2001-02: 3471000; Historical Funding of CRF 2002-03: 1841992; Historical Funding of CRF 2003-04: 1713245; Historical Funding of CRF 2004-05: 1582044; Historical Funding of CRF 2005-06: 1589000; Historical Funding of CRF 2006-07: 857647; Historical Funding of CRF 2008-09: 891000; Historic Funding 2009-10: 1232000; Historic Funding 2010-11: 1516000; Historic Funding 2011-12: 1601000; Historic Funding 2012-13: 1626000; Historic Funding 2014-15: 1626000; Historic Funding 2015-16: 1676000
Sewer Fund Capital Reserve Deposits | 667547 | Historical Funding of CRF 2001-02: 0; Historical Funding of CRF 2002-03: 0; Historical Funding of CRF 2003-04: 0; Historical Funding of CRF 2004-05: 0; Historical Funding of CRF 2005-06: 5650000; Historical Funding of CRF 2006-07: 0; Historical Funding of CRF 2008-09: 0; Historic Funding 2009-10: 0; Historic Funding 2010-11: 0; Historic Funding 2011-12: 0; Historic Funding 2012-13: 0; Historic Funding 2014-15: 0; Historic Funding 2015-16: 0
| 7255922.04 | Historical Funding of CRF 2001-02: 3471000; Historical Funding of CRF 2002-03: 1841992; Historical Funding of CRF 2003-04: 1713245; Historical Funding of CRF 2004-05: 1582044; Historical Funding of CRF 2005-06: 7239000; Historical Funding of CRF 2006-07: 867647; Historical Funding of CRF 2008-09: 891000; Historic Funding 2009-10: 1232000; Historic Funding 2010-11: 1516000; Historic Funding 2011-12: 1601000; Historic Funding 2012-13: 1626000; Historic Funding 2014-15: 1626000; Historic Funding 2015-16: 1676000
Capital Reserve Spending
|  | Historical Spending of CRF | [6 empty] | Projected Spending
Capital Reserve Fund | balance 7/1/07 | 2001-02 | 2002-03 | 2003-04 | 2004-05 | 2005-06 | 2006-07 | 2007-08 | 2008-09 | 2009-10 | 2010-11 | 2011-12 | 2012-13 | 2013-14
Ambulance | 150981 | 0 | -35000 | 0 | 0 | -117701 | 0 | -135000 | 0 | 0 | -135000 | 0 | -140000 | 0
Athletic Field Development | 168435 | 0 | -9053.25 | -239194 | -27046 | 0 | 0 | -90000 | -300000 | -100000 | -350000 | -150000 | 0 | 0
Bridge Replacement | 500203 | -66673 | 0 | -36527 | -33157 | -37177 | -20429 | -385752 | -200000 | -200000 | -118333 | 0 | -20000 | -120000
Communications Equipment | 41391 | 0 | -19232 | 0 | -205319 | 0 | -6518 | -20000 | -40000 | -95000 | 0 | -25000 | 0 | 0
Computer Equipment | 115177 | 0 | 0 | -10800 | -46405.5 | -33361 | 0 | -125000 | -10000 | 0 | -10000 | 0 | -25000 | 0
Drainage Improvements | 565869 | -90613 | -16458 | 0 | 0 | 0 | 0 | 0 | -100000 | 0 | 0 | 0 | 0 | 0
DW Highway Intersection Improvements | 663324 | 0 | 0 | -22963 | -1399 | -400 | -2171 | -90000 | -79900 | -300000 | -600000 | 0 | 0 | 0
Fire Equipment | 674118 | -706763 | 0 | 0 | -384181 | 0 | 0 | 0 | -450000 | -350000 | -155000 | -450000 | -165000 | -450000
Highway Equipment | 430701 | -265524 | -77761 | -131065 | -525838 | -306141 | -112378 | -60000 | -133000 | -290000 | -270000 | -302000 | -236000 | -210000
Land Bank | 465985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Landfill | 0 | -334059.78 | -2393356.8 | -192590 | -1898614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Library Construction | 0 | 0 | -52617 | -1500 | 0 | -2900 | -2639347 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Library Roof | 24149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Northwest Fire Station | 128346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Playground Equipment | 68503 | -52732 | 0 | -56697 | 0 | 0 | 0 | 0 | -20000 | -80000 | 0 | 0 | 0 | 0
Real Estate Reappraisal | 6430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Road Improvements | 1365916 | -175000 | -44532 | -24486 | -28869 | -14084 | -22625 | -1500000 | -90000 | -700000 | 0 | 0 | -50000 | -500000
Salt Shed | 9595 | 0 | 0 | -6007.5 | -13267 | -260000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sewer Line Extension | 754641 | -206677 | -22248 | -23184 | -121709 | -298517 | 0 | 0 | -380000 | 0 | 0 | -20000 | -200000 | -250000
Sidewalks | 242167 | -270709 | 0 | -25666 | -7205 | -11001 | -18326 | -60000 | -50000 | -73440 | -494000 | -25000 | -685000 | -175000
Solid Waste Disposal | 37358 | 0 | 0 | 0 | 0 | 0 | 0 | -35000 | -30000 | -155000 | -245000 | -70000 | -70000 | 0
South Merrimack Fire Station | 145284 | 0 | -59 | -5743 | -10296 | 0 | 0 | 0 | -115000 | -30284 | 0 | 0 | 0 | 0
Traffic Signal Pre-emption System | 19309 | 0 | 0 | -85054 | 0 | 0 | 0 | -5000 | 0 | 0 | 0 | 0 | 0 | 0
WWT Facility CRF | 56173 | -176619.86 | -11107 | 2885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WWT System CRF | 611374 | -202393 | -308822 | -321512 | -335819 | -1654650 | -4311706 | -1337500 | -908600 | -800000 | -1456000 | 0 | -254000 | -1123000
Total property tax financing of capital reserve fund transfers | 7245429 | -2547763.64 | -2990246.05 | -1180103.5 | -3639124.5 | -2735932 | -7133500 | -3843252 | -2906500 | -3173724 | -3833333 | -1042000 | -1845000 | -2828000
Expendable Trust Funds
Milfoil | 10493.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total CRF & Expandable Trust Funds | 7255922.04 | -2547763.64 | -2990246.05 | -1180103.5 | -3639124.5 | -2735932 | -7133500 | -3843252 | -2906500 | -3173724 | -3833333 | -1042000 | -1845000 | -2828000
Breakdown of Funding
General Fund Expandable Trust | 10493.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
General Fund Capital Reserve Deposits | 6577882 | -2168750.78 | -2670317.05 | -861476.5 | -3303305.5 | -1081282 | -2821794 | -2505752 | -1997900 | -2373724 | -2377333 | -1042000 | -1591000 | -1705000
Sewer Fund Capital Reserve Deposits | 667547 | -379012.86 | -319929 | -318627 | -335819 | -1654650 | -4311706 | -1337500 | -908600 | -800000 | -1456000 | 0 | -254000 | -1123000
| 7255922.04 | -2547763.64 | -2990246.05 | -1180103.5 | -3639124.5 | -2735932 | -7133500 | -3843252 | -2906500 | -3173724 | -3833333 | -1042000 | -1845000 | -2828000

## Major with comments funding
Schedule 2
CAPITAL IMPROVEMENTS PROGRAM
MAJOR PROJECTS
No | Department | Project Description |  | Funding Source | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | 2023-24 | 2024-25 | Back-up on pg | Planning Board recommendation
1 | Fire | Public Safety Complex | R | Fire Station CRF (South) | 25000 | 0 | 240000 | 0 | 0 | 0 | 0 | 7 | III - Desirable
|  |  |  | Budget | 25000 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Bond |  | 0 | 4095000 | 0 | 0 | 0 | 0
|  |  |  | Private Donation |  | 0 | 650000 | 0 | 0 | 0 | 0
2 | Admin/Engineering | Bridge Replacement - US 3 (DW Highway)/Baboosic Brook ($3.320,000) | R | Road Infrastructure CRF | 0 | 0 | 0 | 0 | 664000 | 0 | 0 | 8-9 | II - Necessary
|  |  |  | State Funding | 0 | 0 | 0 | 0 | 2656000 | 0 | 0
3 | Admin/Engineering | Bridge Replacement - US 3 (DW Highway)/Souhegan River - Chamberlain Bridge | R | Road Infrastructure CRF | 0 | 0 | 8600 | 0 | 0 | 0 | 34400 | 10-11 | II - Necessary
|  |  |  | State Funding | 0 | 0 | 34400 | 0 | 0 | 0 | 137600
4 | Admin/Engineering | Stormwater Drainage Improvements / Permit Compliance | R | Road Infrastructure CRF | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 12-13 | I - Urgent
5 | Admin/Engineering | Paving - Infrastructure Improvements | R | Road Improvement (Registration Fee) | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 14-15 | I - Urgent
|  |  |  | Budget | 675000 | 725000 | 775000 | 825000 | 875000 | 925000 | 975000
6 | Admin/Engineering | Paving - Infrastructure Improvements - Gravel Roads | R | Road Infrastructure CRF | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 16-17 | IV - Deferrable
7 | Admin/Engineering | Paving - DW Highway | R | DW Highway CRF | 50000 |  |  | 0 | 50000 | 300000 | 0 | 18-19 | II - Necessary
8 | Admin./Engineering | Wire Road Intersection Improvements (TYP, FY2027) | R | Road Infrastructure CRF | 0 | 0 | 0 | 0 | 0 |  | 230425 | 20-21 | III - Desirable
|  |  |  | Federal Funding | 0 | 0 | 0 | 0 | 0 |  | 921700
9 | Admin/Engineering | Turkey Hill Road Intersection Improvements | R | Road Infrastructure CRF | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 22-23 | III - Desirable
10 | Admin/Engineering | Merrimack River Boat Ramp Access Improvement (Formally Griffin St) | R | Road Infrastructure CRF | 0 |  | 200000 | 0 | 0 | 0 | 0 | 24-25 | IV - Deferrable
|  |  |  | Federal Funding | 0 |  | 200000 | 0 | 0 | 0 | 0
11 | Admin/Engineering | Seaverns Bridge Canoe Launch Ramp Access Improvement | R | Road Infrastructure CRF | 50000 |  | 0 | 0 | 0 | 0 | 0 |  | Not Ranked
12 | Admin/Engineering | Baboosic Lake Road & Woodbury Sidewalks | R | Road Infrastructure CRF | 0 | 25600 | 0 | 155400 | 0 | 0 | 0 | 26-27 | II - Necessary
|  |  |  | Federal Funding | 0 | 102400 | 0 | 621600 | 0 | 0 | 0
13 | Admin/Engineering | Daniel Webster Sidewalk (place holder) * | R | Road Infrastructure CRF | 0 |  | 0 | 30400 | 0 | 152000 | 0 | 28-29 | II - Necessary
|  |  |  | Federal Funding | 0 |  | 0 | 121600 | 0 | 608000 | 0
14 | Admin/Engineering | Baboosic Lake Road Sidewalk (Joppa Road to Madeline Bennett) (place holder) * | R | Road Infrastructure CRF | 0 | 0 | 0 |  |  | 42000 | 0 | 30-31 | III - Desirable
|  |  |  | Federal Funding | 0 | 0 | 0 |  | 0 | 168000 | 0
15 | Admin/Engineering | Sewer Line Extensions (Mayflower and McQuestion Sewer Basins) | R | Bond | 0 |  | 0 | 0 | 2360000 | 0 | 0 | 32-33 | II - Necessary
16 | Admin/Engineering | Depot Street Boat Ramp Repairs | N | Road Infrastructure CRF | 0 | 15000 | 150000 | 0 | 0 | 0 | 0 | 34-35 | I - Urgent
17 | Library | HVAC | R | Library Maintenance CRF | 0 | 0 | 0 | 0 | 0 | 0 | 100000 |  | V - Premature
18 | Library | Sprinkler System | R | Library Maintenance CRF | 0 | 0 | 0 | 0 | 0 | 0 | 100000 |  | V - Premature
19 | Library | Sidewalk | R | Library Maintenance CRF | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 36 | V - Premature
20 | Library | Slate roof | R | Library Maintenance CRF | 0 | 0 | 0 | 0 | 0 |  | 100000 | 37 | V - Premature
21 | Library | Drainage Trench by Children's windows | R | Library Maintenance CRF | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 38
22 | Library | Elevator | R | Library Maintenance CRF | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 39 | V - Premature
23 | Library | New Library (place holder) |  | Budget | 2018-19: 0; 2019-20: 0; 2021-22: 100000 | 40-41 | V - Premature
|  |  | R | Bond | 0 | 0 | 0 | 0 | 0 | 0 | 6000000
24 | Community Development | Master Plan | R | Budget | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 42 | II - Necessary
25 | Parks & Recreation | New Athletic Fields (place holder) | A | Athletic Field CRF | 2023-24: 0; 2024-25: 250000 |  | V - Premature
|  |  |  | Bond | 0 | 0 | 0 | 0 | 0 | 0 | 1750000
| TOTAL GENERAL FUND |  |  |  | 1150000 | 1493000 | 6678000 | 2179000 | 7130000 | 2520000 | 11524125
1 | Wastewater | Relocate sewer connector under Everett Turnpike (FKA Exec. Pk. Pump Station) | R | Wastewater CRF |  |  | 0 | 500000 | 0 | 0 | 0 | 43-44 | II - Necessary
2 | Wastewater | Wastewater Treatment Plant Phase III and Pump Station Upgrades | R | User Fees State Loan SRF | 0 | 13100000 | 0 | 12000000 | 0 | 0 | 0 | 45-47 | I - Urgent
0
| TOTAL SEWER FUND |  |  |  | 0 | 13100000 | 0 | 12500000 | 0 | 0 | 0
|  |  |  | CRF | 325000 | 540600 | 798600 | 385800 | 1114000 | 694000 | 1414825
|  |  |  | Funded through Budget | 700000 | 725000 | 775000 | 925000 | 875000 | 925000 | 1175000
|  |  |  | Bonds | 0 | 0 | 4095000 | 0 | 2360000 | 0 | 7750000
|  |  |  | Road Improvement (RSA261:153) | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000
|  |  |  | Private Donation | 0 | 0 | 650000 | 0 | 0 | 0 | 0
|  |  |  | State Aid | 0 | 0 | 34400 | 0 | 2656000 | 0 | 137600
|  |  |  | Federal Aid | 0 | 102400 | 200000 | 743200 | 0 | 776000 | 921700
|  |  |  | User Fees/Bonds | 0 | 13100000 | 0 | 12500000 | 0 | 0 | 0
[5 empty] | 1150000 | 14593000 | 6678000 | 14679000 | 7130000 | 2520000 | 11524125
* Included in CIP just in case we are a recipient of TAP Grant
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
MES -
CRF - $250,000
Taxes - $35,000
Total - $285,000
RFS -
CRF - $50,000 Taxes - $90,000 Total - $140,000
Moved
Moved
MES -
CRF - $250,000
Taxes - $35,000
Total - $285,000
MES -
CRF - $250,000
Taxes - $35,000
Total - $285,000
MES -
CRF - $250,000
Taxes - $35,000
Total - $285,000
MES -
CRF - $250,000
Taxes - $35,000
Total - $285,000
RFS -
CRF - $50,000 Taxes - $90,000 Total - $140,000
Moved
Moved
MES -
CRF - $250,000
Taxes - $35,000
Total - $285,000
MES -
CRF - $250,000
Taxes - $35,000
Total - $285,000
MES -
CRF - $250,000
Taxes - $35,000
Total - $285,000
MES -
CRF - $250,000
Taxes - $35,000
Total - $285,000
MES -
CRF - $250,000
Taxes - $35,000
Total - $285,000
MES -
CRF - $250,000
Taxes - $35,000
Total - $285,000
RFS -
CRF - $50,000 Taxes - $90,000 Total - $140,000
Moved
Moved
MES -
CRF - $250,000
Taxes - $35,000
Total - $285,000
MES -
CRF - $250,000
Taxes - $35,000
Total - $285,000
MES -
CRF - $250,000
Taxes - $35,000
Total - $285,000
MES -
CRF - $250,000
Taxes - $35,000
Total - $285,000
RFS -
CRF - $50,000 Taxes - $90,000 Total - $140,000
Moved
Moved
MES -
CRF - $250,000
Taxes - $35,000
Total - $285,000
MES -
CRF - $250,000
Taxes - $35,000
Total - $285,000
MES -
CRF - $250,000
Taxes - $35,000
Total - $285,000
MES -
CRF - $250,000
Taxes - $35,000
Total - $285,000
MES -
CRF - $250,000
Taxes - $35,000
Total - $285,000

## cipminor
Schedule 3
Capital Improvements Program
MINOR PROJECTS
No | Department | Year | Replace SCH | Model |  | Funding Source | Vehicle Replacement Year | Replacement Cost | Current Year | YR 1 | YR 2 | YR 3 | YR 4 | YR 5 | YR 6 | YR 7 | YR 8 | YR 9 | YR 10
[9 empty] | 2018/19 | 2019/20 | 2020/21 | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29
1 | Assessing |  |  | Revaluation | R | Revaluation CRF | every 5 yrs | 75000 | 0 | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Bld & Grounds | 2004 | 15-20 yrs | 450 4x4 w/ Dump Body | R | Budget | 2014/15 | 45000 | 0 | 45500 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
3 | Bld & Grounds |  |  | HVAC (PD) | N | Budget |  |  | 2018/19: 0; YR 1 2019/20: 0; YR 2 2020/21: 0; YR 3 2021/22: 0; YR 4 2022/23: 0; YR 6 2024/25: 100000
4 | Bld & Grounds |  |  | HVAC (Town Hall ) | R | Budget |  |  | 2018/19: 200000
5 | Bld & Grounds |  |  | Sprinkler System Town Hall | R | Budget |  |  | YR 4 2022/23: 175000
6 | Bld & Grounds |  |  | Reconstruct Parking Lots (Fire station) | R | Budget |  |  | YR 1 2019/20: 35000; YR 3 2021/22: 55000
7 | Bld & Grounds |  |  | Replace brick veneer siding | R | Budget | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 75000 | 0 | 0 | 0 | 0
8 | Bld & Grounds |  |  | Reconstruct Parking Lots (Lower PD and Adult Community Center) | R | Budget | 0 |  | YR 2 2020/21: 45000; YR 3 2021/22: 0; YR 4 2022/23: 0
9 | Communications |  |  | Communications Recorder | R | Communication CRF |  | 20000 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 25000 | 0
10 | Communications |  |  | Radio Base Stations | R | Communication CRF |  | 95000 | 0 | 0 | 0 | 0 |  | 120000 | 0 | 0 | 0 | 0 | 0 | 120000
10 | Communications |  |  | Fire Dispatch, Station 1, Radio Base Stations | R | Communication CRF | 2016/17 | 43000 | YR 1 2019/20: 0; YR 2 2020/21: 0
11 | Communications |  |  | Access Control / Facility Monitoring | R | Communication CRF |  | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 30000 | 0
12 | Communications |  |  | Backup console fire/police | R | Communication CRF |  | 150000 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
13 | Communications |  |  | CAD/RMS Server replacement/Dispatch upgrade | R | Communication CRF |  | 25000 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0
13 | Community Development |  |  | GIS Update & Maintenance Program | R | GIS CRF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 200000
14 | Community Development |  |  | Pool Car | R | Budget |  |  | 2018/19: 20000
15 | Fire | 2019 |  | Building Upgrade to Reeds Ferry (Station 3) |  | Shed Harris Fund |  |  | 0 | 75000 | 0 | 0 | 0 | 0 |  | 0
15 | Fire | 2017 | 100k (miles) | Ambulance 226 | R | Ambulance CRF | 2025 | 235000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 250000 | 250000
16 | Fire | 2016 | 100k (miles) | Ambulance 233 | R | Ambulance CRF | 2024 | 250000 | 0 | 0 | 0 | 0 | . | 235000 | 0 | 0 | 0 | 0 | 0
16 | Fire | 2014 | 100k (miles) | Ambulance 231 | R | Ambulance CRF | 2022 | 235000 | 0 | 0 | 0 | 235000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Fire | 2014 | EOL | Cardiac Defibrillator/Monitor/Transmitter | R | Ambulance CRF | 2022 | 180000 | 0 | 0 | 0 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 0
17 | Fire | 2014 | EOL | Automatic Rescue CPR Devices | R | Ambulance CRF | 2022 | 90000 | 2018/19: 0; YR 1 2019/20: 0; YR 2 2020/21: 0; YR 3 2021/22: 0; YR 4 2022/23: 90000
18 | Fire | 2008 | 10 yrs First Due | Pumper Engine E1 | R | Fire Equip CRF | 2019 | 578000 | 0 | 0 | 578000 | 0 | 0 | 0 | 0 | 598000 | 0 | 0 | 0
19 | Fire | 2013 | 10 yrs First Due | Pumper Engine E2 | R | Fire Equip CRF | 2022 | 575000 | 2018/19: 0; YR 1 2019/20: 0; YR 4 2022/23: 0; YR 5 2023/24: 588500; YR 9 2027/28: 598000; YR 10 2028/29: 0
19 | Fire | 1996 | 20 yr EOL Review | Pumper Engine E3 | R | Pass Down from 10 yrsFirst Due | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Fire | 2005 | 20 yr EOL Review | Pumper Engine E4 | R | Pass Down from 10 yrsFirst Due | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Fire | 2003 | 20 yr EOL Review | Pumper Engine 5 Reserve | R | Pass Down from 10 yrsFirst Due | EOL | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Fire | 2000 | EOL | Fire Apparatus Computer Replacemnt | R | Fire Equip CRF | EOL | 15000 | 2018/19: 15000; YR 1 2019/20: 15000; YR 2 2020/21: 15000
21 | Fire |  |  | Asphalt Parking Area at Station 1 |  | Budget | EOL | 0
21 | Fire | 2017 | EOL | Pickup (1 ton) Forestry Truck F1 | R | Fire Equip CRF | 2027 | 85000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | Fire | 1968 | EOL | Pickup (1 ton) Forestry Truck F2 | R | Fire Equip CRF | 2021 | 98000 | 0 | 0 | 0 | 98500 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | Fire | 1989 | EOL | Forestry Tanker Truck F3 | R | Fire Equip CRF | N/A | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | Fire | 1994 | EOL | Boat Rigid Hull / Inflatable | R | Fire Equip CRF | 2018 | 49000 | 0 | 0 | 0 | 0 | 49000 | 0 | 0 | 0 | 0 | 0 | 0
23 | Fire | 1994 | EOL | Boat Inflatables | R | Fire Equip CRF | 2027 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Fire | 2002 | 25 yr. | Tower/Ladder Quint | R | Fire Equip CRF | 2026 | 950000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000 | 0 | 0
23 | Fire | 2003 | EOL | Heavy Rescue Vehicle R1 | R | Fire Equip CRF | 2024 | 653500 | 0 | 0 | 0 | 0 | 0 | 0 | 653500 | 0 | 0 | 0 | 0
24 | Fire | 2001 | EOL | Rescue / Forestry UTV | R | Fire Equip CRF | 2024 | 25460 | 2018/19: 0; YR 1 2019/20: 0; YR 2 2020/21: 0; YR 3 2021/22: 0; YR 4 2022/23: 0; YR 6 2024/25: 25460
24 | Fire | 2014 | EOL | Fire Command Vehicle | R | Fire Equip CRF | 2027 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000
25 | Fire | 2010 | EOL | Fire Command Vehicle | R | Fire Equip CRF | 2021 | 40000 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 35000 | 0 | 0
26 | Fire | 2002 | EOL | Fire Command Vehicle | R | Fire Equip CRF | 2018 | 39000 | 2018/19: 39000; YR 1 2019/20: 0
27 | Fire | 2015 | EOL | Fire Command Vehicle | R | Fire Equip CRF | 2023 | 40000 | 2018/19: 0; YR 1 2019/20: 0; YR 2 2020/21: 0; YR 3 2021/22: 0; YR 4 2022/23: 0; YR 5 2023/24: 40000
28 | Fire | 1998 | EOL | Prevention/Inspection/Education/Utility Vehicle | R | Fire Equip CRF | 2018 | 42000 | 0 | 0 | 0 | 42000 |  |  | 0 | 0 | 0 | 0 | 0
29 | Fire | 2006 | EOL | 162 SD SC Chassi Utility 1 (1 ton) (6 wheel) | R | Fire Equip CRF | 2019 | 57000 | 0 | 0 | 0 | 52000 | 0 | 0 | 0 | 53000 | 0 | 0 | 0
30 | Fire | 2000 | EOL | Equipment Trailer | A | Fire Equip CRF | 2020 | 15000 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | Fire | 2004 | EOL | Special Operation Trailer EMS / Incident Command | R | Fire Equip CRF | 2023 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0
32 | Fire | 2012 | EOL | Gator Rescue / Forestry Vehicle Trailer | R | Fire Equip CRF | 2022 | 15000 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0
33 | Fire | 2011 | EOL | Hazardous Materials Trailer | R | Fire Equip CRF | 2023 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0
33 | Fire | 1995 | EOL | Thermal Imaging / Night Vision Rescue Cameras | R | Fire Equip CRF | 2018 | 80000 | 2018/19: 0; YR 1 2019/20: 0; YR 2 2020/21: 0; YR 3 2021/22: 0; YR 4 2022/23: 0
34 | Fire | 1990 | EOL | Emergency Breathing Air (SCBA) Cascade System Replacement Replacements | R | Fire Equip CRF | 2019 | 56000 | 0 | 0 | 56000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | Fire | 2000 | EOL | Toxic Gas Monitoring Equipment | R | Fire Equip CRF | 2020 | 24000 | 2018/19: 0; YR 1 2019/20: 0; YR 2 2020/21: 24000; YR 3 2021/22: 0; YR 4 2022/23: 0
36 | Fire | 1980 | EOL | Large Diameter Supply Hose | R | Fire Equip CRF | 2017 to 2019 | 43000 | 2018/19: 15000; YR 1 2019/20: 15000; YR 2 2020/21: 0; YR 3 2021/22: 0; YR 4 2022/23: 0
37 | Fire | 1980 | EOL | Fire Suppression Hose | R | Fire Equip CRF | 2018 to 2019 | 34000 | 2018/19: 17000; YR 1 2019/20: 17000; YR 2 2020/21: 0; YR 3 2021/22: 0; YR 4 2022/23: 0
38 | Fire | 2000 | EOL | Portable Radios | R | Fire Equip CRF | 2018 | 245000 | 2018/19: 298000; YR 1 2019/20: 0; YR 2 2020/21: 0; YR 3 2021/22: 0; YR 4 2022/23: 0
38 | Fire | 2003 | EOL | Hydraulic Rescue Tools (Jaws of Life) | R | Fire Equip CRF | 2025 | 235000 | 2018/19: 0; YR 1 2019/20: 0; YR 2 2020/21: 0; YR 3 2021/22: 0; YR 4 2022/23: 0; YR 7 2025/26: 235000
39 | Fire | N/A | EOL | Opticom Repair / Replace | R | Traffic Pre-emption CRF | 2017 | 25000 | 0 | 5000 | 5000 | 2000 | 5000 | 2000 | 0 | 0 | 0 | 0 | 0
40 | Fire | N/A | EOL | Access Control / Facility Monitoring | A | Budget | 2018 | 20000 | 2018/19: 0; YR 1 2019/20: 20000; YR 2 2020/21: 0; YR 3 2021/22: 0; YR 4 2022/23: 0
41 | Fire | 2000 | EOL | Building Official Vehicle (166) (Used) | R | Budget | 2018/19 | 25000 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | Fire | 2000 | EOL | Building Inspector Vehicle (184) (Used) | R | Budget | 2017/18 | 25000 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | Fire | 2000 | EOL | Fire Inspector Vehicle (111) (Used) | R | Budget | 2016/17 | 25000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | Fire |  | EOL | Message Board | N | Budget | 2019 | 35000 | 2018/19: 0; YR 2 2020/21: 0; YR 4 2022/23: 35000
45 | Highway | 2014 | 20 yr | Hotbox, Asphalt | R | Highway Equip CRF | 2033/34 | 25000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
46 | Highway | 2018 | 12 yr | 6 Wheel Dump H-22 | R | Highway Equip CRF | 2029/30 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | Highway | 2018 | 12 yr | 6 Wheel Dump H-34 | R | Highway Equip CRF | 2029/30 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | Highway | 2018 | 25 yr | Trailer, Paint MN-267 | R | Highway Equip CRF | 2042/43 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | Highway | 2018 | 12 yr | 6 Wheel Dump H-28 | R | Highway Equip CRF | 2029/30 | 180000 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | Highway | 2018 | 12 yr | 6 Wheel Dump H-27 | R | Highway Equip CRF | 2029/30 | 180000 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | Highway | 2018 | 15 yr | SUV H-1 | R | Highway Equip CRF | 2029/30 | 40000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | Highway | 2008 | 10 yr | 3/4 T Pickup H-6 | R | Highway Equip CRF | 2018/19 | 35000 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | Highway | 2015 | 11 yr | 6 Wheel Dump H-24 | R | Highway Equip CRF | 2025/26 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 180000 | 0 | 0 | 0
49 | Highway | 2015 | 11 yr | 6 Wheel Dump H-25 | R | Highway Equip CRF | 2025/26 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 180000 | 0 | 0 | 0
48 | Highway | 2002 | 20 yr | John Deere Tractor H-41 | R | Highway Equip CRF | 2021/22 | 95000 | 0 | 0 | 0 | 95000 | 0 | 0 |  | 0 | 0 | 0 | 0
49 | Highway | 1988 | 25 yr | Trailer Landscape MN-054 | R | Highway Equip CRF | 2012/13 | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | Highway | 2017 | 11 yr | 6 Wheel Dump H-31 | R | Highway Equip CRF | 2027/28 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 180000 | 0
51 | Highway | 2015 | 10 yr | Loader H-16 | R | Highway Equip CRF | 2024/25 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0 | 0
52 | Highway | 2016 | 11 yr | 6 Wheel Dump H-21 | R | Highway Equip CRF | 2026/27 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 180000 | 0 | 0
53 | Highway | 2017 | 10 yr | Utility Trackless Sidewalk H-43 | R | Highway Equip CRF | 2026/27 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125000
50 | Highway | 2018 | 10 yr | 3/4 T Pickup H-2 | R | Highway Equip CRF | 2027/28 | 35000 | 35000 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 40000
51 | Highway | 2006 | 10 yr | 6 Wheel Dump H-20 | R | Highway Equip CRF | 2018/19 | 180000 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
52 | Highway | 2006 | 10 yr | 6 Wheel Dump H-30 | R | Highway Equip CRF | 2018/19 | 180000 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
53 | Highway | 2008 | 10 yr | 1 Ton Dump H-10 | R | Highway Equip CRF | 2018/19 | 60000 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | Highway | 2004 | 15 yr | Wood chipper | R | Highway Equip CRF | 2018/19 | 50000 | 0 | 0 |  | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0
55 | Highway | 2006 | 12 yr | Bucket Truck H-18 | R | Highway Equip CRF | 2017/18 | 100000 | 0 | 0 |  | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0
56 | Highway | 2009 | 10 yr | 6 Wheel Dump H-35 | R | Highway Equip CRF | 2018/19 | 180000 | 0 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | Highway | 1981 | 25 yr | Trailer, Roller MN-031 | R | Highway Equip CRF | 2005/06 | 15000 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | Highway | 2008 | 12 yr | 3/4 T Pickup H-4 | R | Highway Equip CRF | 2019/20 | 40000 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | Highway | 2009 | 10 yr | 6 Wheel Truck H-29 | R | Highway Equip CRF | 2018/19 | 180000 | 0 | 0 | 0 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 0
60 | Highway | 1996 | 25 yr | Trailer Landscape MN-053 | R | Highway Equip CRF | 2020/21 | 15000 | 0 | 0 | 15000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | Highway | 2011 | 10 yr | 1 Ton Dump H-7 | R | Highway Equip CRF | 2020/21 | 60000 | 0 | 0 | 60000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | Highway | 2007 | 15 yr | Backhoe/loader H-13 | R | Highway Equip CRF | 2021/22 | 140000 | 0 | 0 | 0 | 140000 |  | 0 | 0 | 0 | 0 | 0 | 0
63 | Highway | 2010 | 12 yr | 10 Wheel Dump H-33 | R | Highway Equip CRF | 2021/22 | 195000 | 0 | 0 | 0 | 195000 |  | 0 | 0 | 0 | 0 | 0 | 0
64 | Highway | 1997 | 25 yr | Grader H-12 | R | Highway Equip CRF | 2021/22 | 250000 | 0 | 0 | 0 |  | 0 | 275000 | 0 | 0 | 0 | 0 | 0
65 | Highway | 1998 | 25 yr | Trailer, Brine MN-080 | R | Highway Equip CRF | 2022/23 | 15000 | 0 | 0 | 0 | 0 | 15000 |  | 0 | 0 | 0 | 0 | 0
66 | Highway | 2008 | 18 yr | Message Board | R | Highway Equip CRF | 2025/26 | 65000 | 0 | 0 | 0 | 0 |  |  | 0 | 65000 | 0 | 0 | 0
67 | Highway | 2008 | 15 yr | Catch Basin Cleaner H-19 | R | Highway Equip CRF | 2022/23 | 185000 | 0 | 0 | 0 | 0 | 185000 |  | 0 | 0 | 0 | 0 | 0
68 | Highway | 2013 | 11 yr | 1 Ton Dump H-9 | R | Highway Equip CRF | 2023/24 | 60000 | 0 | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0
69 | Highway | 2013 | 11 yr | 1 Ton Dump H-11 | R | Highway Equip CRF | 2023/24 | 60000 | 0 | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0
70 | Highway | 2013 | 11 yr | 1 Ton Dump H-8 | R | Highway Equip CRF | 2023/24 | 60000 | 0 | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0
71 | Highway | 2014 | 11 yr | 6 Wheel Dump H-26 | R | Highway Equip CRF | 2024/25 | 180000 | 0 | 0 | 0 | 0 | 0 |  | 180000 | 0 | 0 | 0 | 0
72 | Highway | 2012 | 10 yr | 3/4 T Pickup H-5 | R | Highway Equip CRF | 2021/22 | 35000 | 0 | 0 | 0 | 35000 |  | 0 |  | 0 | 0 | 0 | 0
73 | Highway | 2002 | 25 yr | Trailer - Black MN-143 | R | Highway Equip CRF | 2026/27 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0
74 | Highway | 2012 | 15 yr | Utility MV Sidewalk Tractor H-44 | R | Highway Equip CRF | 2026/27 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0
75 | Highway | 2003 | 25 yr | Drainage Trailer MN-255 | R | Highway Equip CRF | 2027/28 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0
76 | Highway | 2013 | 15 yr | Backhoe/Loader H-17 | R | Highway Equip CRF | 2027/28 | 170000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145000 | 0
73 | Highway | 2014 | 11 yr | 6 Wheel Dump H-23 | R | Highway Equip CRF | 2024/25 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 |  | 0 | 0 | 0
74 | Highway | 2013 | 15 yr | 1 Ton Utility Truck, M-1 | R | Highway Equip CRF | 2027/28 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
75 | Highway | 2005 | 25 yr | Trailer - Black MN-122 | R | Highway Equip CRF | 2029/30 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
76 | Highway | 2011 | 25 yr | Roller, Steel Drum | R | Highway Equip CRF | 2035/36 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
77 | Highway | 2015 | 25 yr | Hudson Trailer MN-063 | R | Highway Equip CRF | 2040/41 | 15000
78 | Highway | 2016 | 15 yr | Message Board | R | Highway Equip CRF | 2030/31 | 65000
74 | Highway | 2014 | 20 yr | Kubota Tractor | R | Highway Equip CRF | 2023/24 | 95000 | YR 5 2023/24: 0; YR 6 2024/25: 95000
75 | Highway | 2013 | 11 yr | 3/4 T Pickup H-3 | R | Highway Equip CRF | 2023/24 | 35000 |  | 0 | 0 | 0 | 0 | 35000 |  |  | 0 | 0 | 0
76 | Highway | 2019 | 25 yr | Athletic Field Groomer | R | Highway Equip CRF | 2043/44 | 35000 | 2018/19: 35000
77 | Highway | 2013 | 10 yr | Mower, Exmark | R | Budget | 2022/23 | 12000 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0
78 | Highway | 2004 | 10 yr | Mower, Exmark | R | Budget | 2013/14 | 12000 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 12000 | 12000
79 | Highway | 2003 | 10 yr | Mower, Exmark | R | Budget | 2012/13 | 12000 | 0 | 12000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
80 | Highway | 2007 | 10 yr | Mower, Exmark | R | Budget | 2016/17 | 12000 | 0 |  | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | Highway | 2002 | 15 yr | Cement Mixer | R | Budget | 2016/17 | 4000 | 0 |  | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
82 | Highway | 2019 | 25 yr | Trailer for Hot Box | R | Budget |  |  | 2018/19: 16000; YR 1 2019/20: 0; YR 2 2020/21: 0; YR 3 2021/22: 0; YR 4 2022/23: 0
83 | Library |  |  | Book Mobile | A | Budget |  |  | 2018/19: 0; YR 1 2019/20: 0; YR 2 2020/21: 0; YR 3 2021/22: 100000; YR 4 2022/23: 0
84 | Library |  |  | Granite Steps | R | Library Maintenance CRF |  |  | 2018/19: 0; YR 1 2019/20: 0; YR 2 2020/21: 0; YR 3 2021/22: 0; YR 4 2022/23: 75000
85 | Library |  |  | Children Room Windows | R | Library Maintenance CRF |  |  | YR 1 2019/20: 60000
86 | Parks and Recreation | 2013 |  | F-150 | R | Budget | 2015/16 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | Parks and Recreation |  |  | Pond Dredging | A | Budget |  |  | 0 | 95000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | Parks and Recreation |  |  | Netting Twardosky Field | A | Athelitic Field CRF |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | Parks and Recreation |  |  | Dock Replacement | R | Budget |  |  | 2018/19: 0; YR 1 2019/20: 0; YR 3 2021/22: 42400
88 | Parks and Recreation |  |  | Reconstruct Parking Lot (MYA) | R | Budget |  |  | YR 3 2021/22: 0; YR 4 2022/23: 45000
89 | Parks and Recreation |  |  | Tennis Court resurfacing - Wasserman | R | Budget |  |  | 0 | 0 | 37000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | Parks and Recreation |  |  | Martel Filed lighting | A | Athelitic Field CRF |  |  | YR 3 2021/22: 150000
91 | Parks and Recreation |  |  | Function Hall basement Retro fit | R | Budget | Yearly | 30000 | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | Police | Var |  | Patrol Vehicles | R | Budget | Yearly | 30000 | 90000 | 140000 | 105000 | 108150 | 111394.5 | 114736.335 | 118178.4251 | 121723.7778 | 125375.4911 | 129136.7559 | 133010.8585
93 | Police |  |  | Motorcyle | R | Budget |  |  | 2018/19: 0; YR 1 2019/20: 0; YR 2 2020/21: 25000; YR 3 2021/22: 0; YR 4 2022/23: 0; YR 5 2023/24: 0
94 | Police | Var |  | Administrative Vehicle | R | Budget | every 5 yrs | 25000 | 0 | 0 | 30000 | 0 | 27000 | 0 | 0 | 0 | 0 | 0 | 0
95 | Police |  |  | Crime Scene vehicle replacement | R | Budget | every 10 yrs | 100000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | Police | 2003 |  | Animal Control Vehicle | R | Budget | 2008/09 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | Solid Waste Disposal | 2005 | 10 yr | 100 CY Trailer, end dump | R | Solid Waste CRF | 2014/15 |  | 70000 | 0 | 70000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | Solid Waste Disposal | 2005 | 10 yr | 100 CY Trailer, end dump |  | Solid Waste CRF | 2014/15 |  | YR 3 2021/22: 70000
98 | Solid Waste Disposal | 2018 | 10 yr | 100 CY Trailer, end dump |  | Solid Waste CRF | 2027/28 |  | YR 10 2028/29: 70000
99 | Solid Waste Disposal | 2018 | 10 yr | 100 CY Trailer, lift dump |  | Solid Waste CRF | 2027/28 |  | YR 9 2027/28: 70000
98 | Solid Waste Disposal | 1999 | 20 yr | Truck Cab & Chassis - Peterbilt Tractor | R | Solid Waste CRF | 2018/19 | 120000 | 120000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
99 | Solid Waste Disposal | 2005 | 20 yr | Truck Cab & Chassis - International Tractor | R | Solid Waste CRF | 2024/25 | 140000 | 2018/19: 0; YR 1 2019/20: 0; YR 2 2020/21: 0; YR 3 2021/22: 0; YR 4 2022/23: 140000
100 | Solid Waste Disposal | 2003 | 15 yr | Fork Lift | R | Solid Waste CRF | 2017/18 | 25000 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101 | Solid Waste Disposal | 2005 | 12 yr | Transfer Station Loader | R | Solid Waste CRF | 2017/18 | 250000 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | Solid Waste Disposal | 2013 | 12 yr | Transfer Station Loader | R | Solid Waste CRF | 2024/25 | 300000 | 2018/19: 0; YR 1 2019/20: 0; YR 2 2020/21: 0; YR 3 2021/22: 0; YR 4 2022/23: 0; YR 6 2024/25: 300000
103 | Solid Waste Disposal | 2005 | 15 yr | Skid Steer Loader | R | Solid Waste CRF | 2019/20 | 32000 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0
104 | Solid Waste Disposal | 2012 | 15 yr | Skid Steer Loader | R | Solid Waste CRF | 2026/27 | 32000 | 2018/19: 0; YR 1 2019/20: 0; YR 2 2020/21: 0; YR 3 2021/22: 0; YR 4 2022/23: 0; YR 8 2026/27: 32000
104 | Solid Waste Disposal | 2010 | 12 yr | Pickup Trucks w/ Plow | R | Solid Waste CRF | 2021/22 | 35000 | 2018/19: 0; YR 1 2019/20: 0; YR 3 2021/22: 35000
105 | Solid Waste Disposal | 2016 | 12 yr | Pickup Trucks w/ Plow | R | Solid Waste CRF | 2027/28 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40000
105 | Technology |  |  | Licenses/ equipment upgrade | R | Computer CRF |  |  | 0 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
106 | Technology |  |  | Campus WIFI | R | Computer CRF |  |  | 2018/19: 0; YR 1 2019/20: 0; YR 2 2020/21: 0; YR 3 2021/22: 0; YR 4 2022/23: 0; YR 5 2023/24: 0
106 | Technology |  |  | Telephone Upgrade | R | Computer CRF |  |  | 2018/19: 71310.89; YR 1 2019/20: 0; YR 2 2020/21: 0; YR 3 2021/22: 0; YR 4 2022/23: 0; YR 5 2023/24: 0
107 | Town Clerk/Tax Collector |  |  | Voting Booths | R | Budget | every 10 yrs | 100000 | 18690 | 18690 | 0 | 0 | 0 | 0 | 0
108 | Town Clerk/Tax Collector |  |  | Computer Equipment | R | Computer CRF |  | 10000 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0
TOTAL GENERAL FUND | [8 empty] | 1445000.89 | 1545190 | 1581000 | 1630050 | 1514394.5 | 1650236.335 | 1757138.425 | 1832723.7778 | 2299375.4911 | 1824136.7559 | 705010.8585
1 | Wastewater Treatment | 2017 | ongoing | Manhole/Sewer Rehabilitation | R | User Fees |  | 25000 | 25000 | 25000 | 25000 | 125000 | 125000 | 125000 | 125000 | 25000 | 25000 | 25000 | 25000
2 | Wastewater Treatment |  | 11 | CCTV Camera Equipment for Sewer System | R | User Fees | 2028/29 | 90000 | YR 10 2028/29: 90000
3 | Wastewater Treatment | 1996 | 6 | Bobcat Skid Steer Loaders-compost facility | R | User Fees | 2021/22 | 40000 | YR 4 2022/23: 0; YR 5 2023/24: 40000; YR 9 2027/28: 50000; YR 10 2028/29: 50000
4 | Wastewater Treatment |  | 6 | Bobcat Skid Steer Loaders-compost facility | R | User Fees | 2021/22 | 40000 | YR 4 2022/23: 0; YR 5 2023/24: 40000
5 | Wastewater Treatment | 2012 | 20 | Bobcat Toolcat, trailer and accessories-X Country Sewer Maintenance | R | User Fees | 2035/36 | 90000
5 | Wastewater Treatment | 2016 | 18 | Compost Screener | R | User Fees | 2018/19 | 305000 | YR 1 2019/20: 305000
6 | Wastewater Treatment | 2001 | 15 | Sewer Vacuum Truck | R | User Fees | 2019/20 | 300000 | YR 3 2021/22: 0; YR 4 2022/23: 370000
7 | Wastewater Treatment | 2005 | 15 | Ford Explorer -Sewer Inspector | R | User Fees | 2019/20 | 35000 | 0 | 0 | 35000 |  |  |  | 0 | 0 | 0 | 0 | 0
8 | Wastewater Treatment | 2005 | 15 | Ford Explorer -Pretreatment Manager | R | User Fees | 2021/22 | 30000 | YR 4 2022/23: 30000
9 | Wastewater Treatment | 2007 | 10 | Cat 938 loader C-1-compost facility (Bought used 2014 in 2018) | R | User Fees | 2023/24 | 240000 | 2018/19: 119000; YR 5 2023/24: 280000
10 | Wastewater Treatment | 2006 | 10 | Cat 938 loader C-2-compost facility (Bought Used 2015 in 2018) | R | User Fees | 2024/25 | 240000 | 2018/19: 119000; YR 6 2024/25: 280000
11 | Wastewater Treatment | 2006 | 10 | Cat 938 loader C-3-compost facility | R | User Fees | 2015/16 | 250000 | YR 2 2020/21: 250000
12 | Wastewater Treatment | 2006 | 15 | Ford Focus Assistant DPW | R | User Fees | 2023/24 | 25000 | YR 5 2023/24: 25000
13 | Wastewater Treatment | 2009 | 15 | Ford F-150 4X4- Maintenance | R | User Fees | 2026/27 | 35000 | YR 8 2026/27: 35000; YR 9 2027/28: 27000
14 | Wastewater Treatment | 2012 | 20 | Kenworth T-800 Roll Off truck-sludge hauling | R | User Fees | 2031/32 | 200000
13 | Wastewater Treatment | 2012 | 11 | Ford F-250 4X4 Maintenance/plow vehicle | R | User Fees | 2024/25 | 35000 | YR 6 2024/25: 35000
14 | Wastewater Treatment | 2014 | 11 | Ford F-250 4X4 Maintenance/plow vehicle | R | User Fees | 2026/27 | 35000 | YR 7 2025/26: 35000
15 | Wastewater Treatment | 2016 | 15 | Chevrolet 350 Cut Away (Camera) Van | R | User Fees | 2031/32 | 50000
14 | Wastewater Treatment | 2017 | 10 | Husquvarna Zero Turn riding mower | R | User Fees | 2022/23 | 10000 | YR 4 2022/23: 10000
15 | Wastewater Treatment | 2013 | 10 | Exmark walk behind mower | R | User Fees | 2024/25 | 7500 | YR 6 2024/25: 7500
16 | Wastewater Treatment | 2015 | 10 | Update Sewer Rate Study | R | User Fees | 2018/19 | 25000 | YR 1 2019/20: 25000
17 | Wastewater Treatment | 2009 | 20 | Replace OEM lights with new LED lights in all plant buildings | R | User Fees |  | 48000 | 2018/19: 48000
18 | Wastewater Treatment | 1970 | 20 | Emergency generator- Pearson Rd pump station | R | User Fees | 2015/16 | 20000 | YR 2 2020/21: 20000
19 | Wastewater Treatment | 1996 | 20 | Replace two sludge pumps | R | User Fees |  | 25000 | 2018/19: 25000; YR 2 2020/21: 25000
20 | Wastewater Treatment | 1970 | 10 | Replacement instrumentation controllers and probes | R | User Fees | 2026/27 | 40000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
21 | Wastewater Treatment | 2007 | 5-yr program | Sewer System Assesment Program | N | User Fees |  | 33464 | 0 | 14564 | 13920 | 13020 | 12500 | 0 | 0
TOTAL SEWER FUND | [8 empty] | 336000 | 369564 | 368920 | 138020 | 547500 | 510000 | 447500 | 60000 | 100000 | 102000 | 165000
1 | Cable Television |  |  | Cablecast and Local Head End Equipment | R | Franchise Fees |  |  | 0 | 80000 | 0 | 0 | 0 | 0 | 70000 | 0 | 0 | 0 | 0
2 | Cable Television |  |  | Town Hall Matthew Thornton Room Equipment | R | Franchise Fees |  |  | 40000 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0
3 | Cable Television |  |  | Town Hall Memorial Conference Room Equipment | R | Franchise Fees |  |  | 0 | 0 | 20000 | 0 | 0 | 0 | 0
4 | Cable Television |  |  | Software | R | Franchise Fees |  |  | 0 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 0 | 0 | 0 | 0
5 | Cable Television |  |  | Remote Equipment | A | Franchise Fees |  |  | 10000 | 0 | 0 | 20000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0
6 | Cable Television |  |  | Public Access Studio Lighting | A | Franchise Fees |  |  | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Cable Television |  |  | Public Access Studio Equipment | A | Franchise Fees |  |  | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Cable Television |  |  | Public Access Studio Cameras and Video Switcher | R | Franchise Fees |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Cable Television |  |  | Public Access Editing Systems | R | Franchise Fees |  |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0
9 | Cable Television |  |  | Media Staff Hardware | R | Franchise Fees |  |  | 0 | 0 | 10000 | 0 | 0 | 0 | 0
10 | Cable Television |  |  | Public Access Cameras and Audio Equipment | A | Franchise Fees |  |  | 0 | 0 | 0 | 10000 | 0 | 0 | 0
11 | Cable Television |  |  | Lower Power FM Equipment | R | Franchise Fees |  |  | 0 | 0 | 0 | 0 | 0 | 30000 | 0
12 | Cable Television |  |  | Other CATV Equipment | R | Franchise Fees |  |  | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000
| Total CATV FUND | [7 empty] | 60000 | 95000 | 65000 | 55000 | 55000 | 55000 | 85000 | 0 | 0 | 0 | 0
[9 empty] | 1841000.89 | 2009754 | 2014920 | 1823070 | 2116894.5 | 2215236.335 | 2289638.425 | 1892723.7778 | 2399375.4911 | 1926136.7559 | 870010.8585 | 0 | 0
[6 empty] | CRF | Cap Reserve |  | 1075310.89 | 1072000 | 1283000 | 1114500 | 1109000 | 1535500 | 1463960 | 1711000 | 2162000 | 1683000 | 560000 | 120000 | 0
[6 empty] | Funded through Budget | Funded through Budget |  | 369690 | 398190 | 298000 | 515550 | 405394.5 | 114736.335 | 293178.4251 | 121723.7778 | 137375.4911 | 141136.7559 | 145010.8585 | 0 | 0
[6 empty] | Private Donation |  |  | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | User Fees/Bonds | User Fees WWTF |  | 336000 | 369564 | 368920 | 138020 | 547500 | 510000 | 447500 | 60000 | 100000 | 102000 | 165000 | 0 | 0
[6 empty] | Cable Franchise Fees | Franchise Fees |  | 60000 | 95000 | 65000 | 55000 | 55000 | 55000 | 85000 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 1841000.89 | 2009754 | 2014920 | 1823070 | 2116894.5 | 2215236.335 | 2289638.425 | 1892723.7778 | 2399375.4911 | 1926136.7559 | 870010.8585 | 120000 | 0
[9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Public Safety Building
Capital Improvements Program
PROJECT REQUEST FORM
1. Description of Project: Public Safety Complex
Replace the South Merrimack, District Fire Station and Police Station
2a. Was this same project reflected in the prior CIP? Yes
2b. If 2a = yes, indicate areas of significant changes reflected in this Project Request Form
and briefly explain why the changes have been made: cost X ; year X ; scope __; none __
(check all that apply)
Explanation:
The replacement of the South Fire Station is urgent. The Police department is outgrowing the current station. The two departments are looking to have a space needs study completed in the upcoming fiscal year. So that a Public Safety Complex could be accurately sized.
3. Expected Useful Life: 50+ years with proper maintenance and care
4. Explanation of Need:
The South Fire Station originally constructed in 1973 as a two bay garage to house only fire apparatus. This station was expanded in the 1987 to included living quarters for 3 Fire personal. The Police Station is made up of two indivdual builds that have a common entry way built when the police department was relocated there in the 1994. The first was constructed in 1960 and the second was built in 1975.
Merrimack has had steady growth since these facilities were first open. Some of the latest growth includes: The Merrimack Premium Outlet Mall, Nanocomp, Laidlaw Freight, and future build out in the North end of the community. In addition with the age of these facilities it is hard to expand to due the fact that both of these locations are in Residentail areas and there is no availabel land surronding these facilities.
The construction of a new Public Safety Complex would allow the town's first responders to be colocated in an area of town where access to the major roads is easily available.
5. Estimated Cost:
Design | 90000
Engineering | 85000
Construction | 4210000
Equipment | 650000
Bond issue costs | 0
Temporary housing | 0
Total | 5035000
6. Financing:
Federal/State Grant | 0
Private Grant | 650000
User Fees (Sewer/Water) | 0
Sale of Replaced Asset | 0
Capital Reserve Fund | 265000
Bond Proceeds | 4095000
Property Tax | 25000
Total | 5035000
7. Impact on Operating Budget:
Personnel | 0
Maintenance | 3000
Insurance | 2500
Utilities | 6500
Total | 12000
8. Project Period:
0
Project Period:
2018-19 | 50000
2019-20
2020-21 | 4985000
2021-22
2022-23
2023-24
2024-25
Total | 5035000

## Bridge-US 3 Baboosic
Capital Improvements Program
PROJECT REQUEST FORM
Project: Bridge Replacement - US 3 (DW Highway) @ Baboosic Brook
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
NEW PROJECT
Explanation and Need: See attached information sheet.
Estimated Cost:
Design
Engineering - including wetlands mitigation, ROW acquisitions, permits | 300000
Construction | 3020000
Equipment
Trade-In Allowance
Total | 3320000
Financing:
State Grant (80% State Bridge Aid) | 2656000
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund (20%) (Infrastructure CRF) | 664000
Bond Proceeds
Property Tax
Total | 3320000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2018-19
2019-20
2020-21
2021-22
2022-23 | 3320000
2023-24
2024-25
Total | 3320000

## Bridge-US 3 Chamberlain
Capital Improvements Program
PROJECT REQUEST FORM
Project: Bridge Replacement - US 3 (DW Highway) @ Souhegan River Chamberlain
Project same as reflected in prior CIP? Yes: No: X
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: 215,000 Year: 2027 Scope: None: (Check all that apply).
NEW PROJECT
Explanation and Need: See attached information sheet.
Estimated Cost:
Design
Engineering - including wetlands mitigation, ROW acquisitions, permits | 43000
Construction | 172000
Equipment
Trade-In Allowance
Total | 215000
Financing:
State Grant (80% State Bridge Aid) | 172000
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund (20%) (Infrastructure CRF) | 43000
Bond Proceeds
Property Tax
Total | 215000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2018-19
2019-20
2020-21 | 43000
2021-22
2022-23
2023-24
2024-25 | 172000
Total | 215000

## StormwaterDrainage
Capital Improvements Program
PROJECT REQUEST FORM
Project: Stormwater Drainage Improvements
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
Explanation and Need: See attached information sheet.
Estimated Cost:
Design | 30000
Engineering - including wetlands mitigation, ROW acquisitions, permits
Construction | 170000
Equipment
Trade-In Allowance
Total | 200000
Financing: (ANNUAL)
Federal/State Grant
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund (Infrastructure CRF) | 200000
Bond Proceeds
Property Tax
Total | 200000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2018-19 | 200000
2019-20 | 200000
2020-21 | 200000
2021-22 | 200000
2022-23 | 200000
2023-24 | 200000
2024-25 | 200000
Total | 1400000

## Paving
Capital Improvements Program
PROJECT REQUEST FORM
Paving - Infrastructure Improvements
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
Explanation and Need: See attached information sheet. See Sunset Shores Project
Estimated Cost:
Design
Engineering - including wetlands mitigation, ROW acquisitions, permits
Construction | 750000
Equipment
Trade-In Allowance
Total
Financing: (ANNUAL)
Federal/State Grant
Private Grant
User Fees (Road Improvement Registration Fee) | 125000
Sale of Replaced Asset
Capital Reserve Fund
Bond Proceeds
Property Tax | 725000
Total | 850000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2018-19 | 800000
2019-20 | 850000
2020-21 | 900000
2021-22 | 950000
2022-23 | 1000000
2023-24 | 1050000
2024-25 | 1100000
Total | 6650000

## Paving Gravel Roads
Capital Improvements Program
PROJECT REQUEST FORM
Project: Paving - Gravel Roads
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: X Year: Scope: None: (Check all that apply).
Explanation and Need: See attached information sheet.
Estimated Cost:
Design
Engineering - including wetlands mitigation, ROW acquisitions, permits
Construction | 300000
Equipment
Trade-In Allowance
Total | 300000
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund (Infrastructure CRF) | 300000
Bond Proceeds
Property Tax
Total | 300000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2018-19
2019-20
2020-21
2021-22
2022-23
2023-24
2024-25 | 300000
Total | 300000

## Paving DW Highway
Capital Improvements Program
PROJECT REQUEST FORM
Project: Paving - Daniel Webster Highway
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: X Year: Scope: None: (Check all that apply).
Explanation and Need: See attached information sheet.
Estimated Cost:
Design
Engineering - including wetlands mitigation, ROW acquisitions, permits
Construction | 400000
Equipment
Trade-In Allowance
Total | 400000
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund (DW Highway Infrastructure Account) | 400000
Bond Proceeds
Property Tax
Total | 400000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2018-19 | 50000
2019-20
2020-21
2021-22
2022-23 | 50000
2023-24 | 300000
2024-25
Total | 400000

## Wire@DWIntersection
Capital Improvements Program
PROJECT REQUEST FORM
Project: Wire Road Intersection Improvements
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: X Year: Scope: None: (Check all that apply).
Explanation and Need: See attached information sheet.
Estimated Cost:
Design
Engineering - including wetlands mitigation, ROW acquisitions, permits | 230425
Construction | 921700
Equipment
Trade-In Allowance
Total | 1152125
Financing:
Federal/State Grant (80%) | 921700
Private Grant
User Fees (Unearned Impact Fees) (Reeds Ferry Crossing)
Sale of Replaced Asset
Capital Reserve Fund (Infrastructure CRF) | 230425
Bond Proceeds
Property Tax
Total | 1152125
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2018-19
2019-20
2020-21
2021-22
2022-23
2023-24
2024-25 (scheduled for 2027) | 1152125
Total | 1152125

## Turkey Hill Intersection
Capital Improvements Program
PROJECT REQUEST FORM
Project: Turkey Hill Road Intersection Improvements
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: X Year: Scope: None: (Check all that apply).
Explanation and Need: See attached information sheet.
Estimated Cost:
Design
Engineering - including wetlands mitigation, ROW acquisitions, permits
Construction | 300000
Equipment
Trade-In Allowance
Total | 300000
Financing:
Federal/State Grant
Private Grant
User Fees (Unearned Impact Fees) (Reeds Ferry Crossing)
Sale of Replaced Asset
Capital Reserve Fund (Infrastructure CRF) | 300000
Bond Proceeds
Property Tax
Total | 300000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2018-19
2019-20 | 300000
2020-21
2021-22
2022-23
2023-24
2024-25
Total | 300000

## Merrimack River Boat ramp
Capital Improvements Program
PROJECT REQUEST FORM
Project: Merrimack River Boat Ramp Access Improvement
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
New Project.
Explanation and Need: See attached information sheet.
Estimated Cost:
Design | 0
Engineering - including wetlands mitigation, ROW acquisitions, permits | 80000
Construction | 320000
Equipment
Trade-In Allowance
Total | 400000
Financing:
Federal/State Grant | 200000
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund (Infrastructure CRF) | 200000
Bond Proceeds
Property Tax
Total | 400000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2018-19
2019-20
2020-21 | 400000
2021-22
2022-23
2023-24
2024-25
Total | 400000

## Baboosic & Woodbury Sidewalk
Capital Improvements Program
PROJECT REQUEST FORM
Project: Sidewalk Construction: Baboosic Lake Rd & Woodbury Street Sidewalks
Project same as reflected in prior CIP? Yes: No: X
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
Explanation and Need: See Attached Information Sheet
Estimated Cost:
Design
Engineering - including wetlands mitigation, ROW acquisitions, permits | 128000
Construction | 777000
Equipment
Trade-In Allowance
Total | 905000
Financing:
Federal/State Grant | 724000
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund
Bond Proceeds
Property Tax | 181000
Total | 905000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2018-19
2019-20 | 128000
2020-21
2021-22 | 777000
2022-23
2023-24
2024-25
Total | 905000

## DW Highway Sidewalk
Capital Improvements Program
PROJECT REQUEST FORM
Project: Sidewalk Construction: Daniel Webster Highway Sidewalks
Project same as reflected in prior CIP? Yes: No: X
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
Explanation and Need: See Attached Information Sheet
Estimated Cost:
Design
Engineering - including wetlands mitigation, ROW acquisitions, permits | 182400
Construction | 729600
Equipment
Trade-In Allowance
Total | 912000
Financing:
Federal/State Grant | 729600
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund | 182400
Bond Proceeds
Property Tax
Total | 912000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2018-19
2019-20
2020-21
2021-22 | 152000
2022-23
2023-24 | 760000
2024-25
Total | 912000

## SIDEWALK BABOOSIC LAKE RD
Capital Improvements Program
PROJECT REQUEST FORM
Project: Sidewalk Construction: Baboosic Lake Road to Middle School
Project same as reflected in prior CIP? Yes: No: X
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
Explanation and Need: See Attached Information Sheet
Estimated Cost:
Design
Engineering - including wetlands mitigation, ROW acquisitions, permits | 210000
Construction | 1050000
Equipment
Trade-In Allowance
Total | 1260000
Financing:
Federal/State Grant | 1008000
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund | 252000
Bond Proceeds
Property Tax
Total | 1260000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2018-19
2019-20
2020-21
2021-22
2022-23
2023-24 | 210000
2024-25 (FY25/26) | 1050000
Total | 1260000

## Sewer Line Ext
Capital Improvements Program
PROJECT REQUEST FORM
Project: Sewer Line Ext.
Project same as reflected in prior CIP? Yes: No: X
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: X Year: Scope: None: (Check all that apply).
New Project.
Explanation and Need: See attached information sheet.
Estimated Cost:
Design (Complete) | 360000
Engineering - including wetlands mitigation, ROW acquisitions, permits
Construction | 2000000
Equipment
Trade-In Allowance
Total | 2360000
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water) | 2360000
Sale of Replaced Asset
Capital Reserve Fund
Bond Proceeds
Property Tax
Total | 2360000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2018-19
2019-20
2020-21
2021-22
2022-23 | 2360000
2023-24
2024-25
Total | 2360000

## Depot Street Boat Ramp Repairs
Capital Improvements Program
PROJECT REQUEST FORM
Project: Depot Street Boat ramp Repairs
Project same as reflected in prior CIP? Yes: No: X
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
New Project.
Explanation and Need: See attached information sheet.
Estimated Cost:
Design | 0
Engineering - including wetlands mitigation, ROW acquisitions, permits | 15000
Construction | 150000
Equipment
Trade-In Allowance
Total | 165000
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund (Infrastructure CRF) | 165000
Bond Proceeds
Property Tax
Total | 165000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2019-20 | 15000
2020-21 | 150000
2021-22
2022-23
2023-24
2024-25
Total | 165000

## Library Sidewalk (2)
Capital Improvements Program
PROJECT REQUEST FORM
Project: Library Sidewalk Replacement
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
Explanation and Need: replacement of all library sidewalks: along parking lot side of building;
Baboosic side and corner; DW side of building
May coincide with future renovation proejcts
Estimated Cost:
Design
Construction
Equipment
Trade-In Allowance
Total | 0
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund
Bond Proceeds
Property Tax
Total | 0
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2018-19
2019-20
2020-21
2021-22
2022-23
2023-24
2024-25 | 100000
Total | 0

## Library Slate Roof (2)
Capital Improvements Program
PROJECT REQUEST FORM
Project: Library Slate Roof
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
Explanation and Need: Slate Roof needs to be repaired or replaced because of
leaks and ice dams.
Estimated Cost:
Design
Construction
Equipment
Trade-In Allowance
Total | 0
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund | 200000
Bond Proceeds
Property Tax
Total | 200000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2018-19
2019-20
2020-21
2021-22
2022-23
2023-24
2024-25 | 200000
Total | 200000

## Library DW Trench Drain (2)
Capital Improvements Program
PROJECT REQUEST FORM
Project: Library DW Trench Drain Evaluation/Repair
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
Explanation and Need: With flooding 3 consecutive years 2016, 2017, & 2018 during heavy
summer rains, the drain in the trench should be evaluated to determine a better
configuration to prevent additional future flooding of the Children's Room
Coordinate with Town's proposed Stormwater Drain evaluation project?
Estimated Cost:
Design
Construction
Equipment
Trade-In Allowance
Total | 0
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund | 100000
Bond Proceeds
Property Tax
Total | 100000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2018-19
2019-20
2020-21
2021-22
2022-23 | 100000
2023-24
2024-25 | 0
Total | 100000

## Library Elevator (2)
Capital Improvements Program
PROJECT REQUEST FORM
Project: Library Elevator
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
Explanation and Need: replacement of elevator
May coincide with future renovation projects.
Estimated Cost:
Design
Construction
Equipment
Trade-In Allowance
Total | 0
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund | 100000
Bond Proceeds
Property Tax
Total | 100000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2018-19
2019-20
2020-21
2021-22
2022-23 | 100000
2023-24
2024-25 | 0
Total | 100000

## Library Evaluation (2)
Capital Improvements Program
PROJECT REQUEST FORM
Project: Library Evaluation
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
Explanation and Need: Merrimack has outgrown the 1979 library addition. The staff and
Trustees will look to hire an outside firm to evaluate the space needs that may include a
renovation, addition or new building construction. This evaluation will include consideration of
staffing levels needed for service goals that will benefit our community.
Estimated Cost:
Design
Construction
Equipment
Trade-In Allowance
Total | 0
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund | 100000
Bond Proceeds
Property Tax
Total | 100000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2018-19
2019-20
2020-21
2021-22 | 100000
2022-23
2023-24
2024-25
Total | 100000

## New Library (2)
Capital Improvements Program
PROJECT REQUEST FORM
Project: New Library
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
Explanation and Need: Merrimack has outgrown the 1979 library addition.
Placeholder for new construction dependent on updated evaluation - see CIP for Library
Evaluation.
Estimated Cost:
Design
Construction
Equipment
Trade-In Allowance
Total | 0
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund
Bond Proceeds | 6000000
Property Tax
Total | 6000000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2018-19
2019-20
2020-21
2021-22
2022-23
2023-24
2024-25 | 6000000
Total | 6000000

## CD - 2025 Master Plan Update
Capital Improvements Program
PROJECT REQUEST FORM
Project: 2025 Master Plan Update
Project same as reflected in prior CIP? Yes: No: X
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
Explanation and Need: funding of professional planning consultant services to assist Planning Board in unpdting to the existing 2013 Master Plan.
Estimated Cost:
Design | 200000
Construction
Equipment
Trade-In Allowance
Total | 200000
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund
Bond Proceeds
Property Tax | 200000
Total | 200000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2018-19
2019-20
2020-21
2021-22
2022-23
2023-24
2024-25 | 200000
Total | 200000

## Executive Park Dr. PS
Capital Improvements Program
PROJECT REQUEST FORM
Relocate Sewer Connector under FEET
Project same as reflected in prior CIP? Yes: No: X
If No, indicate area of significant change reflected and briefly explain why the
changes have been made: Cost: Year: FY Scope:
Explanation and Need: See attached information sheet
Estimated Cost:
Design | 50000
Engineering - | 50000
Construction | 400000
Contingency
Trade-In Allowance
Total | 500000
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water) State Revolving Loan Fund or Bond | 500000
Sale of Replaced Asset
Capital Reserve Fund
Bond Proceeds
Property Tax
Total | 500000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2018-19
2019-20
2020-21
2021-22 | 500000
2022-23
2023-24
2024-25
Total | 500000

## Phase III & PS
Capital Improvements Program
PROJECT REQUEST FORM
Project: Phase III plant and TF and Souhgan pump station improvements
Project same as reflected in prior CIP? Yes: No: X
If No, indicate area of significant change reflected and briefly explain why the
changes have been made: Cost: X Year: FY 19/20 Scope: Added TF and
Souhegan pump station projects and adjusted costs for project.
Explanation and Need: See attached information sheet
Estimated Cost:
Design Final | 1300000
Engineering -
Construction | 23800000
Contingency
Trade-In Allowance
Total | 25100000
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water) State Revolving Loan Fund or Bond | 25100
Sale of Replaced Asset
Capital Reserve Fund
Bond Proceeds
Property Tax
Total | 25100
Impact on Operating Budget:
Personnel | 0
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2018-19
2019-20 | 13100000
2020-21
2021-22 | 12000000
2022-23
2023-24
2024-25
Total | 25100000

## minor back-up sheets
Informational Sheets for Minor Projects

## Eng 1 Equip
Capital Improvements Program
PROJECT REQUEST FORM
Project: Engine 1 Replacement and Equipment
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
Explanation and Need:
Estimated Cost:
Design
Construction | 578000
Equipment | 21000
Trade-In Allowance
Total | 599000
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund
Bond Proceeds
Property Tax
Total | 0
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2018-19
2019-20 | 578000
2020-21
2021-22
2022-23
2023-24
2024-25
Total | 578000

## Wasserman Beach Reconstruction
Capital Improvements Program
PROJECT REQUEST FORM
1. Description of Project: Wasserman Park Beach Reconstruction Project
2a. Was this same project reflected in the prior CIP? Yes
2b. If 2a = yes, indicate areas of significant changes reflected in this Project Request Form
and briefly explain why the changes have been made: cost X ; year ; scope _X_; none __
(check all that apply)
Explanation: The waterfront area at Wasserman Park is the only official public swimming area in Town and it has experienced significant erosion problems, combined with ADA Access issues and poor water quality in some areas.
3. Expected Useful Life: 25 years
4. Explanation of Need: See attached
5. Estimated Cost: | 95000
Design | 0
Engineering | 0
Construction | 0
Equipment | 0
Bond issue costs | 0
Temporary housing | 0
Total | 0
6. Financing:
Federal/State Grant | 0
Private Grant | 0
User Fees (Sewer/Water) | 0
Sale of Replaced Asset | 0
Capital Reserve Fund | 0
Bond Proceeds | 0
Property Tax | 95000
Total | 95000
7. Impact on Operating Budget:
Personnel | 0
Maintenance | 0
Insurance | 0
Utilities | 0
Total | 0
8. Project Period:
2018-19
2019-20 | 95000
2020-21 | 0
2021-22 | 0
2022-23 | 0
2023-24
Total | 95000

## Tennis Court Resurfacing
Capital Improvements Program
PROJECT REQUEST FORM
1. Description of Project: Wasserman Tennis Court Resurfacing
2a. Was this same project reflected in the prior CIP? Yes
2b. If 2a = yes, indicate areas of significant changes reflected in this Project Request Form
and briefly explain why the changes have been made: cost ; year ; scope __; none __
(check all that apply)
Explanation: The Wasserman Park tennis courts
3. Expected Useful Life: 10 - 15 years
4. Explanation of Need: See attached
5. Estimated Cost: | 37000
Design | 0
Engineering | 0
Construction | 0
Equipment | 0
Bond issue costs | 0
Temporary housing | 0
Total | 0
6. Financing:
Federal/State Grant | 0
Private Grant | 0
User Fees (Sewer/Water) | 0
Sale of Replaced Asset | 0
Capital Reserve Fund | 0
Bond Proceeds | 0
Property Tax | 37000
Total | 37000
7. Impact on Operating Budget:
Personnel | 0
Maintenance | 0
Insurance | 0
Utilities | 0
Total | 0
8. Project Period:
2018-19 | 0
2019-20 | 0
2020-21 | 37000
2021-22 | 0
2022-23 | 0
2023-24 | 0
2024-25 | 0
Total | 37000

## Wasserman Park Dock Replacement
Capital Improvements Program
PROJECT REQUEST FORM
1. Description of Project: Wasserman Park Dock Replacement
2a. Was this same project reflected in the prior CIP? Yes
2b. If 2a = yes, indicate areas of significant changes reflected in this Project Request Form
and briefly explain why the changes have been made: cost X ; year X ; scope _X_; none __
(check all that apply)
Explanation:The existing waterfront docks at Wasserman Park have been in use since 1992 are are nearing the end of their natural life span.
3. Expected Useful Life: 25 - 30 years
4. Explanation of Need:
5. Estimated Cost: | 42400
Design | 0
Engineering | 0
Construction | 0
Equipment | 0
Bond issue costs | 0
Temporary housing | 0
Total | 0
6. Financing:
Federal/State Grant | 0
Private Grant | 0
User Fees (Sewer/Water) | 0
Sale of Replaced Asset | 0
Capital Reserve Fund | 0
Bond Proceeds | 42400
Property Tax | 0
Total | 42400
7. Impact on Operating Budget:
Personnel | 0
Maintenance | 0
Insurance | 0
Utilities | 0
Total | 0
8. Project Period:
2018-19 | 0
2019-20 | 0
2020-21 | 0
2021-22 | 42400
2022-23 | 0
2023-24 | 0
2024-25 | 0
Total | 42400

## Function Hall basement
Capital Improvements Program
PROJECT REQUEST FORM
1. Description of Project: Function Hall Basement
2a. Was this same project reflected in the prior CIP? Yes
2b. If 2a = yes, indicate areas of significant changes reflected in this Project Request Form
and briefly explain why the changes have been made: cost ; year ; scope __; none X_
(check all that apply)
Explanation: Finish the space and turn basement into a group of smaller meeting and activty rooms.
3. Expected Useful Life: 30 years
4. Explanation of Need: See Attached
5. Estimated Cost: | 60000
Design | 0
Engineering | 0
Construction | 0
Equipment | 0
Bond issue costs | 0
Temporary housing | 0
Total | 0
6. Financing:
Federal/State Grant | 0
Private Grant | 0
User Fees (Sewer/Water) | 0
Sale of Replaced Asset | 0
Capital Reserve Fund
Bond Proceeds | 0
Property Tax | 60000
Total | 60000
7. Impact on Operating Budget:
Personnel | 0
Maintenance | 0
Insurance | 0
Utilities | 0
Total | 0
8. Project Period:
2018-19 | 0
2019-20 | 0
2020-21 | 0
2021-22 | 60000
2022-23 | 0
2023-24 | 0
2024-25 | 0
Total | 60000

## PD Siding (2)
Capital Improvements Program
PROJECT REQUEST FORM
Project: Police Station Siding
Project same as reflected in prior CIP? Yes: No: X
If No, indicate area of significant change reflected and briefly explain why the
changes have been made: Cost: Year: FY Scope:
Explanation and Need: The brick veneer is falling off of the police station
Estimated Cost:
Design
Engineering -
Construction | 115000
Contingency
Trade-In Allowance
Total | 115000
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water) State Revolving Loan Fund or Bond
Sale of Replaced Asset
Capital Reserve Fund
Bond Proceeds
Property Tax | 115000
Total | 115000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2018-19
2019-20
2020-21
2021-22 | 75000
2022-23
2023-24
2024-25 | 40000
Total | 115000

## PD_ACC Parking Lot (2)
Capital Improvements Program
PROJECT REQUEST FORM
Project: Reconstruc Parking lot at PD and Adult Comm. Center
Project same as reflected in prior CIP? Yes: No: X
If No, indicate area of significant change reflected and briefly explain why the
changes have been made: Cost: Year: FY Scope:
Explanation and Need: The PD Rear lot and ACC lots are failing and need to be reconstructed
Estimated Cost:
Design
Engineering -
Construction | 45000
Contingency
Trade-In Allowance
Total | 45000
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water) State Revolving Loan Fund or Bond
Sale of Replaced Asset
Capital Reserve Fund
Bond Proceeds
Property Tax | 45000
Total | 45000
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2018-19
2019-20
2020-21 | 45000
2021-22
2022-23
2023-24
2024-25
Total | 45000

## Library CR Windows (2)
Capital Improvements Program
PROJECT REQUEST FORM
Project: Children's Room Window Replacement and Reconfiguration
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
Explanation and Need: The Children's Room windows have flooded during heavy rains three
years in a row. These windows are below street level and border a trench with a drain.
When the drain clogs or is slow to empty, the water in the trench rises and spills into the room.
We propose hiring a contractor to build up the bottom wall and design and install new, smaller
windows that are higher than the flood line.
Estimated Cost:
Design
Engineering -
Construction
Equipment
Trade-In Allowance
Total | 0
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund
Bond Proceeds
Property Tax
Total | 0
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2018-19
2019-20
2020-21
2021-22 | 75000
2022-23
2023-24
2024-25
Total | 75000

## Library Granite Steps (2)
Capital Improvements Program
PROJECT REQUEST FORM
Project: Library DW Steps Replacement/Repair
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
Explanation and Need: Library granite steps at DW entrance are uneven;
with steps that were installed later; Iron railing is loose.
Estimated Cost:
Design
Engineering -
Construction
Equipment
Trade-In Allowance
Total | 0
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund
Bond Proceeds
Property Tax
Total | 0
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2018-19
2019-20
2020-21
2021-22 | 75000
2022-23
2023-24 | 75000
2024-25
Total | 75000

## Library Bookmobile (2)
Capital Improvements Program
PROJECT REQUEST FORM
Project: Library Bookmobile
Project same as reflected in prior CIP? Yes: X No:
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: Year: Scope: None: (Check all that apply).
Explanation and Need: The Library staff and Trustees recognize the need to provide
outreach services to residents who are home bound or are otherwise not able to come to
the building. We can evaluate the possibility of using a professional vehicle to deliver materials
or to provide off site library services.
Estimated Cost:
Design
Engineering -
Construction
Equipment
Trade-In Allowance
Total | 0
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water)
Sale of Replaced Asset
Capital Reserve Fund
Bond Proceeds
Property Tax
Total | 0
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2018-19
2019-20
2020-21
2021-22
2022-23
2023-24
2024-25 | 100000
Total | 0

## Sewer System Evaluation
Capital Improvements Program
PROJECT REQUEST FORM
Project: Sewer System Evaluation
Project same as reflected in prior CIP? Yes: No:X
If No, indicate area of significant change reflected and briefly explain why the changes have
been made: Cost: X Year: Scope: None: (Check all that apply).
Explanation and Need: Engineering level assistance to assist staff in developing a
comprehensive condition assesment of the sewer system with the goal of
planning future rehabilitation and upgrade projects utilizing Town generated videos
and rating criteria based on industry standards and incorporating into VUEWorks
asset management software. Estimated project costs will be developed from this information
starting with the most critical needs.
Estimated Cost:
Design | 112783
Engineering -
Construction
Equipment
Trade-In Allowance
Total | 112783
Financing:
Federal/State Grant
Private Grant
User Fees (Sewer/Water) | 112783
Sale of Replaced Asset
Capital Reserve Fund
Bond Proceeds
Property Tax
Total | 112783
Impact on Operating Budget:
Personnel
Maintenance
Insurance
Utilities
Total | 0
Project Period:
2018-19
2019-20 | 33464
2020-21 | 25315
2021-22 | 14564
2022-23 | 13920
2023-24 | 13020
2024-25 | 12500
Total | 112783